## Slide 1: The DOE Supported Effort to Complete the MICE Ionization Cooling Demonstration
Mark Palmer
Fermilab
June 8, 2015

## Slide 2: Preface
Would first like to follow up on Ken’s remarks:
  The MICE experimental program is now starting to launch
    Supported by strong STFC and DOE commitments to complete construction expeditiously
  NSF has played a major role in supporting experimenters and deploying hardware for the experiment
    Major investment by the agency and by the research groups
  There is now unique opportunity to exploit the experiment
    Results are absolutely necessary if a neutrino factory successor to the long baseline effort is required
    Consistent with the overall P5 consensus that a neutrino factory remains a possibility for the future

## Slide 3: Key Updates Since Our Last Meeting
In January…
  Presented the re-baselined MICE plan
  We were in the midst of…
    Completing MICE Step IV Construction Activities
    Conducting the remaining critical design and R&D steps towards the Ionization Cooling Demonstration
Now…
  MICE Step IV Hardware a DELIVERED!
  Cooling Demonstration RF R&D Results a DELIVERED!
  Cooling Demonstration Design Work a Ready for procurement process a HARDWARE Deliveries expected Feb-June 2016 a Thus enabling cooling demonstration operations by mid-2017

## Slide 4: MICE Step IV PRY Installation

## Slide 5: MICE & MuCool Test Area
MICE 201 MHz RF Module – MTA Acceptance Test in B-field Complete 11MV/m in Fringe of 5T Lab-G Solenoid
<4×10-7 Spark Rate (0 observed)

## Slide 6: MICE Cooling Demonstration Design

## Slide 7: Fermilab’s MTA RF R&D
R&D Status as of May 31, 2015:
  MICE 201 MHz Prototype RF Module
    Extended run at 11 MV/m in magnetic field complete
      Lab G Solenoid is prototype of focus coil magnet
      MICE specification is 10.3 MV/m
    Subsequent high power tests up to 14.5 MV/m
      These tests all carried out with Be windows in place
    High power coupler evaluation completed successfully
    Full characterization of tuner system in B-field complete
  All acceptance tests are now complete
    Critical sign-off for Cooling Demo RF module production
a Construction Project R&D is now complete!

## Slide 8: US Effort Summary & Conclusion
Step IV commissioning is underway
  Physics data is imminent
Cooling Demonstration construction is moving forward rapidly
  We expect all remaining major hardware procurements to be in place on the ~1 month timescale
  PRY Extension
    Material (JFE Steel) arriving mid-July
    Design complete
      Drawing package ready for procurement this week
    Intend to release sole source package to Step IV vendor this week
  RF Modules
    Prototype validation complete
    Design complete
      Drawing package ready for procurement this week
    RFP to vendors anticipated next week
  Progress is consistent with having all US-supplied hardware to RAL by June 2016 in preparation for 2017 operations
We sincerely hope that NSF will re-connect to the exploitation of this unique experimental capability