## Slide 1: Single Phase Test at CERN DUNE prototype
David Montanari / Dimitar Mladenov
Jun 12, 2015

## Slide 2: News
There has been a change in the organization.
Dimitar M. will now lead all cryostat activities for CERN.
I will remain the interface for the design of the top plate and beam window.

## Slide 3: Needed information
Finalize the cryostat inner dimensions (flat plate to flat plate):
  Currently  7,826 mm (Transverse) x 8,874 mm (Parallel) x 8,073 mm (Height)
  Resources  DUNE Collaboration.
  When  now.
TPC installation plans:
  May change the access to the cryostat and design of the top.
TPC support needs:
  May change the design of the top.
Grounding and isolation requirements/needs:
  Few months ago the LBNF requirements were challenged and meant to be discussed again, but I do not know the outcome of such a discussion, if that ever happened).
Instrumentation inside and on top of the cryostat, if any:
  May change the layout of the penetrations on the top and the design of the top.
Loads on the top plate (racks, if any, instrumentation, etc.).
  Needed for the design of the top.

## Slide 4: Tasks (next ~9 months)
Finalize preliminary design of the top plate:
  Resources  Rahul S. (BNL) + Jack F. (Duke) for integration with TPC design and installation needs.
  When  Connected to outer support structure design.
Finalize preliminary design of steel outer support structure:
  Resources  Dimitar M. (CERN)
  When  2-4 weeks after finalization of cryostat dimensions and top plate preliminary design.
Award contract for feasibility study to GTT:
  Resources  CERN
  When  after completion of preliminary design of support structure/top plate
Finalize design of top plate:
  Resources  Rahul S. (BNL) + Jack F. (Duke) for integration with TPC design.
  When  Connected to outer support structure.
Finalize design of steel outer support structure:
  Resources  Dimitar M. (CERN)
  When  After completion of the feasibility study from GTT.
GTT detailed study of membrane cryostat:
  Resources  CERN
  When  After the feasibility study.
Design of the beam windows:
  Resources  Tim L. (LBL).
  When  On-going. Preliminary by Oct 2015, Final by Dec 2015.