## Slide 1: Cryomodule Interconnect Installation Issues A Comparison of XFEL to LCLSII
Karen Fant
7/29/2015

## Slide 2: Introduction
  Design of LCLS II Interconnection based upon XFEL design
    Major Difference in Size of Tunnel & Location CM within Tunnel
    Minor Difference in Build to Install Sequence
    XFEL: Assembly Transport Accept Test RFI Install
    LCLS-II: Assembly Test RFI Transport Accept Install
3.35m (11’)
3.05m (10’)
LCLS-II
XFEL
(Graphics to scale)

## Slide 3: SLAC Interconnect Installation Assumptions
  FNAL design team has checked that CM interconnections are achievable within SLAC tunnel space and ergonomic constraints
  This FDR covers only string interconnect string (CM to CM, not to End/Feed caps)
  Prototype and Production CM interconnects are identical
  CM delivered to SLAC Ready for Installation
  Incoming acceptance inspection confirms no change or damage during long transit
    Checks for vacuum, electrical continuity, alignment, shipping
  FNAL provides designs for interconnect tooling and fixturing
  SLAC procures interconnect tooling and fixturing
  FNAL will develop interconnect procedures
  SLAC will develop interconnect travelers

## Slide 4: Receiving and Off-Loading
Truck Arrives from SACLAY
Remove Ceiling and Walls
Check Data Shock Logger
Attach Lifting Beam
CM removed from Transport Frame
CM Lowered onto Supports

## Slide 5: Receiving and Prep for Test
Check Vacuum Gauges and Alignment
Shipping Caps Removed
Portable Clean Room to Remove Vacuum Gauges
Accessory Box to Check Pipes and Vacuum

## Slide 6: Pipe Preparation-Cut, Face, Clean & Package
Tooling to Measure and Mark Pipe Length
Inserting Wire Brush to Keep Pipe Clean
Cutting Pipe to Length with Band Saw
Removing Brush after Cutting

## Slide 7: Pipe Preparation-Cut, Face, Clean & Package
Tooling to Face Ends of Pipes
All Pipes are Cut and Faced
Pipes Capped and Ready for Installation
Desiccant
Humidity Indicator

## Slide 8: Assembly of Large Bellows on CM
Prep to Lift
Bellows Install Complete
Transport Bellows to CM
Prepare to Install on CM

## Slide 9: CM Transport Test to Tunnel
CM Transported from Test Facility
CM Arrives at Install Site
Preparing to Lower into Tunnel
CM Transporter Viewed from Above

## Slide 10: CM into Tunnel
CM Transporter
CM Transporter-Attachment Cradle
Lowering CM to Tunnel
Preparing to Install CM on Transporter

## Slide 11: Tunnel Transport and Ceiling Mount
Moving CM through Tunnel
Raising CM to Supports
Attaching CM to Supports
CM Installed

## Slide 12: Welding the HGRP
Qualify the weld
Tack interconnect pipe in place
Checking weld set-up
Performing weld-workers on both sides of CM
Orbital Track Welder with Custom Head

## Slide 13: Welding Cryogenic Pipes
Qualify the weld
Install paddle weld head
Tack interconnect pipe in place
Head oriented to fit location
Perform the weld
Completed weld

## Slide 14: Leak Checking Cryogenic Pipes
Elastomer Leak Check Fixtures
Leak Checking HGRP Welds
Leak Checking Cryogenic Pipes Welds with Elastomer Fixture
Aluminum Leak Check Fixtures
Aluminum Leak Check Fixtures Installed
Leak Checking Cryogenic Pipes Welds with Aluminum Fixture

## Slide 15: HOM Installation
Class 10 Portable Cleanroom
HOM Install Fixture
Placing HOM on Fixture in CR
Prep Gate Valves in CR

## Slide 16: HOM Installation
Raising HOM into Position
Removing Flange Caps
HOM Ready to Interconnect
HOM Installed
HOM with Clean Room Removed

## Slide 17: Thermal Shield Connection
Solid Aluminum Thermal Shield Covers
Perforated Aluminum Shield Covers
Final Layer of MIL Installed-Ready for Lg Bellows
Shield and Cryo-Pipe Bellows Restraint Installed

## Slide 18: Large Bellows Installation
Bellows Install Fixture
Top Supported (Tunnel)
Bellows Install Fixture
Bottom Supported (Test Facility)
Bellows Prep’d to Move
Sliding Bellows into Position
Bellows in Position

## Slide 19: Large Bellows Installation
Sliding Ring into Position
Bolting Ring to Bellows
Attaching Clamps Aisle Side
Attaching Clamps Wall Side
Bellows Installed and Threaded Rods Removed

## Slide 20: Example of Vacuum Pump Station Installed on Large Bellows

## Slide 21: Testing the Design
Recommend FNAL and/or JLAB “interconnect” 2 CM for fit up check
In next few months SLAC will build weld test fixture to confirm design
    Use pipe X, Y coordinates, materials, dimensions as defined in CM Interconnect Assembly Procedure
    Model to confirm clearance work for weld tracker, custom weld head, paddle heads, insulation shield fit
    Development of weld sequence and parameters, purge and leak check tooling
    Model to check ergonomics, special tooling requirements not already identified
    Develop pressure test or X-ray procedures

## Slide 22: Some Areas of Concern or Issues to Resolve
  Tube cutting prior to ship
  Receiving Inspection and Acceptance
  Vacuum gages attached during transit in tunnel
  Tube welding
  Purge, welding gas (space for 12 pack)
  Thermal Insulation Shield – XFEL fit problems
  Installation of HOM absorber
  Pressure test vs X-ray
  Big Bellows installation and connection
  Continuous dry air purge vs desiccants
  Class 10 cleanroom in tight environment
  Installation required from wall side? – ergonomics, special tooling

## Slide 23: Summary
LCLS II CM Interconnect similar but not identical to XFEL CM interconnect
SLAC personnel observation & participation at XFEL extremely useful for understanding and recording installation process
    Photos all courtesy K. Ratcliffe and J. Garcia - Complete set of photos can be found at:
    https://slacspace.slac.stanford.edu/sites/ad/work_planning_control/Work_Planning_Control_Documents/Partner_Lab_Info/Partner%20Labs%20Photos%20and%20Videos.aspx
Major differences identified
Working with FNAL design team to identify, address and resolve gap/issues
So far don’t see any show stoppers

## Slide 24: End