## Slide 1: HLRF, Vacuum, Mech Support, LLRF, Instrumentation, Cryo, Beam Delivery, Accel Physics & Design Booster/RR/MI too!
Paul Derwent
PIP-II Budget Retreat
June 30, 2015

## Slide 2: Standard Presentation Outline
Resources required to meet target Goals:
 | Allocation | Requested | Manager
Accel Design | 1.0 | 1.2 | Valeri
Accel Physics | 3.0 | 2.4 | Valeri
Beam Delivery | 0.25 | 2.37 | Dave
Cryo | 3.00 | 2.55 | Arkadiy
Instrumentation | 1.76 | 3.7 | Vic
LLRF | 3.25 | 3.25 | Brian
Mech Support | 1.0 | 0.1 | Curtis
Vacuum | 0 | 0.7 | Alex
HLRF | 0.35 | 1.0 | Ralph
Total | 13.61 | 17.27 | (3.66)
Boo/RR/MI | - | 6.3 | (6.3)
Note: Cryo & LLRF include 2 Indian guest engineers

## Slide 3: Standard Presentation Outline
Resources required to meet target Goals:
 | Allocation | Requested | Manager
Accel Design | - | - | Valeri
Accel Physics | $50,000 |  | Valeri
Beam Delivery | - | - | Dave
Cryo | - | $800,000 | Arkadiy
Instrumentation | $100,000 | $98,000 | Vic
LLRF | $100,000 | $222,520 | Brian
Mech Support | $50,000 | $15,000 | Curtis
Vacuum | - | $48,800 | Alex
HLRF | - | $60,000 | Ralph
Total | $300,000 | $1,244,320 | ($944,320)
Boo/RR/MI | - | $530,000 | ?

## Slide 4: PIP-II Accelerator Physics - FY16 Initial Goals
Complete Conceptual Design Requirement (CDR)
  Provide any required elucidation of the goal here
Support LEBT, RFQ, and MEBT beam analysis
  Provide any required elucidation of the goal here

## Slide 5: PIP-II Accelerator Physics - FY16 Initial Goals
Support Conceptual Design Report (CDR) development
  Provide any required elucidation of the goal here
Support LEBT, RFQ, and MEBT beam analysis
  Provide any required elucidation of the goal here

## Slide 6: PIP-II Beam Delivery - FY16 Initial Goals
Beam Delivery – Booster – Support completion of Conceptual Design Requirement (CDR)
  Provide any required elucidation of the goal here
Beam Delivery – Booster – Interface with booster injection development
  Provide any required elucidation of the goal here
Beam Delivery – Dump Line – Support completion of Conceptual Design Requirement (CDR)
  Provide any required elucidation of the goal here
Beam Delivery – Dump Line – Develop design concepts for beam line and dump
  Provide any required elucidation of the goal here
Beam Delivery – Dump Line – Initiate mechanical design for beam line and dump components
  Provide any required elucidation of the goal here

## Slide 7: PIP-II Cryogenics - FY16 Initial Goals
Support Conceptual Design Report (CDR) development
  Provide any required elucidation of the goal here
Initiate PXIE cryogenics distribution design
  Provide any required elucidation of the goal here

## Slide 8: PIP-II Instrumentation - FY16 Initial Goals
Support PXIE beam commissioning
Install/commission MEBT beam current electronics
  Critical for RFQ/MEBT commissioning – mostly FTE in FY16
Install/commission of MEBT BPM system
  Critical for RFQ/MEBT commissioning – mostly FTE in FY16
Install/commission Time-of-Flight energy measurement system
  Required for RFQ/MEBT beam energy measurements – mostly FTE in FY16
Install/commission Fast Faraday Cup (FFC) Longitudinal Profile Measurement System
  Required for RFQ and MEBT buncher cavity commissioning – mostly FTE in FY16
Continue development of laser based profile system
  Installation of beamline vacuum hardware only in FY16
Design and construction of two (2) MEBT wire scanner
  Profile monitor prototype development and testing in FY16
Design and construction of prototype resistive wall current monitors (RWCM)
  Required for chopper extinction measurements – need ~1 year to develop
Design and construction of MEBT Allison emittance scanner
  Critical for RFQ/MEBT commissioning; build new detector in FY16; reuse LEBT electronics
Support Conceptual Design Report (CDR)

## Slide 9: PIP-II Low Level Radio Frequency (LLRF) - FY16 Initial Goals
Support RFQ commissioning
  Provide any required elucidation of the goal here
Support resonance control experiments
  Provide any required elucidation of the goal here
Develop strategy for LLRF and timing control for PIP-II
  Provide any required elucidation of the goal here
Support the completion of the CDR
  Provide any required elucidation of the goal here

## Slide 10: PIP-II Mechanical Support Systems - FY16 Initial Goals
Support Conceptual Design Report (CDR) development
  Milestones:
    Start developing and documenting design concepts for mechanical support systems in support of CDR
    Generate CDR input
    LOE support for planning and reporting
  Biggest single effort will be work on PIP-II fluids systems by the MSD fluids group
  Vacuum Systems will be in its own WBS element, and is no longer captured by this account

## Slide 11: PIP-II Vacuum - FY16 Initial Goals
Support design, acquisition, and installation of vacuum equipment for the LEBT
  Provide any required elucidation of the goal here
Support design, acquisition, and installation of vacuum equipment for the MEBT
  Provide any required elucidation of the goal here
Support design, acquisition, and installation of vacuum equipment for the RFQ
  Provide any required elucidation of the goal here
Support design of vacuum equipment for the HEBT
  Provide any required elucidation of the goal here
Support Conceptual Design Report (CDR) development
  Provide any required elucidation of the goal here

## Slide 12: PIP-II RF Power (Front End, HWR, 325 MHz) - FY16 Initial Goals
Power - 325 MHz – Support coupler tests for 325 MHz device
  Test stand currently operational, but uses HINS resources which may prove to be a conflict with FAST
Power - 325 MHz –Test the Indian 325 MHz source
  Need replacement power modules
Power – Front end – Support commissioning of RFQ
  Once installed and connected, commissioning will continue into FY16 requiring RF support personnel.
Power Front end – Support commissioning of MEBT buncher
  There is a need to procure connectors for the transmission line we already own as scavenged from PBAR
Power – HWR – Support coupler tests for 162.5 MHz (HWR) Device
  Test stand is in the hands of Argonne
Support the completion of the CDR
  Fractional FTE for support as requested.

## Slide 13: HLRF, Vacuum, Mech Support, LLRF, Instrumentation, Cryo, Beam Delivery, Accel Physics & Design
Initial Budget Request for: |  |  |  | 
HLRF, Vacuum, Mech Support, LLRF, Instrumentation, |  |  |  | 
Cryo, Beam Delivery, and Accel Physics & Design |  |  |  | 
 | FTE | SWF | M&S | Tot. Directs
Original Target | 9.61 | $1,220,470 | $300,000 | $1,520,470
Current Request | 13.27 | $1,876,585 | $1,244,320 | $3,120,905
(Over)/Under Target | (3.66) | $(656,115) | $(944,320) | $(1,600,435)
SWF: Beam Delivery & Instrumentation
  Note 4 Indian engineers (Cryo + LLRF) not included in this table
M&S: Cryo, LLRF & HLRF

## Slide 14: HLRF, Vacuum, Mech Support, LLRF, Instrumentation, Cryo, Beam Delivery, Accel Physics & Design By OHAP Category, Role and Div.
 |  |  | Values | 
Category | Role | Home DSC | Sum of FTE | Sum of SWF
 | 0 | 0 | - | $0
 |  |  | - | $0
Design | Cryo Designer | AD | 0.25 | $27,509
 | Mechanical Drafter | AD | 0.42 | $34,459
Electrical Engineer | Electrical Design Engineer | AD | 0.42 | $62,902
 | Electronics Design Engineer | AD | 0.80 | $119,813
 |  | AD | 0.65 | $97,348
 | RF Design Engineer | AD | 1.15 | $140,293
Electrical Technician | Electronics Technician | AD | 0.75 | $72,406
 |  | AD | 0.45 | $43,444
Information Technology | Applications Development & Systems Analyst | AD | 0.60 | $86,273
Mechanical Engineer | Cryogenics Engineer | AD | 0.30 | $44,930
 | Magnet Design Engineer | TD | 0.42 | $62,902
 | Mechanical Design Engineer | 0 | 0.40 | $59,906
 |  | AD | 1.07 | $160,250
 | Process/Controls Engineer | AD | 0.05 | $6,100
Mechanical Technician | Mechanical Systems Technician | AD | 0.20 | $15,449
Postdoctoral Res Assoc | Accelerator Experimental Research Associate | TD | 0.50 | $40,800
Scientist | Accelerator Physicist Experimental | AD | 0.88 | $139,558
 |  | AD | 0.40 | $63,435
 | Accelerator Physicist Theory | AD | 2.35 | $397,188
 |  | AD | 0.50 | $84,508
 | Magnet Scientist | TD | 0.71 | $117,114
Grand Total |  |  | 13.27 | $1,876,585
Note 4 Indian engineers (Cryo + LLRF) not included in this table

## Slide 15: HLRF, Vacuum, Mech Support, LLRF, Instrumentation, Cryo, Beam Delivery, Accel Physics & Design – Achievable Goals at Initial Target
HLRF, Vacuum, LLRF, Instrumentation
  These budget lines focus on support of LEBT, RFQ, MEBT
Cryo
  This budget line is for the distribution system at PXIE, have to have it in FY16 if want any chance of cryogenics in late FY17
Beam Delivery
  HEBT : absorber design ?
  Booster Transfer & Dump ?
Accel Physics & Design:
  ~95% towards CDR development
  ~5% towards beam analysis

## Slide 16: R&D Plan: Booster/MI/RR
Presented to AD in June
Before swept into project scope

## Slide 17: Requests:
Booster Injection Region: 1.05 FTE
  gradient magnet design (TD): 0.5 FTE
  absorber design (APC Energy Deposition): 0.25 FTE
  injection girder (Scientist, Eng Phys in PIP-II): 0.3 FTE
Booster Beam Quality & Collimation: 0.75 FTE
  beam dynamics, emittance and loss control, collimation
  Scientist PIP-II, Proton Source: 0.5 FTE
  APC Energy Deposition: 0.25 FTE
Recycler RF Cavity Design: 2 FTE
  RF Engineer: 2 FTE
MI RF Power: 2.2 FTE
  RF Engineer 1.1 FTE, RF Tech 1.1 FTE
MI Gamma T Magnet: 0.3 FTE
  Prototype Magnet Design (TD) 0.3 FTE

## Slide 18: backups

## Slide 19: Brian on LLRF:
  First, here is the narrative of how I would like things to go in an ideal world
  My team gets the RFQ system finished up this summer and we start testing with the RFQ as soon as possible in low duty factor pulsed mode. This system will be based on our old MFC card.
  I will be bringing on a new engineer by the end of the summer and he will join in on the effort to build the next gen card, our SOCMFC. We have a first prototype now. We are supposed to have two Indian engineers in the fall and we should be able to fast track a system for the buncher cavities. In the mean time we are working towards a final system design that will pass reviews and such.
  Ongoing effort in RFQ resonance control as we increase the RF duty factor.
  Note that we have never driven a cavity with two amplifiers here at FNAL, so there may be some adventure during the RFQ commissioning.
Ways to cut back:
  LLRF
  2) Cobble up the buncher cavities with old hardware and leave new design for another day.
  3) Run everything at 15 Hz, 1 ms pulse rate.
  4) Don’t work on the kicker waveform generator

## Slide 20: Vic on Instrumentation
Support PXIE beam commissioning
Install/commission MEBT minimal beam current electronics
  Pulsed beam only; non-biased scrapers
Install/commission of MEBT minimal BPM system
    Pulsed beam only; single harmonic (no bunch length)
Install/commission Time-of-Flight energy measurement system
Install/commission minimal Fast Faraday Cup
  Manual operation; manual scope readout; offline analysis
Support CDR
Not supported: MEBT Emittance monitor, wire scanners, RWCM, laser wire development

## Slide 21: PIP-II Instrumentation– Resources Required to Meet Initial Goals
Describe FTE resource needs to reach goals
  A number of instruments will be commissioned in FY16 requiring an increase in FTEs
  Most of these instruments required to commission RFQ
Describe M&S resource needs to reach goals
  Original target M&S appear adequate to meet FY16 initial goals
  Additional narrative here, if needed

## Slide 22: Curtis on Mechanical Support Systems – Achievable Goals at Initial Target
The goal of supporting the CDR can be achieved with less than this original target

## Slide 23: PIP-II RF Power (Front End, HWR, 325 MHz) – Resources Required to Meet Initial Goals
Describe FTE resource needs to reach goals
  Electrical engineering support at 0.8 FTE 0.2 FTE technician
  Keep RFQ RF functioning, Installation of MEBT RF
Describe M&S resource needs to reach goals
  Procurement of connectors for MEBT, and one 7kW HWR 162.5 MHz amplifier with a one year lead time, needed in 2017