## Slide 1: Workshop Goals Project Management – FY16 Budget Request
Steve Holmes
PIP-II Budget Retreat
June 30, 2015

## Slide 2: Goals for the Retreat
Establish a set of self-consistent goals and resource requirements, consistent with our FY16 budget guidance.
  Preliminary goals established at level 3 of WBS
  Initial resource target allocations established at level 3 of WBS
  Unlikely we will achieve this goal today, but we will have all info required to develop a rational plan and will make a start
FY16 Guidance = $19.5M
  Compare to FY15 budget of $20.6M
  This will be augmented by whatever we carry over/forward fund from FY15
Level 3 Managers to present:
  Resources required to meet the preliminary goals
  Goals that can be met at the initial target resource allocation
    And plan for delaying deliverables by one year

## Slide 3: FY16 PIP-II High Level Goals
Prepare for CD-1
Initiate Project activities
Keep PXIE on schedule
Keep SRF R&D on schedule

## Slide 4: Integrated Request vs. Initial Allocation
Integrated request corresponding to L3 Goals:
The difference is beyond the realm of “tweaking”
We are going to have to slow down multiple activities
  We need to do this in a consistent manner so that things are coming together synchronously, albeit later than originally planned
    PXIE: HWR, SSR1, cryo, rf, power, LCW…
    HTS-2 and HB650
    Appropriate balance between CD-1 and R&D activities
  Coordination with our Indian collaborators
*Note: Total resources requested is nearly identical to what we informed the laboratory and DOE last September would be required in FY2016
 | FTE | M&S
Initial Target | 56.6 | $5.3M
Requests | 80.0 | $10.1M
Difference* | 23.4 | $4.8M

## Slide 5: PIP-II Project Management - FY16 Initial Goals
Manage PIP-II
  Appoint Associate Project Manager for Planning & Reporting
  Keep things moving smoothly
Organize CD-1 documentation, including alternative study
  Complete Alternatives Study, including cost estimate for pulsed linac
  Complete draft CDR
Organize PIP-II collaboration meeting
  Organize meeting in fall 2015 with potential collaborators
Support conference, workshop, and collaboration meeting travel
  Provide conference travel support

## Slide 6: PIP-II ESH&Q - FY16 Initial Goals
General ES&H support for PXIE and PIP-II
  Complete HA and ORC for RFQ beam commissioning
Initiate NEPA documentation
  Complete EENF
  Update Wetlands Delineation Report
  Initiate EA development
Support completion of the CDR

## Slide 7: PIP-II Business Office - FY16 Initial Goals
Initiate development of resource loaded schedule
  Develop RLS for R&D program
  Initiate development of PIP-II RLS
Develop CD-1 estimate
  Update PIP-II cost estimate (when needed)
  Support development of alternatives estimate(s)
Develop CD-1 documentation
  Initiate CD-1 documentation

## Slide 8: PIP-II International Collaboration - FY16 Initial Goals
Manage international collaborations
  3 Face to Face meeting between IIFC Sub-Project Managers
    Cryogenic Plant, Instrumentation and Controls
    RF Power, LLRF and RF Protection
    SRF
  1 Face to Face Annual IIFC Management meeting
Establish detail technical plan for deliverables
  Finalize all the TRS
    SSR2 Dressed Cavity and CM
    HB650 CM
Support Indian R&D deliverables
  FY16 deliverables outlined in IIFC Joint R&D Project Document

## Slide 9: PIP-II Experimental Design Requirements - FY16 Initial Goals
Establish Mu2e/Stage 2 and SBN Strategy

## Slide 10: PIP-II Systems Engineering & Integration - FY16 Initial Goals
Implement in Teamcenter all PIP-II engineering documentation
  Assist PIP-II personnel to develop the necessary skills in Teamcenter to be successful in document management
Establish a PIP-II EPDM structure in Teamcenter for all project work packages (WBS developement)
Develop a PIP-II EPDM systems integration plan
  Identify engineering multi-disciplines per work package and develop the strategy for integrating them
Engineering Oversight
  Provide component/system reviews, support and guidance
  Help coordinate budgets and schedules
  Develop technical facility layouts to facilitate working group meetings

## Slide 11: PIP-II Project Management – Resources Required to Meet Initial Goals
FTE resource needs to reach goals
  Senior management team including newly hired Associate Project Manager for Planning & Reporting and Project Controls Manager
M&S resource needs to reach goals
  $10K for office supplies
  $40K for conference travel support (16 attendees x $2500)
  $50K for NEPA consultant
  $96K for India trips (4 face-to-face meetings:16 trips x $6K/trip)
  $93K for support for short-term Indian visitors (24 visitor-months)
  $3K to support attendance at Teamcenter conferences and User Group meetings

## Slide 12: PIP-II Project Management – FTE – By OHAP Category, Role and Div.
Project Office staff (7.0)
Indian Collaboration Management (3.7)

## Slide 13: PIP-II Project Management – Achievable Goals at Initial Target
We can largely meet assigned goals, expect for a slow down in preparations for CD-1
Reduce Finance Manager fraction (0.25 FTE)
Delay assignment of Project Controls Manager fraction (0.25 FTE)
Delay assignment of Deputy Project Engineer (0.4 FTE)
Delay start of NEPA development: no consultants ($50K)
Reduce conference support by factor of two ($20K)
Reduce India trips to ten ($36K)
Reduce Indian short-term visits to 1 person-year ($47K)
Unidentified ($160K)