## Slide 1: Medium Energy Beam Transport (MEBT) – FY16 Budget Request
L. Prost for A. Shemyakin
PIP-II Budget Retreat
June 30, 2015

## Slide 2: Standard Presentation Outline
Resources required to meet target goals
Goals that can be met with the initial resources allocation

## Slide 3: MEBT stages
Diagnostics
Beam dump
MEBT-1 : 2 doublets, 1 buncher, diagnostics (FFC, ToF, scrapers etc.). Several modifications that differ by parts after the second doublet. RFQ beam characterization; 10 kW into beam dump.
Absorber prototype chamber
Diagnostics: BPM, scrapers, wire scanner
Beam dump
MEBT-2 : Add 4 triplets, 1 buncher, prototypes of kicker and absorber. Optics; tests of absorber and kicker prototypes.
MEBT-3 : Add 3 triplets, 1 buncher, final chopper.
Final MEBT : Clean last 2.5m. Bunch-by-bunch separation. Injection into HWR.
Optics; vacuum management.

## Slide 4: PIP-II Medium Energy Beam Transport (MEBT) - FY16 Initial Goals
MEBT-1 installed
  2 doublets, 1 buncher, diagnostics (FFC, ToF, scrapers etc.)
RFQ beam measurements in pulse mode
  Energy, emittance, Twiss parameters
CW beam in MEBT-1, up to 10 kW into beam dump
MEBT-2 installation
  Add 4 triplets, 1 buncher, prototypes of kicker and absorber
MEBT-2 commissioning
  Pass the beam through; absorber test; initial kicker tests
Design of full length MEBT
  Except the final chopping system
  Manufacture most of parts except UHV portion

## Slide 5: PIP-II Medium Energy Beam Transport (MEBT) – Resources Required to Meet Initial Goals
Difference in FTE
  Most of installation work in MEBT will be done in FY16
  Large design and commissioning efforts
    Includes characterization of the beam out of RFQ
M&S
  Vacuum pumps and equipment are in separate Vacuum line
  Largest items: vacuum chambers ($50k) and scrapers ($80k)
  Payment for contractor (D. Snee, $20k) can be done in FY15

## Slide 6: PIP-II Medium Energy Beam Transport (MEBT) – FTE – By OHAP Category, Role and Div.
3.4 FTE goes to mechanical design
Efforts related to water, cabling, controls, and most of instrumentation are not included, as well as others <0.05FTE
Technicians time for major installation is included into Infrastructure

## Slide 7: PIP-II Medium Energy Beam Transport (MEBT) – Achievable Goals at Initial Target
Main difference: 9.4 FTE requested vs 6.0 in original target
Most of the goals related to beam commissioning in FY16 can be achieved with initial target funding
  Commissioning of MEBT-2 would be delayed
Lower number of FTEs would affect preparation for FY17
  Design of full-length MEBT (MEBT-3 will be delayed in FY17)
  Final absorber design
  Work with kickers