## Slide 1: Horizontal Test Stand – 2 (HTS-2) – FY16 Budget Request
Joe Ozelis, Sr. Engineering Physicist
PIP-II Budget Retreat
June 30, 2015

## Slide 2: Outline
Resources required to meet target goals
Goals that can be met with the initial resources allocation

## Slide 3: PIP-II Horizontal Test Stand – 2 (HTS-2) - FY16 Initial Goals
Progress on HTS-2 Cryostat
  Fabrication Oversight and Coordination with Collaborators
    HTS-2 Cryostat to be fabricated in India using Indian vendors, direct (local) oversight by RRCAT, additional oversight by FNAL (teleconferences, periodic visits)
Preparation of infrastructure for FY17 delivery and commissioning of HTS-2 cryostat
  Conventional facilities
  Cryogenic systems
  RF/Controls/DAQ
  Safety systems
  Ancillary systems (vacuum pumping, magnetic shielding, etc.)

## Slide 4: PIP-II Horizontal Test Stand – 2 (HTS-2) – Resources Required to Meet Initial Goals
4.3 FTE’s (CryEng, MechEng, RFEng, CtrlEng, MTs, ETs)
  Design, fabrication, installation of cryo distribution systems
  Design, procurement installation of control systems (RF, cryo, diagnostics, interlocks)
  Enclosure/infrastructure design, assembly, layout (racks, trays, AC power, HVAC, LCW, gates, cryostat supports, shldg)

## Slide 5: PIP-II Horizontal Test Stand – 2 (HTS-2) – Resources Required to Meet Initial Goals
M&S resources
  Does not include cost of HTS-2 cryostat or RF amplifiers (supplied by RRACT)
  Includes cost of :
    Shielding blocks, racks, cable trays & cabling, HPRF components, LLRF controls HW, cryo controls HW, 2K pump skid, safety system infrastructure (gates, chipmunks, interlock HW), cavity & coupler vacuum systems (cavity/coupler/ins vac), HVAC (ODH fans),

## Slide 6: PIP-II Horizontal Test Stand – 2 (HTS-2) – FTE – By OHAP Category, Role and Div.
Mech Eng : cave infrastructure, cryostat supports, vacuum systems (RT & cryo), HVAC
Cryo Eng : cryodistribution systems, controls, ODH analysis
RF Eng : HPRF & LLRF systems
Intlk Eng : interlocks, safety systems, ODH systems
Controls Eng : cryo & RF controls, diagnostics
Mech Tech : mechanical assembly, fab, installation
Elec Tech : electrical assembly , fab, installation

## Slide 7: PIP-II Horizontal Test Stand – 2 (HTS-2) – Achievable Goals at Initial Target
Under Initial Target scenario, concentrate on preparing infrastructure, some basic systems. 2.49 FTE/175k$
  Complete facility design/layout
  LLRF – complete design, fab, installation
  Cryo distribution system – fabrications, installation
  Cable trays & racks – procurement and installation
  LCW system – specification, design, & installation
  Cabling – specification, procurement, fab, install
  ODH/HVAC – analysis, procurement, installation

## Slide 8: PIP-II Horizontal Test Stand – 2 (HTS-2) – Achievable Goals with 1-year Delay of Deliverables
Original timetable
  FY16 – prepare for installation and commissioning of HTS-2
  FY17 - complete commissioning prep, install HTS-2 and commission
One year delay
  FY16 – minor preparation work for facility, complete designs
  FY17 – prepare for installation and commissioning of HTS-2
  FY18 – complete commissioning prep, install HTS-2 and commission

## Slide 9: PIP-II Horizontal Test Stand – 2 (HTS-2) – Achievable Goals with 1-year Delay of Deliverables – FY16
One year delay
  FY16 – minor preparation work for facility, complete designs
    Compete facility design
    Procure & install racks/cable trays
    Spec & install LCW
    Mech installation of cryo distribution
    Complete LLRF design, some fab & controls dev
  1.4FTE/105k$ M&S