## Slide 1: MICE RF System Review Closeout
September 10, 2015

## Slide 2: Committee
Terry Anderson, FNAL
Jean-Pierre Delahaye, SLAC/CERN
Mark Keelan, RAL
Mark Palmer, FNAL (chair)
Ralph Pasquinelli, FNAL
Robert Rimmer, JLAB
Yagmur Torun, IIT (remotely joining)

## Slide 3: Findings
The re-baselined MICE RF system is much simpler with only 2 cavities and greatly reduced RF distribution system. This improves the chances that the systems can be delivered and commissioned on the tight schedule.
The desired RF gradient has been demonstrated in the MTA with similar (but not identical), magnetic field. This is very encouraging.
A revised version of the RF couplers should improve reliability and the critical RF window structure will be protected by the PRY magnetic shield.
The pulse length in the MTA was significantly shorter than that needed for MICE so this needs to be demonstrated, however a somewhat reduced pulse length or lower gradient could be tolerated at the expense of statistics in the experiment.
Only two RF stations are now needed. One has been commissioned and met spec but has been disassembled and mostly returned to Daresbury. The second one is in progress but appears to be going very slowly due to other resource priorities. There are two spare TH116 tubes in addition to the two new or fairly new tubes to be installed. This should be adequate for the experimental run.

## Slide 4: Findings
Although the energy loss in the channel is reduced to 5%, the reduced RF will not completely compensate the energy loss through the absorbers. The effect of energy compensation (or deceleration in the opposing phase) however will be big enough to measure with acceptable accuracy to validate simulations, and the technical goals of running the RF in the magnetic field and in close proximity to absorbers and sensitive instrumentation can be demonstrated.
A draft list of RF system interlock signals is being developed by the collaboration. The definition of the hardware to implement the RF system interlocks is not yet clear. The interface to vacuum and personnel safety systems must also be well-defined.

## Slide 5: Findings
Both a precision water temperature control loop and a mechanical tuner system are being developed. The water system is based on proven hardware at DL and the mechanical tuner with air actuators was demonstrated at MTA. An improved version of the air actuator is being developed at LBNL for higher reliability. These two systems provide some duplication of function on similar time scales. On the plus side this could provide redundancy, but the feedback systems could also interact
The LLRF system for MICE is in the conceptual stage. It is planned to use the proven LLRF4 board for the RF control part and develop a new labview based module, drawing on similar software used in the MTA test program, for the signal analysis and monitoring.
The tuner control was shown as a separate function but might be also integrated into one or the other of these functional blocks. Loss of key personnel is a concern in this area and rebuilding this capability is urgent.
Commissioning of the RF modules off-line is very important to identify any problems before installation into the cooling channel. At least one fully operational RF system (including controls and interlocks) will be required to support this. Neither the cavities nor the new couplers will have been pre-commissioned so the first time they will see RF power will be in the hall. There are plenty of spare cavities and two spare couplers will be built, but once installed in MICE it will be very difficult to access to make any repairs.

## Slide 6: Findings
Installation will require opening the insulating vacuum in the hall. A portable clean room and procedures such as used in the MTA will be used to minimize particulate intrusion into the vacuum space, which is connected to the cavities. The other beam line spaces and components must likewise be kept clean and treated in a similar manner. A slow pump down protocol may be needed to minimize the risk of particulate migration within the module due to turbulent flow.
The TH116 power tube has a known good lifetime approaching 15,000 hours at ISIS. With four tubes in inventory, this should be adequate for the life of the program. If there is no hot spare RF system, a full list of repair parts should be on site at RAL to allow repair of a broken RF system
Rotatable flanges on the RF rigid coax should be employed at all critical connections. As described, the only “flexible” sections are one-meter long heliax, which is not that flexible.
The RF controls will be based on Labview and will require an interface to the MICE EPICs control system. It may not be compatible with the operations of ISIS and that could be an issue if the ISIS operations crew is expected to monitor MICE on off shifts 24/7. Software for a control system is also not trivial and could require significant investment of software professionals.
The construction of a second RF amplifier chain that is identical to the prototype is projected to be 6 months. This seems excessive unless the time is due to lack of resources.

## Slide 7: Comments
If further run time beyond that presently scheduled were to be forthcoming it would be nice to see a configuration in which the absorber loss and RF gain were balanced.
It might be useful to add a “tune mode” state to the state machine in which RF is enabled and tune up can be performed but power is limited to a safe value.
A local phase detector between cavities with remote readback of error voltage could be a beneficial set point of the system and is totally passive.
The LLRF will use FPGAs and the programming of such will require an expert. This resource is currently being added to the collaboration.

## Slide 8: Comments
If possible, when testing the RF cavities outside the beam line, they should be accessible from all sides. Because a clean room is also planned, moving the test site away from the existing magnet lattice would allow space to install the clean room.
It is essential to calibrate all couplers and cables. This should be very easy as the distance between input and output ports are all well within reach of calibration cables within the hall.
The LLRF should consider the implementation of a self-excited frequency loop, i.e. the frequency of the cavity is tracked by the LLRF to allow quicker tuning to a fixed frequency. Both cavities must be run at the determined frequency and waiting for thermal equilibrium may be reached more quickly with such a loop.
The pulse width at MTA was limited by the RF system and well below the 1 ms pulse width required by MICE. It is a well-known fact that spark rate increases exponentially with pulse width. Understanding the effect of taking data based on a reduced pulse length to limit sparking should be examined. This can only be accomplished in timely fashion as part of the offline testing of the cavities in the MICE Hall.

## Slide 9: Recommendations
The RF system interlocks should be formalized as early as possible to allow the development of the state machine and interlock hardware configuration.
Mechanical and thermal tuning loops should be modeled and, if necessary, the systems could be programmed to respond on different time scales, one reacting to long term drifts, the other to short term fluctuations. Transfer functions of both thermal and mechanical tuning are known from the MTA tests.

## Slide 10: Recommendations
Close collaboration with the ISIS LINAC RF team is required. Fortunately collaboration between DL and RAL was started before the key DL personnel left. MICE Management should pursue strengthening this relationship further.
Direct involvement of the ISIS RF experts at an early stage and during commissioning is highly desirable. Support from the ISIS RF team will be essential during the experimental running when the initial commissioning team may not be on hand. We note that the ISIS LINAC section is also small and highly committed so the possibility of a joint hire(s) should be considered.
The RF distribution system, as currently designed, should be mocked up as soon as possible. Specifically the ability to safely connect the Heliax sections should be verified.

## Slide 11: Recommendations
The interlock system must consist of dedicated analog and digital hardware with no computer in the series link other than a processor for reporting status. Latching is essential for diagnosing intermittent faults. This is an extensive system that will not only monitor the RF, but also vacuum, water, controls, beam permit, etc. Not a trivial task and will require significant effort to implement.

## Slide 12: Recommendations
The tasks at hand are considerable and it is not clear the existing staff is adequate to bring the project to a successful result within the allotted time frame. The committee is concerned that the required resources are significantly underestimated and recommends that a re-evaluation of the required resources and potential sources of electrical and RF expertise be prepared.
  In addition, most of the collaboration is not based at RAL, so a dedicated on site staff must be made available for the duration of the experiment to implement repairs and modifications. Delays for repairs and control interfaces must be avoided and can only be satisfied with an on-site team.