## Change log
Version Date | Description of Change(s) | Person(s) making change | Comments | Have Risk Dollars been moved yet? | Amount
2014-12-10 | Added Quality to the assessment Matrix. This is now a part of the previuos ES&H. Now it will be ESH&Q. | Ron Ray |  | N/A
2014-12-10 | Moved CONST-049 to realized tab | Mike Dinnon | Tom states that $154,364 is the amount of the opportunity. We need to account for this change when we get a schedule from the contractor | No
2014-12-10 | Moved CONST-165 to retired tab | Mike Dinnon | Contract is out so no more changes accepted. Need to move $47K into available contingency | No | $47K
2014-12-10 | Accepted Quality rankings in the risk register | Mike Dinnon | Per CD2 Review we have added Quality into our analysis | N/A
2015-01-12 | Added risk SOL-205 TS Prototype Coil Module test failure | Mike Dinnon | Successful TS Prototype test is a prerequisite to place TS Coil Module Purchase Order. Placement of the PO is on the project critical path. Thus, a delay in completing a successful prototype test delays the project schedule. | No
2015-01-21 | Risk Management Board Meeting 1-16-15 Changes--- ACCEL-015 - changed FY16-19 to FY17-19 - changed owner to Steve Werkema ACCEL-020 - changed probablity from VL to L MUON-138 - changed FY19 to FY19 -20 - changed schedule from M to N PM-153 - changed date from FY16-18 to FY16-19 - changed point estimate from 50% to 51% PM-154 - changed date from FY16-18 to FY16-19 SOL-148 - changed FY18-19 to FY19-20 - changed T.Page to M.Lamm as owner SOL-183 - changed FY20 to FY16-17 TRACK-169 - changed FY15 to FY15-16 - changed cost from H to VH | Mike Dinnon | High risk entries were reviewed at the 1-16-2015 RMB. The changes are reflected here and the forms have been updated as well. | N/A
2015-01-26 | Updated Transferred Risk tab with the updated information supplied by Doug from the RMB meeting 1-16-15 | Mike Dinnon | Transferred risk items were reviewed initially by Doug and then brought to the board for final discussion before submittal. | N/A
2015-01-26 | Added changes to the Risk Dollars per year tab per discussion with Ron | Mike Dinnon | With changes to dates of risk, the funding profile of risk items has changed | N/A
2015-01-27 | Updated Transferred Risk tab 1) MUON-143 had a VH cost impact but a point estimate of only 75k. It’s corrected to be $750k. 2) ACCEL-152 had a Schedule Delay score of N, should have be M. Also, the point estimate read “0”, changed to be $175k. | Mike Dinnon | Few typos that were corrected | N/A
2015-03-11 | Trigger/DAQ changes- TRIG-134 column E - change "FY15-FY19" to "FY17" (not a FY15 risk) column H - change "M" to "L" column Q - change "25%" to "10%" TRIG-135 column H - change "L" to "M" column Q - change "10%" to "30%" TRIG-136 column E - change "FY15-FY19" to "FY18-FY19" (not a FY15 risk) TRIG-130 column Q - change "30%" to "50%" TRIG -131 column E - change "FY16-FY19" to "FY19" | Mike Dinnon | Changes for 3-13-15 RMB discussion on FY15 risks
2015-05-13 | TRACK-092 Change: FY15-FY16 to FY16. VETO-122 Change: FY15-FY20 to FY17. TRACK-206 transferred to operations | Mike Dinnon | Changes from March RMB
2015-05-15 | Realized Sol-155 | Mike Dinnon | Changes from May RMB |  | $1.972M
2015-06-12 | Retired Accel-020 | Mike Dinnon | Changes from June RMB |  | $108K
2015-09-11 | ACCEL-203 Extend end date to FY17 | Mike Dinnon | Changes from September RMB
2015-09-11 | SOL-205 Retired | Mike Dinnon | Changes from September RMB |  | $17K
2015-09-11 | TRACK-139 Retired | Mike Dinnon | Changes from September RMB |  | $9K
2015-09-11 | TRACK-166 Change probability from 25% to 5% | Mike Dinnon | Changes from September RMB
2015-09-11 | TRACK-169 Extend end date to FY17 | Mike Dinnon | Changes from September RMB
2015-09-11 | All TRIG changed owner to Ryan Rivera | Mike Dinnon | Changes from September RMB
2015-09-11 | VETO-122 Extend end date to FY17 | Mike Dinnon | Changes from September RMB
2015-09-11 | VETO-159 Extend end date to FY16 | Mike Dinnon | Changes from September RMB
2015-09-11 | VETO-162 Extend end date to FY16 | Mike Dinnon | Changes from September RMB
2015-09-11 | VETO-163 Extend end date to FY16 | Mike Dinnon | Changes from September RMB
2015-09-11 | ACCEL-038 The choice of target cooling is made; Need to change risk; Will do when better understand the cost impact | Mike Dinnon | Changes from September RMB
2015-09-11 | ACCEL-151 Some RH design modifications are being made; Will need to change risk; Will do when better understand the cost impact | Mike Dinnon | Changes from September RMB
2015-09-11 | MUON-147 change prob to 80% | Mike Dinnon | Changes from September RMB
2015-09-11 | PM-008 work with Ron to update | Mike Dinnon | Changes from September RMB
2015-09-11 | PM-009 work with Ron to update | Mike Dinnon | Changes from September RMB
2015-09-11 | SOL-183 Extend end date to FY19 | Mike Dinnon | Changes from September RMB
2015-09-11 | SOL-189 Change probability to Low 25% | Mike Dinnon | Changes from September RMB
2015-09-11 | no change | Mike Dinnon | Changes from September RMB
2015-09-11 | TRACK-167 Change to FY17-18 | Mike Dinnon | Changes from September RMB
2015-09-11 | TRIG-131 Change Owner to Ryan Rivera- Ryan has updated also | Mike Dinnon | Changes from September RMB

## RISK REGISTER
[19 empty] | y | Include Opportunities?
DocDb#-4320 |  | Next ID 208
Risk | [6 empty] | Post-mitigation | [11 empty] | Risk Contingency $ | [6 empty] | NOTES:
Risk ID | Risk Form DocDb # | Type | Title | Date of Risk | Mitigation Cost (Included in baseline) | Category | Probability | Schedule-Delays Level 3 Milestone or Project Critical Path by X Days | Cost | Technical | ESH&Q | Score | Owner | Point estimate (cost k$) | Point Estimate (sched-days) | Point estimate (prob) | EXPECTATION VALUE IN k$ | EXPECTATION VALUE IN Days | Prob Range |  | Prob RMS | 80%CL | 85% CL | 90% CL
ACCEL-011 | 3328 | Threat | Inadequate AD Engineering Resources | FY15-FY19 |  | Current Risk | M | L | N | N | N | L | Ron Ray | 75000 | 60 | 25% | 18750 | 15 | 25% | 75% | 14.43% | 36.5101 | 37.725 | 39.25
ACCEL-015 | 3331 | Threat | Injection damper required for Delivery Ring | FY17-FY19 |  | Current Risk | L | N | N | VH | N | H | S. Werkema | 185000 | 0 | 10% | 18500 | 0 | 10% | 25% | 4.33% | 31.6425 | 32.5415 | 33.67
ACCEL-038 | 3344 | Threat | Radiated target will not survive in the Beam. | FY16-FY20 | 100000 | Current Risk | L | N | M | N | N | M | R. Coleman | 175000 |  | 10% | 17500 | 0 | 10% | 25% | 4.33% | 29.9321 | 30.7825 | 31.85
ACCEL-151 | 3833 | Threat | Redesign the Remote Handling System for Water cooled target | FY16-FY18 | 100000 | Current Risk | VL | N | VH | M | N | H | M.Campbell, R.Coleman | 3300000 |  | 5% | 165000 | 0 | 0% | 10% | 2.887% | 211.2891 | 221.98 | 235.4
ACCEL-200 | 4589 | Threat | Need to add new power supplies to the beam line. | FY15-FY16 | 20000 | Current Risk | M | VL | H | VL | N | H | D. Still | 400000 | 20 | 60% | 240000 | 12 | 25% | 75% | 14.43% | 241.3873 | 247.8667 | 256
ACCEL-201 | 4590 | Threat | Need to fabricate additional magnets to the beam line. | FY15-FY16 | 20000 | Current Risk | L | VL | M | VL | N | M | D. Still | 200000 | 20 | 20% | 40000 | 4 | 10% | 25% | 4.33% | 40.8748 | 41.8467 | 43.0667
ACCEL-202 | 4591 | Opportunity | Replace the Diagnostic Absorber dipole with an existing magnet | FY15-FY16 | 5000 | Current Risk | M | VL | M | VL | N | M | D. Still | -110000 | 20 | 50% | -55000 | 10 | 25% | 75% | 14.43% | -62.7148 | -64.4967 | -66.7333
ACCEL-203 | 4592 | Opportunity | Availability of spare sextupole magnets for use in Mu2e | FY15-FY17 |  | Current Risk | L | N | M | N | N | M | V.Nagaslaev | -166000 |  | 15% | -24900 | 0 | 10% | 25% | 4.33% | -31.1594 | -31.9661 | -32.9787
ACCEL-204 | 4593 | Threat | Need to add 2 more collimators to the Extinction section | FY15-FY16 |  | Current Risk | L | N | M | N | N | M | E.Prebys | 160000 |  | 10% | 16000 | 0 | 10% | 25% | 4.33% | 27.3665 | 28.144 | 29.12 | 525.1281
CAL-108 | 3347 | Threat | INFN cannot deliver full in-kind scope. | FY16-FY20 |  | Current Risk | L | N | N | H | N | H | R. Ray | 0 |  | 10% | 0 | 0 | 10% | 25% | 4.33% | 0 | 0 | 0
CAL-148 | 3834 | Threat | Cannot develop UV-extended solid state photodetector that is blind to longer wavelengths | FY15 | 100000 | Current Risk | M | M | N | H | N | H | D. Hitlin | 0 | 40 | 50% |  | 20 | 25% | 75% |  | 0 | 0 | 0
CAL-170 | 4468 | Threat | Inability to purchase DT generator from Russia | FY18-FY19 |  | Current Risk | M | N | L | N | N | L | Frank Porter | 90000 | 0 | 50% | 45000 | 0 | 25% | 75% | 14.43% | 51.3122 | 52.77 | 54.6 | 51
MUON-138 | 3360 | Threat | Detector installation takes longer than expected. | FY19-FY20 |  | Current Risk | M | N | H | N | N | H | G. Ginther | 400000 | 0 | 50% | 200000 | 0 | 25% | 75% | 14.43% | 228.054 | 234.5333 | 242.6667
MUON-146 | 3835 | Threat | Rates exceed Muon Stopping Target Monitor capabilities | FY17-18 |  | Current Risk | M | N | M | M | N | M | J. Miller | 200000 |  | 25% | 50000 | 0 | 25% | 75% | 14.43% | 97.3603 | 100.6 | 104.6667
MUON-147 | 3836 | Threat | Degrader needed for calibration | FY16-FY19 |  | Current Risk | M | N | M | M | VL | M | G. Ginther | 250000 |  | 80% | 200000 | 0 | 25% | 75% | 14.43% | 167.5337 | 171.5833 | 176.6667 | 492.9481
MUON-207 | 6045 | Threat | Inner Proton Absorber cannot be effectively realized in polymer | FY18 |  | Current Risk | L | VL | L | L | M |  | Hank Glass | 300000 | 30 | 15% | 45000 | 4.5 | 10% | 25% | 4.33% | 56.3122 | 57.77 | 59.6
PM-007 | 3363 | Threat | CD-4 float inadequate. | FY20 |  | Current Risk | L | M | L | N | N | M | Ron Ray | 2545787 | 500 | 10% | 0 | 50 | 10% | 25% | 4.33% | 435.4327 | 447.8039 | 463.3332
PM-008 | 3364 | Threat | Additional resources required in Project Office to manage Project. | FY16-FY20 |  | Current Risk | L | N | H | N | N | M | Ron Ray | 500000 |  | 25% | 125000 | 0 | 10% | 25% | 4.33% | 110.5203 | 112.95 | 116
PM-009 | 3365 | Opportunity | Fewer Resources than anticipated required in Project Office to manage Project. | FY16-FY20 |  | Current Risk | L | N | M | N | N | M | Ron Ray | -500000 |  | 10% | -50000 | 0 | 10% | 25% | 4.33% | -85.5203 | -87.95 | -91
PM-010 | 3366 | Threat | Increase in Fermilab overhead rates | FY16-FY20 |  | Current Risk | M | N | VH | N | N | H | Ron Ray | 1500000 | 0 | 50% | 750000 | 0 | 25% | 75% | 14.43% | 855.2025 | 879.5 | 910
PM-048 | 3350 | Threat | Significant injury or death associated with Mu2e construction/assembly. | FY15-FY20 | 25000 | Current Risk | VL | H | VH | N | VH | M | R. Ray | 1000000 | 260 | 1% | 10000 | 2.6 | 0% | 10% | 2.887% | 50.6937 | 53.9333 | 58
PM-142 | 3757 | Threat | Currency fluctuations on foreign procurements | FY17-FY18 |  | Current Risk | L | N | VL | N | N | L | Ron Ray | 100000 | 0 | 10% | 10000 | 0 | 10% | 25% | 4.33% | 17.1041 | 17.59 | 18.2
PM-153 | 3844 | Opportunity | Commodity prices decrease | FY16-FY19 |  | Current Risk | L | N | VH | N | N | H | Ron Ray | -1173000 |  | 10% | -117300 |  | 10% | 25% | 4.33% | -200.6305 | -206.3307 | -213.486
PM-154 | 3845 | Threat | Commodity prices escalate faster than inflation | FY16-FY19 |  | Current Risk | L | N | VH | N | N | H | Ron Ray | 1173000 |  | 20% | 234600 |  | 10% | 25% | 4.33% | 239.7305 | 245.4307 | 252.586 | 1422.5329
SOL-070 | 3368 | Threat | Interface problems with the solenoids. | FY17-FY20 |  | Current Risk | L | H | VH | N | N | H | M. Lamm | 1000000 | 60 | 20% | 200000 | 12 | 10% | 25% | 4.33% | 204.3738 | 209.2333 | 215.3333
SOL-137 | 3373 | Threat | Solenoid fringe field impacts performance of nearby equipment | FY17-FY20 | 100000 | Current Risk | L | N | L | L | M | M | K. Krempetz | 100000 |  | 20% | 20000 | 0 | 10% | 25% | 4.33% | 20.4374 | 20.9233 | 21.5333
SOL-148 | 3837 | Threat | Production Solenoid must be installed through PS hatch using a large rented crane. | FY19-20 |  | Current Risk | M | N | H | N | N | H | M. Lamm | 300000 |  | 50% | 150000 | 0 | 25% | 75% | 14.43% | 171.0405 | 175.9 | 182
SOL-171 | 4556 | Threat | Production cable does not meet specification | FY16 | 700000 | Current Risk | VL | H | N | N | L | L | M.Lamm | 2000000 | 250 | 10% | 200000 | 25 | 0% | 10% | 2.887% | 161.3873 | 167.8667 | 176
SOL-172 | 4557 | Threat | DS Magnet fabrication failure due to process or component | FY18-19 | 700000 | Current Risk | VL | H | VH | M | L | M | M.Lamm | 4000000 | 250 | 10% | 400000 | 25 | 0% | 10% | 2.887% | 322.7747 | 335.7333 | 352
SOL-173 | 4558 | Threat | Completed cryostated magnet does not pass acceptance tests at vendor | FY18-19 |  | Current Risk | VL | M | N | N | L | L | M.Lamm | 1000000 | 125 | 10% | 100000 | 12.5 | 0% | 10% | 2.887% | 80.6937 | 83.9333 | 88
SOL-174 | 4559 | Threat | Vendor delays not caused by FNAL | FY18-19 |  | Current Risk | L | L | N | N | N | L | M.Lamm | 520000 | 65 | 25% | 130000 | 16.25 | 10% | 25% | 4.33% | 114.9411 | 117.468 | 120.64
SOL-175 | 4560 | Threat | Magnet is damaged during shipping and handling | FY19 |  | Current Risk | VL | H | N | N | N | L | M.Lamm | 2000000 | 250 | 5% | 100000 | 12.5 | 0% | 10% | 2.887% | 128.054 | 134.5333 | 142.6667
SOL-176 | 4561 | Threat | Operational failure during final acceptance tests at FNAL. | FY20 |  | Current Risk | VL | VH | VH | N | L | M | M.Lamm | 4500000 | 500 | 10% | 450000 | 50 | 0% | 10% | 2.887% | 363.1215 | 377.7 | 396
SOL-177 | 4562 | Threat | DS Magnet fabrication failure due to process or component | FY18-19 | 200000 | Current Risk | VL | M | H | N | L | L | M.Lamm | 1500000 | 125 | 10% | 150000 | 12.5 | 0% | 10% | 2.887% | 121.0405 | 125.9 | 132
SOL-178 | 4563 | Threat | Completed cryostated magnet does not pass acceptance tests at vendor | FY20 |  | Current Risk | VL | M | N | N | L | L | M.Lamm | 1000000 | 125 | 10% | 100000 | 12.5 | 0% | 10% | 2.887% | 80.6937 | 83.9333 | 88
SOL-179 | 4564 | Threat | Vendor delays not caused by FNAL | FY18-19 |  | Current Risk | L | L | N | N | N | L | M.Lamm | 520000 | 65 | 25% | 130000 | 16.25 | 10% | 25% | 4.33% | 114.9411 | 117.468 | 120.64
SOL-180 | 4565 | Threat | Magnet is damaged during shipping and handling | FY20 |  | Current Risk | VL | H | N | N | N | L | M.Lamm | 2000000 | 250 | 5% | 100000 | 12.5 | 0% | 10% | 2.887% | 128.054 | 134.5333 | 142.6667
SOL-181 | 4566 | Threat | Operational failure during final acceptance tests at FNAL. | FY20 |  | Current Risk | VL | VH | VH | N | N | M | M.Lamm | 4500000 | 500 | 5% | 225000 | 25 | 0% | 10% | 2.887% | 288.1215 | 302.7 | 321
SOL-182 | 4567 | Threat | Delay in FNAL supplied processes or components | FY17-19 |  | Current Risk | L | L | N | N | N | L | M.Lamm | 520000 | 65 | 15% | 78000 | 9.75 | 10% | 25% | 4.33% | 97.6077 | 100.1347 | 103.3067
SOL-183 | 4568 | Threat | TS Magnet fabrication failure due supplied process or component | FY18-19 | 200000 | Current Risk | M | L | M | N | N | H | M.Lamm | 620000 | 65 | 40% | 248000 | 26 | 25% | 75% | 14.43% | 332.817 | 342.86 | 355.4667
SOL-184 | 4569 | Threat | Vendor delays not caused by FNAL | FY18-19 |  | Current Risk | L | L | N | N | N | L | M.Lamm | 350000 | 42 | 25% | 87500 | 10.5 | 10% | 25% | 4.33% | 77.3642 | 79.065 | 81.2
SOL-185 | 4570 | Threat | Damage to the coil module during shipping and handling | FY18-19 |  | Current Risk | VL | L | M | N | N | L | M.Lamm | 770000 | 65 | 5% | 38500 | 3.25 | 0% | 10% | 2.887% | 49.3008 | 51.7953 | 54.9267
SOL-186 | 4571 | Threat | Failure of design or fabrication of Fermilab designed cryogenic system | FY18-19 |  | Current Risk | VL | H | H | N | L | L | M.Lamm | 2500000 | 250 | 10% | 250000 | 25 | 0% | 10% | 2.887% | 201.7342 | 209.8333 | 220
SOL-187 | 4572 | Threat | Integrated module out of tolerances | FY18-19 |  | Current Risk | VL | L | N | N | L | L | M.Lamm | 520000 | 65 | 10% | 52000 | 6.5 | 0% | 10% | 2.887% | 41.9607 | 43.6453 | 45.76
SOL-188 | 4573 | Threat | Final assembled magnet does not perform as designed | FY20 |  | Current Risk | VL | H | H | N | L | L | M.Lamm | 2500000 | 250 | 10% | 250000 | 25 | 0% | 10% | 2.887% | 201.7342 | 209.8333 | 220
SOL-189 | 4574 | Threat | Fermilab space or personnel resources not available when needed for final assembly | FY16-19 |  | Current Risk | L | M | VH | N | N | M | M.Lamm | 2000000 | 125 | 25% | 500000 | 31.25 | 10% | 25% | 4.33% | 442.081 | 451.8 | 464
SOL-190 | 4575 | Threat | Building is Not Ready-Unable to start infrastructure installation | FY16 |  | Current Risk | L | M | N | N | N | M | M.Lamm | 1000000 | 125 | 25% | 250000 | 31.25 | 10% | 25% | 4.33% | 221.0405 | 225.9 | 232
SOL-191 | 4576 | Threat | Cryogenics, Power, or Vacuum Infrastructure Not available for commissioning | FY18-19 |  | Current Risk | L | M | N | N | N | M | M.Lamm | 1000000 | 125 | 25% | 250000 | 31.25 | 10% | 25% | 4.33% | 221.0405 | 225.9 | 232
SOL-192 | 4577 | Threat | Manpower not available to start commissioning | FY19-20 |  | Current Risk | L | M | N | N | N | M | M.Lamm | 500000 | 60 | 10% | 50000 | 6 | 10% | 25% | 4.33% | 85.5203 | 87.95 | 91
SOL-193 | 4578 | Threat | Support Frames require major rework | FY18-19 |  | Current Risk | VL | M | L | N | N | L | M.Lamm | 1100000 | 125 | 10% | 110000 | 12.5 | 0% | 10% | 2.887% | 88.763 | 92.3267 | 96.8
SOL-194 | 4579 | Threat | Installation Tooling not adequate | FY18-19 |  | Current Risk | L | L | L | N | N | L | M.Lamm | 620000 | 65 | 15% | 93000 | 9.75 | 10% | 25% | 4.33% | 116.3784 | 119.3913 | 123.1733
SOL-195 | 4580 | Threat | Vendor delays during Feedbox fabrication | FY17-19 |  | Current Risk | L | L | N | N | N | L | M.Lamm | 520000 | 65 | 25% | 130000 | 16.25 | 10% | 25% | 4.33% | 114.9411 | 117.468 | 120.64
SOL-196 | 4581 | Threat | HTS leads damage during assembly | FY17-19 |  | Current Risk | L | L | VL | N | N | L | M.Lamm | 570000 | 65 | 15% | 85500 | 9.75 | 10% | 25% | 4.33% | 106.9931 | 109.763 | 113.24
SOL-197 | 4582 | Threat | Cold leak in Feedbox | FY19 |  | Current Risk | L | M | N | N | VL | M | M.Lamm | 1000000 | 125 | 25% | 250000 | 31.25 | 10% | 25% | 4.33% | 221.0405 | 225.9 | 232
SOL-198 | 4583 | Threat | Cryo, vacuum or electrical problems in cryo lines | FY18-19 |  | Current Risk | L | L | L | N | VL | L | M.Lamm | 620000 | 65 | 25% | 155000 | 16.25 | 10% | 25% | 4.33% | 137.0451 | 140.058 | 143.84
SOL-199 | 4584 | Threat | Unanticipated building interferences with cryoline | FY18 |  | Current Risk | L | L | L | N | N | L | M.Lamm | 620000 | 65 | 25% | 155000 | 16.25 | 10% | 25% | 4.33% | 137.0451 | 140.058 | 143.84
TRACK-091 | 3382 | Threat | Simulations indicate that tracker occupancy higher than expected | FY15-FY16 |  | Current Risk | VL | L | L | N | N | L | D.Brown | 50000 | 30 | 5% | 2500 | 1.5 | 0% | 10% | 2.887% | 3.2014 | 3.3633 | 3.5667
TRACK-092 | 3383 | Threat | Need to switch straw manufacturer | FY16 |  | Current Risk | L | H | VL | N | N | M | A. Mukherjee | 100000 | 250 | 5% | 5000 | 12.5 | 10% | 25% | 4.33% | 15.4374 | 15.9233 | 16.5333
TRACK-096 | 3385 | Threat | Detector support structure not sufficiently rigid or stable | FY15-FY17 | 62000 | Current Risk | L | N | M | M | N | M | A. Mukherjee | 100000 |  | 25% | 25000 | 0 | 10% | 25% | 4.33% | 22.1041 | 22.59 | 23.2
TRACK-104 | 3390 | Threat | Gain loss in tracker. | FY15-FY17 | 5000 | Current Risk | L | M | H | L | N | M | A. Mukherjee | 500000 | 40 | 10% | 50000 | 4 | 10% | 25% | 4.33% | 85.5203 | 87.95 | 91
TRACK-166 | 4445 | Threat | High crosstalk | FY15-FY16 | 5000 | Current Risk | M | N | L | M | N | M | A. Mukherjee | 50000 | 0 | 5% | 2500 | 0 | 25% | 75% | 14.43% | 21.0068 | 21.8167 | 22.8333
TRACK-167 | 4446 | Opportunity | Drop in price of COTS components | FY17-18 |  | Current Risk | H | N | L | N | N | M | A. Mukherjee | -50000 | 0 | 25% | -12500 | 0 | 75% | 90% | 4.33% | -32.7187 | -32.9617 | -33.2667
TRACK-168 | 4447 | Opportunity | Drop in price of 3D printing | FY15-FY16 |  | Current Risk | M | N | M | N | N | M | A. Mukherjee | -100000 | 0 | 50% | -50000 | 0 | 25% | 75% | 14.43% | -57.0135 | -58.6333 | -60.6667
TRACK-169 | 4444 | Threat | Background levels >4x expectation necessitate additional Tracker stations | FY15-FY17 |  | Current Risk | M | N | VH | M | N | H | A. Mukherjee | 1000000 | 0 | 25% | 250000 | 0 | 25% | 75% | 14.43% | 486.8017 | 503 | 523.3333 | 544.3393
TRIG-128 | 3393 | Threat | Insufficient manpower for DAQ software. | FY17-FY20 |  | Current Risk | M | N | H | N | N | H | Ryan Rivera | 500000 |  | 25% | 125000 | 0 | 25% | 75% | 14.43% | 243.4008 | 251.5 | 261.6667
TRIG-130 | 3394 | Threat | Insufficient DAQ online processing. | FY18-FY19 |  | Current Risk | M | N | L | N | N | L | Ryan Rivera | 70000 |  | 50% | 35000 | 0 | 25% | 75% | 14.43% | 39.9094 | 41.0433 | 42.4667
TRIG-131 | 3395 | Threat | Higher than expected data rates to the DAQ. | FY19 |  | Current Risk | M | N | VL | N | N | L | Ryan Rivera | 100000 |  | 50% | 50000 | 0 | 25% | 75% | 14.43% | 57.0135 | 58.6333 | 60.6667
TRIG-132 | 3396 | Opportunity | Use of surplus equipment for DAQ. | FY17 |  | Current Risk | M | N | L | N | N | L | Ryan Rivera | -30000 |  | 50% | -15000 | 0 | 25% | 75% | 14.43% | -17.1041 | -17.59 | -18.2
TRIG-134 | 3397 | Opportunity | Lower cost commercial PCIe card for DTC. | FY17 |  | Current Risk | L | N | L | N | N | L | Ryan Rivera | -20000 |  | 10% | -2000 | 0 | 10% | 25% | 4.33% | -3.4208 | -3.518 | -3.64
TRIG-135 | 3398 | Opportunity | Slow Controls development in common with other experiments. | FY15-FY19 |  | Current Risk | L | N | L | N | N | L | Ryan Rivera | -40000 |  | 30% | -12000 | 0 | 10% | 25% | 4.33% | -9.5083 | -9.7027 | -9.9467
TRIG-136 | 3399 | Opportunity | Efficient Calorimeter Trigger reduces online processing requirements. | 50 |  | Current Risk | L | N | L | N | N | L | Ryan Rivera | -40000 |  | 10% | -4000 | 0 | 10% | 25% | 4.33% | -6.8416 | -7.036 | -7.28 | 303.449
VETO-114 | 3400 | Threat | Simulations indicate that neutron flux at the CRV is too high. | FY17-FY20 | 2000000 | Current Risk | L | N | H | H | N | M | C. Dukes | 2000000 | 0 | 10% | 200000 | 0 | 10% | 25% | 4.33% | 342.081 | 351.8 | 364
VETO-122 | 3402 | Threat | Need to use inferior fibers | FY-15-FY17 |  | Current Risk | L | N | L | VL | N | M | C. Dukes | 50000 |  | 20% | 10000 | 0 | 10% | 25% | 4.33% | 10.2187 | 10.4617 | 10.7667
VETO-156 | 4199 | Threat | Can’t control size and shape of fiber holes in extruded scintillator | FY17-FY18 |  | Current Risk | L | H | H | M | N | M | A. Pla | 500000 | 200 | 20% | 100000 | 40 | 10% | 25% | 4.33% | 102.1869 | 104.6167 | 107.6667
VETO-158 | 4257 | Threat | Custom SiPM size is needed | FY17 |  | Current Risk | L | N | VL | N | N | L | C. Dukes | 50000 | 0 | 20% | 10000 | 0 | 10% | 25% | 4.33% | 10.2187 | 10.4617 | 10.7667
VETO-159 | 4260 | Threat | Photoelectron yield does not meet requirements. | FY16 |  | Current Risk | L | N | L | N | N | L | C. Dukes | 150000 | 0 | 20% | 30000 | 0 | 10% | 25% | 4.33% | 30.6561 | 31.385 | 32.3
VETO-161 | 4262 | Opportunity | UVa on-campus space can be found for module factory. | FY17-18 |  | Current Risk | M | N | L | N | N | L | C. Dukes | -100000 | 0 | 50% | -50000 | 0 | 25% | 75% | 14.43% | -57.0135 | -58.6333 | -60.6667
VETO-162 | 4259 | Opportunity | Photoelectron yield exceeds requirements. | FY16 |  | Current Risk | M | N | L | N | N | L | C. Dukes | -100000 | 0 | 50% | -50000 | 0 | 25% | 75% | 14.43% | -57.0135 | -58.6333 | -60.6667
VETO-163 | 4263 | Opportunity | Wider counters can be extruded that meet specifications. | FY16 |  | Current Risk | M | N | L | N | N | L | C. Dukes | -200000 | 0 | 50% | -100000 | 0 | 25% | 75% | 14.43% | -114.027 | -117.2667 | -121.3333
VETO-164 | 4258 | Threat | More CRV coverage is needed. | FY17-FY20 |  | Current Risk | H | N | VL | N | N | L | C. Dukes | 60000 | 0 | 80% | 48000 | 0 | 67.5% | 92.5% | 7.217% | 50.1041 | 50.59 | 51.2 | 318.4114
[5 empty] | 4342000 | [8 empty] | 57474787 | 5847 |  | 8073150 | 725.85 |  | 0.75 |  | 8907.5152 | 9187.2755 | 9538.4512 | 3657.8088
|  |  |  | Retired Mitigation | 40000 | [15 empty] | amount with $1245K credit from 2015 | 6803
|  |  |  | Transferred Mitigation | 3685000
|  |  |  | Deleted Mitigation | 470000
|  |  |  | Total Mitigation Costs | 8537000
Note on D84: A custom SiPM size will be needed, most likely due to the need to keep the dark-noise rate, which scales are SiPM active area, within specifications.
Note on D85: The photoelectron yield is less than expected. This would require a larger diameter fiber (and larger associated SiPM only in the case that a custom SiPM size is required).
Note on D86: If space can be found to fabricate the modules at on-campus facilities at UVA, this eliminates the need to rent space for the module fabrication factory. The search for suitable sites is being actively pursued by UVA collaborators.
Note on D87: The photoelectron yield is greater than expected due to the availability of SiPMs with higher PDEs. This would allow a smaller diameter fiber and perhaps a smaller SiPM to be used.
Note on D88: The gaps between counters are too large to allow the efficiency requirement to be met. The easiest way to mitigate this would be to fabricate wider counters, 6 cm to 7 cm, which allow wider gaps without adversely affecting the efficiency requirement. This would require minor redesigns to various components of the CRV, including items such as counter motherboards, modules, and the support structure. The increased cost would be offset by the smaller number of fibers, SiPMs, and front-end boards.
Note on D89: More coverage will be needed with CRV-D. A very recent simulation targeting cosmic-ray muons entering in the downstream sector show that three events over the course of the entire running period enter just below the module coverage. All are vetoed by the calorimeter. Simulating with more statistics may show that some events are not vetoed by the calorimeter or CRV, and hence more coverage is needed.

## Risk Dollars per year
[19 empty] | y | Include Opportunities?
DocDb#-4320 |  | Next ID 208 | [24 empty] | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
Risk | [6 empty] | Post-mitigation | [11 empty] | Risk Contingency $ | [6 empty] | NOTES:
Risk ID | Risk Form DocDb # | Type | Title | Date of Risk | Mitigation Cost (Included in baseline) | Category | Probability | Schedule-Delays Level 3 Milestone or Project Critical Path by X Days | Cost | Technical | ESH&Q | Score | Owner | Point estimate (cost k$) | Point Estimate (sched-days) | Point estimate (prob) | EXPECTATION VALUE IN k$ | EXPECTATION VALUE IN Days | Prob Range |  | Prob RMS | 80%CL | 85% CL | 90% CL
ACCEL-011 | 3328 | Threat | Inadequate AD Engineering Resources | FY15-FY19 |  | Current Risk | M | L | N | N | N | L | Ron Ray | 75000 | 60 | 25% | 18750 | 15 | 25% | 75% | 14.43% | 36.5101 | 37.725 | 39.25 |  |  | 37 | [7 empty] | 36.5101
ACCEL-015 | 3331 | Threat | Injection damper required for Delivery Ring | FY17-FY19 |  | Current Risk | L | N | N | VH | N | H | S. Werkema | 185000 | 0 | 10% | 18500 | 0 | 10% | 25% | 4.33% | 31.6425 | 32.5415 | 33.67 |  |  |  |  | 32 | [5 empty] | 31.6425
ACCEL-020 |  |  |  | retired 2015 | [22 empty] | -108
ACCEL-038 | 3344 | Threat | Radiated target will not survive in the Beam. | FY16-FY20 | 100000 | Current Risk | L | N | M | N | N | M | R. Coleman | 175000 |  | 10% | 17500 | 0 | 10% | 25% | 4.33% | 29.9321 | 30.7825 | 31.85 |  |  |  | 30 | [6 empty] | 29.9321
ACCEL-151 | 3833 | Threat | Redesign the Remote Handling System for Water cooled target | FY16-FY18 | 100000 | Current Risk | VL | N | VH | M | N | H | M.Campbell, R.Coleman | 3300000 |  | 5% | 165000 | 0 | 0% | 10% | 2.887% | 211.2891 | 221.98 | 235.4 |  |  |  | 211 | [6 empty] | 211.2891
ACCEL-200 | 4589 | Threat | Need to add new power supplies to the beam line. | FY15-FY16 | 20000 | Current Risk | M | VL | H | VL | N | H | D. Still | 400000 | 20 | 60% | 240000 | 12 | 25% | 75% | 14.43% | 241.3873 | 247.8667 | 256 |  |  | 241 | [7 empty] | 241.3873
ACCEL-201 | 4590 | Threat | Need to fabricate additional magnets to the beam line. | FY15-FY16 | 20000 | Current Risk | L | VL | M | VL | N | M | D. Still | 200000 | 20 | 20% | 40000 | 4 | 10% | 25% | 4.33% | 40.8748 | 41.8467 | 43.0667 |  |  | 41 | [7 empty] | 40.8748
ACCEL-202 | 4591 | Opportunity | Replace the Diagnostic Absorber dipole with an existing magnet | FY15-FY16 | 5000 | Current Risk | M | VL | M | VL | N | M | D. Still | -110000 | 20 | 50% | -55000 | 10 | 25% | 75% | 14.43% | -62.7148 | -64.4967 | -66.7333 |  |  | -63 | [7 empty] | -62.7148
ACCEL-203 | 4592 | Opportunity | Availability of spare sextupole magnets for use in Mu2e | FY15-FY17 |  | Current Risk | L | N | M | N | N | M | V.Nagaslaev | -166000 |  | 15% | -24900 | 0 | 10% | 25% | 4.33% | -31.1594 | -31.9661 | -32.9787 |  |  | -31 | [7 empty] | -31.1594
ACCEL-204 | 4593 | Threat | Need to add 2 more collimators to the Extinction section | FY15-FY16 |  | Current Risk | L | N | M | N | N | M | E.Prebys | 160000 |  | 10% | 16000 | 0 | 10% | 25% | 4.33% | 27.3665 | 28.144 | 29.12 | 525.1281 |  | 27 | [7 empty] | 27.3665
CAL-108 | 3347 | Threat | INFN cannot deliver full in-kind scope. | FY16-FY20 |  | Current Risk | L | N | N | H | N | H | R. Ray | 0 |  | 10% | 0 | 0 | 10% | 25% | 4.33% | 0 | 0 | 0 | [10 empty] | 0
CAL-148 | 3834 | Threat | Cannot develop UV-extended solid state photodetector that is blind to longer wavelengths | FY15 | 100000 | Current Risk | M | M | N | H | N | H | D. Hitlin | 0 | 40 | 50% |  | 20 | 25% | 75% |  | 0 | 0 | 0 | [10 empty] | 0
CAL-170 | 4468 | Threat | Inability to purchase DT generator from Russia | FY18-FY19 |  | Current Risk | M | N | L | N | N | L | Frank Porter | 90000 | 0 | 50% | 45000 | 0 | 25% | 75% | 14.43% | 51.3122 | 52.77 | 54.6 | 51 |  |  |  |  | 51 |  |  |  |  | 51.3122
MUON-138 | 3360 | Threat | Detector installation takes longer than expected. | FY19-FY20 |  | Current Risk | M | N | H | N | N | H | G. Ginther | 400000 | 0 | 50% | 200000 | 0 | 25% | 75% | 14.43% | 228.054 | 234.5333 | 242.6667 | [6 empty] | 228 |  |  |  | 228.054
MUON-146 | 3835 | Threat | Rates exceed Muon Stopping Target Monitor capabilities | FY17-18 |  | Current Risk | M | N | M | M | N | M | J. Miller | 200000 |  | 25% | 50000 | 0 | 25% | 75% | 14.43% | 97.3603 | 100.6 | 104.6667 |  |  |  |  | 97 | [5 empty] | 97.3603
MUON-147 | 3836 | Threat | Degrader needed for calibration | FY16-FY19 |  | Current Risk | M | N | M | M | VL | M | G. Ginther | 250000 |  | 80% | 200000 | 0 | 25% | 75% | 14.43% | 167.5337 | 171.5833 | 176.6667 | 492.9481 |  |  | 168 | [5 empty] | up from 143 | 167.5337
MUON-207 | 6045 | Threat | Inner Proton Absorber cannot be effectively realized in polymer | FY18 |  | Current Risk | L | VL | L | L | M |  | Hank Glass | 300000 | 30 | 15% | 45000 | 4.5 | 10% | 25% | 4.33% | 56.3122 | 57.77 | 59.6 | [5 empty] | 56 |  |  |  | addition | 56.3122
PM-007 | 3363 | Threat | CD-4 float inadequate. | FY20 |  | Current Risk | L | M | L | N | N | M | Ron Ray | 2545787 | 500 | 10% | 0 | 50 | 10% | 25% | 4.33% | 435.4327 | 447.8039 | 463.3332 | [7 empty] | 435 |  |  | 435.4327
PM-008 | 3364 | Threat | Additional resources required in Project Office to manage Project. | FY16-FY20 |  | Current Risk | L | N | H | N | N | M | Ron Ray | 500000 |  | 25% | 125000 | 0 | 10% | 25% | 4.33% | 110.5203 | 112.95 | 116 |  |  |  | 111 | [6 empty] | 110.5203
PM-009 | 3365 | Opportunity | Fewer Resources than anticipated required in Project Office to manage Project. | FY16-FY20 |  | Current Risk | L | N | M | N | N | M | Ron Ray | -500000 |  | 10% | -50000 | 0 | 10% | 25% | 4.33% | -85.5203 | -87.95 | -91 |  |  |  | -86 | [6 empty] | -85.5203
PM-010 | 3366 | Threat | Increase in Fermilab overhead rates | FY16-FY20 |  | Current Risk | M | N | VH | N | N | H | Ron Ray | 1500000 | 0 | 50% | 750000 | 0 | 25% | 75% | 14.43% | 855.2025 | 879.5 | 910 |  |  |  | 855 | [6 empty] | 855.2025
PM-048 | 3350 | Threat | Significant injury or death associated with Mu2e construction/assembly. | FY15-FY20 | 25000 | Current Risk | VL | H | VH | N | VH | M | R. Ray | 1000000 | 260 | 1% | 10000 | 2.6 | 0% | 10% | 2.887% | 50.6937 | 53.9333 | 58 |  |  | 51 | [7 empty] | 50.6937
PM-142 | 3757 | Threat | Currency fluctuations on foreign procurements | FY17-FY18 |  | Current Risk | L | N | VL | N | N | L | Ron Ray | 100000 | 0 | 10% | 10000 | 0 | 10% | 25% | 4.33% | 17.1041 | 17.59 | 18.2 |  |  |  |  | 17 | [5 empty] | 17.1041
PM-153 | 3844 | Opportunity | Commodity prices decrease | FY16-FY19 |  | Current Risk | L | N | VH | N | N | H | Ron Ray | -1173000 |  | 10% | -117300 |  | 10% | 25% | 4.33% | -200.6305 | -206.3307 | -213.486 |  |  |  | -201 | [6 empty] | -200.6305
PM-154 | 3845 | Threat | Commodity prices escalate faster than inflation | FY16-FY19 |  | Current Risk | L | N | VH | N | N | H | Ron Ray | 1173000 |  | 20% | 234600 |  | 10% | 25% | 4.33% | 239.7305 | 245.4307 | 252.586 | 1422.5329 |  |  | 240 | [6 empty] | 239.7305
SOL-070 | 3368 | Threat | Interface problems with the solenoids. | FY17-FY20 |  | Current Risk | L | H | VH | N | N | H | M. Lamm | 1000000 | 60 | 20% | 200000 | 12 | 10% | 25% | 4.33% | 204.3738 | 209.2333 | 215.3333 |  |  |  |  | 204 | [5 empty] | 204.3738
SOL-137 | 3373 | Threat | Solenoid fringe field impacts performance of nearby equipment | FY17-FY20 | 100000 | Current Risk | L | N | L | L | M | M | K. Krempetz | 100000 |  | 20% | 20000 | 0 | 10% | 25% | 4.33% | 20.4374 | 20.9233 | 21.5333 |  |  |  |  | 20 | [5 empty] | 20.4374
SOL-148 | 3837 | Threat | Production Solenoid must be installed through PS hatch using a large rented crane. | FY19-20 |  | Current Risk | M | N | H | N | N | H | M. Lamm | 300000 |  | 50% | 150000 | 0 | 25% | 75% | 14.43% | 171.0405 | 175.9 | 182 | [6 empty] | 171 |  |  |  | 171.0405
SOL-155 | [26 empty] | -1972 | [5 empty] | amount we credit
SOL-171 | 4556 | Threat | Production cable does not meet specification | FY16 | 700000 | Current Risk | VL | H | N | N | L | L | M.Lamm | 2000000 | 250 | 10% | 200000 | 25 | 0% | 10% | 2.887% | 161.3873 | 167.8667 | 176 |  |  |  | 161 | [6 empty] | 161.3873
SOL-172 | 4557 | Threat | DS Magnet fabrication failure due to process or component | FY18-19 | 700000 | Current Risk | VL | H | VH | M | L | M | M.Lamm | 4000000 | 250 | 10% | 400000 | 25 | 0% | 10% | 2.887% | 322.7747 | 335.7333 | 352 | [5 empty] | 323 |  |  | moved to 2018 from 2017 |  | 322.7747
SOL-173 | 4558 | Threat | Completed cryostated magnet does not pass acceptance tests at vendor | FY18-19 |  | Current Risk | VL | M | N | N | L | L | M.Lamm | 1000000 | 125 | 10% | 100000 | 12.5 | 0% | 10% | 2.887% | 80.6937 | 83.9333 | 88 | [5 empty] | 81 |  |  |  |  | 80.6937
SOL-174 | 4559 | Threat | Vendor delays not caused by FNAL | FY18-19 |  | Current Risk | L | L | N | N | N | L | M.Lamm | 520000 | 65 | 25% | 130000 | 16.25 | 10% | 25% | 4.33% | 114.9411 | 117.468 | 120.64 | [5 empty] | 115 |  |  |  |  | 114.9411
SOL-175 | 4560 | Threat | Magnet is damaged during shipping and handling | FY19 |  | Current Risk | VL | H | N | N | N | L | M.Lamm | 2000000 | 250 | 5% | 100000 | 12.5 | 0% | 10% | 2.887% | 128.054 | 134.5333 | 142.6667 | [6 empty] | 128 |  |  |  | 128.054
SOL-176 | 4561 | Threat | Operational failure during final acceptance tests at FNAL. | FY20 |  | Current Risk | VL | VH | VH | N | L | M | M.Lamm | 4500000 | 500 | 10% | 450000 | 50 | 0% | 10% | 2.887% | 363.1215 | 377.7 | 396 | [7 empty] | 363 |  |  | 363.1215
SOL-177 | 4562 | Threat | DS Magnet fabrication failure due to process or component | FY18-19 | 200000 | Current Risk | VL | M | H | N | L | L | M.Lamm | 1500000 | 125 | 10% | 150000 | 12.5 | 0% | 10% | 2.887% | 121.0405 | 125.9 | 132 | [5 empty] | 121 |  |  |  |  | 121.0405
SOL-178 | 4563 | Threat | Completed cryostated magnet does not pass acceptance tests at vendor | FY20 |  | Current Risk | VL | M | N | N | L | L | M.Lamm | 1000000 | 125 | 10% | 100000 | 12.5 | 0% | 10% | 2.887% | 80.6937 | 83.9333 | 88 | [7 empty] | 81 |  |  | 80.6937
SOL-179 | 4564 | Threat | Vendor delays not caused by FNAL | FY18-19 |  | Current Risk | L | L | N | N | N | L | M.Lamm | 520000 | 65 | 25% | 130000 | 16.25 | 10% | 25% | 4.33% | 114.9411 | 117.468 | 120.64 | [5 empty] | 115 |  |  |  |  | 114.9411
SOL-180 | 4565 | Threat | Magnet is damaged during shipping and handling | FY20 |  | Current Risk | VL | H | N | N | N | L | M.Lamm | 2000000 | 250 | 5% | 100000 | 12.5 | 0% | 10% | 2.887% | 128.054 | 134.5333 | 142.6667 | [7 empty] | 128 |  |  | 128.054
SOL-181 | 4566 | Threat | Operational failure during final acceptance tests at FNAL. | FY20 |  | Current Risk | VL | VH | VH | N | N | M | M.Lamm | 4500000 | 500 | 5% | 225000 | 25 | 0% | 10% | 2.887% | 288.1215 | 302.7 | 321 | [7 empty] | 288 |  |  | 288.1215
SOL-182 | 4567 | Threat | Delay in FNAL supplied processes or components | FY17-19 |  | Current Risk | L | L | N | N | N | L | M.Lamm | 520000 | 65 | 15% | 78000 | 9.75 | 10% | 25% | 4.33% | 97.6077 | 100.1347 | 103.3067 |  |  |  |  | 98 | [5 empty] | 97.6077
SOL-183 | 4568 | Threat | TS Magnet fabrication failure due supplied process or component | FY18-19 | 200000 | Current Risk | M | L | M | N | N | H | M.Lamm | 620000 | 65 | 40% | 248000 | 26 | 25% | 75% | 14.43% | 332.817 | 342.86 | 355.4667 | [5 empty] | 333 |  |  | was in 2016 |  | 332.817
SOL-184 | 4569 | Threat | Vendor delays not caused by FNAL | FY18-19 |  | Current Risk | L | L | N | N | N | L | M.Lamm | 350000 | 42 | 25% | 87500 | 10.5 | 10% | 25% | 4.33% | 77.3642 | 79.065 | 81.2 | [5 empty] | 77 |  |  |  |  | 77.3642
SOL-185 | 4570 | Threat | Damage to the coil module during shipping and handling | FY18-19 |  | Current Risk | VL | L | M | N | N | L | M.Lamm | 770000 | 65 | 5% | 38500 | 3.25 | 0% | 10% | 2.887% | 49.3008 | 51.7953 | 54.9267 | [5 empty] | 49 |  |  |  |  | 49.3008
SOL-186 | 4571 | Threat | Failure of design or fabrication of Fermilab designed cryogenic system | FY18-19 |  | Current Risk | VL | H | H | N | L | L | M.Lamm | 2500000 | 250 | 10% | 250000 | 25 | 0% | 10% | 2.887% | 201.7342 | 209.8333 | 220 | [5 empty] | 202 |  |  |  |  | 201.7342
SOL-187 | 4572 | Threat | Integrated module out of tolerances | FY18-19 |  | Current Risk | VL | L | N | N | L | L | M.Lamm | 520000 | 65 | 10% | 52000 | 6.5 | 0% | 10% | 2.887% | 41.9607 | 43.6453 | 45.76 | [5 empty] | 42 |  |  |  |  | 41.9607
SOL-188 | 4573 | Threat | Final assembled magnet does not perform as designed | FY20 |  | Current Risk | VL | H | H | N | L | L | M.Lamm | 2500000 | 250 | 10% | 250000 | 25 | 0% | 10% | 2.887% | 201.7342 | 209.8333 | 220 | [7 empty] | 202 |  |  | 201.7342
SOL-189 | 4574 | Threat | Fermilab space or personnel resources not available when needed for final assembly | FY16-19 |  | Current Risk | L | M | VH | N | N | M | M.Lamm | 2000000 | 125 | 25% | 500000 | 31.25 | 10% | 25% | 4.33% | 442.081 | 451.8 | 464 |  |  |  | 442 |  |  |  |  | up from 128 |  | 442.081
SOL-190 | 4575 | Threat | Building is Not Ready-Unable to start infrastructure installation | FY16 |  | Current Risk | L | M | N | N | N | M | M.Lamm | 1000000 | 125 | 25% | 250000 | 31.25 | 10% | 25% | 4.33% | 221.0405 | 225.9 | 232 |  |  |  | 221 | [6 empty] | 221.0405
SOL-191 | 4576 | Threat | Cryogenics, Power, or Vacuum Infrastructure Not available for commissioning | FY18-19 |  | Current Risk | L | M | N | N | N | M | M.Lamm | 1000000 | 125 | 25% | 250000 | 31.25 | 10% | 25% | 4.33% | 221.0405 | 225.9 | 232 | [5 empty] | 221 |  |  |  |  | 221.0405
SOL-192 | 4577 | Threat | Manpower not available to start commissioning | FY19-20 |  | Current Risk | L | M | N | N | N | M | M.Lamm | 500000 | 60 | 10% | 50000 | 6 | 10% | 25% | 4.33% | 85.5203 | 87.95 | 91 | [6 empty] | 86 |  |  |  | 85.5203
SOL-193 | 4578 | Threat | Support Frames require major rework | FY18-19 |  | Current Risk | VL | M | L | N | N | L | M.Lamm | 1100000 | 125 | 10% | 110000 | 12.5 | 0% | 10% | 2.887% | 88.763 | 92.3267 | 96.8 | [5 empty] | 89 |  |  |  |  | 88.763
SOL-194 | 4579 | Threat | Installation Tooling not adequate | FY18-19 |  | Current Risk | L | L | L | N | N | L | M.Lamm | 620000 | 65 | 15% | 93000 | 9.75 | 10% | 25% | 4.33% | 116.3784 | 119.3913 | 123.1733 | [5 empty] | 116 |  |  |  |  | 116.3784
SOL-195 | 4580 | Threat | Vendor delays during Feedbox fabrication | FY17-19 |  | Current Risk | L | L | N | N | N | L | M.Lamm | 520000 | 65 | 25% | 130000 | 16.25 | 10% | 25% | 4.33% | 114.9411 | 117.468 | 120.64 |  |  |  |  | 115 | [5 empty] | 114.9411
SOL-196 | 4581 | Threat | HTS leads damage during assembly | FY17-19 |  | Current Risk | L | L | VL | N | N | L | M.Lamm | 570000 | 65 | 15% | 85500 | 9.75 | 10% | 25% | 4.33% | 106.9931 | 109.763 | 113.24 |  |  |  |  | 107 | [5 empty] | 106.9931
SOL-197 | 4582 | Threat | Cold leak in Feedbox | FY19 |  | Current Risk | L | M | N | N | VL | M | M.Lamm | 1000000 | 125 | 25% | 250000 | 31.25 | 10% | 25% | 4.33% | 221.0405 | 225.9 | 232 | [6 empty] | 221 |  |  |  | 221.0405
SOL-198 | 4583 | Threat | Cryo, vacuum or electrical problems in cryo lines | FY18-19 |  | Current Risk | L | L | L | N | VL | L | M.Lamm | 620000 | 65 | 25% | 155000 | 16.25 | 10% | 25% | 4.33% | 137.0451 | 140.058 | 143.84 | [5 empty] | 137 |  |  |  |  | 137.0451
SOL-199 | 4584 | Threat | Unanticipated building interferences with cryoline | FY18 |  | Current Risk | L | L | L | N | N | L | M.Lamm | 620000 | 65 | 25% | 155000 | 16.25 | 10% | 25% | 4.33% | 137.0451 | 140.058 | 143.84 | [5 empty] | 137 |  |  |  |  | 137.0451
SOL-205 | [26 empty] | -17 | [5 empty] | retired
TRACK-091 | 3382 | Threat | Simulations indicate that tracker occupancy higher than expected | FY15-FY16 |  | Current Risk | VL | L | L | N | N | L | D.Brown | 50000 | 30 | 5% | 2500 | 1.5 | 0% | 10% | 2.887% | 3.2014 | 3.3633 | 3.5667 |  |  | 3 | [7 empty] | 3.2014
TRACK-092 | 3383 | Threat | Need to switch straw manufacturer | FY16 |  | Current Risk | L | H | VL | N | N | M | A. Mukherjee | 100000 | 250 | 5% | 5000 | 12.5 | 10% | 25% | 4.33% | 15.4374 | 15.9233 | 16.5333 |  |  |  | 15 |  |  |  |  | money was dedicated in 2015 |  | 15.4374
TRACK-096 | 3385 | Threat | Detector support structure not sufficiently rigid or stable | FY15-FY17 | 62000 | Current Risk | L | N | M | M | N | M | A. Mukherjee | 100000 |  | 25% | 25000 | 0 | 10% | 25% | 4.33% | 22.1041 | 22.59 | 23.2 |  |  | 22 | [7 empty] | 22.1041
TRACK-104 | 3390 | Threat | Gain loss in tracker. | FY15-FY17 | 5000 | Current Risk | L | M | H | L | N | M | A. Mukherjee | 500000 | 40 | 10% | 50000 | 4 | 10% | 25% | 4.33% | 85.5203 | 87.95 | 91 |  |  | 86 | [7 empty] | 85.5203
TRACK-139 | [26 empty] | -9 | [5 empty] | retired risk
TRACK-166 | 4445 | Threat | High crosstalk | FY15-FY16 | 5000 | Current Risk | M | N | L | M | N | M | A. Mukherjee | 50000 | 0 | 5% | 2500 | 0 | 25% | 75% | 14.43% | 21.0068 | 21.8167 | 22.8333 |  |  | 21 | [5 empty] | was $24 |  | 21.0068
TRACK-167 | 4446 | Opportunity | Drop in price of COTS components | FY17-18 |  | Current Risk | H | N | L | N | N | M | A. Mukherjee | -50000 | 0 | 25% | -12500 | 0 | 75% | 90% | 4.33% | -32.7187 | -32.9617 | -33.2667 |  |  |  |  | -33 |  |  |  | was part of 2016 originally |  | -32.7187
TRACK-168 | 4447 | Opportunity | Drop in price of 3D printing | FY15-FY16 |  | Current Risk | M | N | M | N | N | M | A. Mukherjee | -100000 | 0 | 50% | -50000 | 0 | 25% | 75% | 14.43% | -57.0135 | -58.6333 | -60.6667 |  |  | -57 | [7 empty] | -57.0135
TRACK-169 | 4444 | Threat | Background levels >4x expectation necessitate additional Tracker stations | FY15-FY17 |  | Current Risk | M | N | VH | M | N | H | A. Mukherjee | 1000000 | 0 | 25% | 250000 | 0 | 25% | 75% | 14.43% | 486.8017 | 503 | 523.3333 | 544.3393 |  | 487 | [7 empty] | 486.8017
TRIG-128 | 3393 | Threat | Insufficient manpower for DAQ software. | FY17-FY20 |  | Current Risk | M | N | H | N | N | H | Ryan Rivera | 500000 |  | 25% | 125000 | 0 | 25% | 75% | 14.43% | 243.4008 | 251.5 | 261.6667 |  |  |  |  | 243 | [5 empty] | 243.4008
TRIG-130 | 3394 | Threat | Insufficient DAQ online processing. | FY18-FY19 |  | Current Risk | M | N | L | N | N | L | Ryan Rivera | 70000 |  | 50% | 35000 | 0 | 25% | 75% | 14.43% | 39.9094 | 41.0433 | 42.4667 | [5 empty] | 40 |  |  | was $35 originally |  | 39.9094
TRIG-131 | 3395 | Threat | Higher than expected data rates to the DAQ. | FY19 |  | Current Risk | M | N | VL | N | N | L | Ryan Rivera | 100000 |  | 50% | 50000 | 0 | 25% | 75% | 14.43% | 57.0135 | 58.6333 | 60.6667 | [6 empty] | 57 |  | was originally $6 and part of 2016 |  | 57.0135
TRIG-132 | 3396 | Opportunity | Use of surplus equipment for DAQ. | FY17 |  | Current Risk | M | N | L | N | N | L | Ryan Rivera | -30000 |  | 50% | -15000 | 0 | 25% | 75% | 14.43% | -17.1041 | -17.59 | -18.2 |  |  |  |  | -17 | [5 empty] | -17.1041
TRIG-134 | 3397 | Opportunity | Lower cost commercial PCIe card for DTC. | FY17 |  | Current Risk | L | N | L | N | N | L | Ryan Rivera | -20000 |  | 10% | -2000 | 0 | 10% | 25% | 4.33% | -3.4208 | -3.518 | -3.64 |  |  |  |  | -3 |  |  |  | was originally $10 savings in 2015 |  | -3.4208
TRIG-135 | 3398 | Opportunity | Slow Controls development in common with other experiments. | FY15-FY19 |  | Current Risk | L | N | L | N | N | L | Ryan Rivera | -40000 |  | 30% | -12000 | 0 | 10% | 25% | 4.33% | -9.5083 | -9.7027 | -9.9467 |  |  | -10 | [5 empty] | was originally $7 savings in 2015 |  | -9.5083
TRIG-136 | 3399 | Opportunity | Efficient Calorimeter Trigger reduces online processing requirements. | FY15-FY19 |  | Current Risk | L | N | L | N | N | L | Ryan Rivera | -40000 |  | 10% | -4000 | 0 | 10% | 25% | 4.33% | -6.8416 | -7.036 | -7.28 | 303.449 |  | -7 | [7 empty] | -6.8416
VETO-114 | 3400 | Threat | Simulations indicate that neutron flux at the CRV is too high. | FY17-FY20 | 2000000 | Current Risk | L | N | H | H | N | M | C. Dukes | 2000000 | 0 | 10% | 200000 | 0 | 10% | 25% | 4.33% | 342.081 | 351.8 | 364 |  |  |  |  | 342 | [5 empty] | 342.081
VETO-122 | 3402 | Threat | Need to use inferior fibers | FY-15-FY17 |  | Current Risk | L | N | L | VL | N | M | C. Dukes | 50000 |  | 20% | 10000 | 0 | 10% | 25% | 4.33% | 10.2187 | 10.4617 | 10.7667 |  |  | 10 | [7 empty] | 10.2187
VETO-156 | 4199 | Threat | Can’t control size and shape of fiber holes in extruded scintillator | FY17-FY18 |  | Current Risk | L | H | H | M | N | M | A. Pla | 500000 | 200 | 20% | 100000 | 40 | 10% | 25% | 4.33% | 102.1869 | 104.6167 | 107.6667 |  |  |  |  | 102 | [5 empty] | 102.1869
VETO-158 | 4257 | Threat | Custom SiPM size is needed | FY17 |  | Current Risk | L | N | VL | N | N | L | C. Dukes | 50000 | 0 | 20% | 10000 | 0 | 10% | 25% | 4.33% | 10.2187 | 10.4617 | 10.7667 |  |  |  |  | 10 | [5 empty] | 10.2187
VETO-159 | 4260 | Threat | Photoelectron yield does not meet requirements. | FY16 |  | Current Risk | L | N | L | N | N | L | C. Dukes | 150000 | 0 | 20% | 30000 | 0 | 10% | 25% | 4.33% | 30.6561 | 31.385 | 32.3 |  |  |  | 31 |  |  |  |  | accounted for in 2015 originally |  | 30.6561
VETO-161 | 4262 | Opportunity | UVa on-campus space can be found for module factory. | FY17-18 |  | Current Risk | M | N | L | N | N | L | C. Dukes | -100000 | 0 | 50% | -50000 | 0 | 25% | 75% | 14.43% | -57.0135 | -58.6333 | -60.6667 |  |  |  |  | -57 | [5 empty] | -57.0135
VETO-162 | 4259 | Opportunity | Photoelectron yield exceeds requirements. | FY16 |  | Current Risk | M | N | L | N | N | L | C. Dukes | -100000 | 0 | 50% | -50000 | 0 | 25% | 75% | 14.43% | -57.0135 | -58.6333 | -60.6667 |  |  |  | -57 |  |  |  |  | accounted for in 2015 originally |  | -57.0135
VETO-163 | 4263 | Opportunity | Wider counters can be extruded that meet specifications. | FY16 |  | Current Risk | M | N | L | N | N | L | C. Dukes | -200000 | 0 | 50% | -100000 | 0 | 25% | 75% | 14.43% | -114.027 | -117.2667 | -121.3333 |  |  |  | -114 |  |  |  |  | accounted for in 2015 originally |  | -114.027
VETO-164 | 4258 | Threat | More CRV coverage is needed. | FY17-FY20 |  | Current Risk | H | N | VL | N | N | L | C. Dukes | 60000 | 0 | 80% | 48000 | 0 | 67.5% | 92.5% | 7.217% | 50.1041 | 50.59 | 51.2 | 318.4114 |  |  |  | 50 | [5 empty] | 50.1041
[5 empty] | 4342000 | [8 empty] | 57474787 | 5847 |  | 8073150 | 725.85 |  | 0.75 |  | 8907.5152 | 9187.2755 | 9538.4512 | 3657.8088 |  | -1248 | 2027 | 1327 | 2305 | 891 | 1497 | 6799 |  | 8907.5152
|  |  |  | Retired Mitigation | 40000 | [29 empty] | 6801.5152
|  |  |  | Transferred Mitigation | 3685000
|  |  |  | Deleted Mitigation | 470000
|  |  |  | Total Mitigation Costs | 8537000
Note on D84: A custom SiPM size will be needed, most likely due to the need to keep the dark-noise rate, which scales are SiPM active area, within specifications.
Note on D85: The photoelectron yield is less than expected. This would require a larger diameter fiber (and larger associated SiPM only in the case that a custom SiPM size is required).
Note on D86: If space can be found to fabricate the modules at on-campus facilities at UVA, this eliminates the need to rent space for the module fabrication factory. The search for suitable sites is being actively pursued by UVA collaborators.
Note on D87: The photoelectron yield is greater than expected due to the availability of SiPMs with higher PDEs. This would allow a smaller diameter fiber and perhaps a smaller SiPM to be used.
Note on D88: The gaps between counters are too large to allow the efficiency requirement to be met. The easiest way to mitigate this would be to fabricate wider counters, 6 cm to 7 cm, which allow wider gaps without adversely affecting the efficiency requirement. This would require minor redesigns to various components of the CRV, including items such as counter motherboards, modules, and the support structure. The increased cost would be offset by the smaller number of fibers, SiPMs, and front-end boards.
Note on D89: More coverage will be needed with CRV-D. A very recent simulation targeting cosmic-ray muons entering in the downstream sector show that three events over the course of the entire running period enter just below the module coverage. All are vetoed by the calorimeter. Simulating with more statistics may show that some events are not vetoed by the calorimeter or CRV, and hence more coverage is needed.

## Retired risks
[19 empty] | y | Include Opportunities?
Risk | [6 empty] | Post-mitigation | [5 empty] | Details | [5 empty] | Risk Contingency | [6 empty] | NOTES:
ID | DocDb # | Type | Title | Date of Risk | Mitigation Cost (included in plan) | Category | Probability | Schedule-Delays Level 3 Milestone or Project Critical Path by X Days | Cost | Technical | ESH&Q | Score | Owner | Point estimate (cost k$) | Point Estimate (sched-days) | Point estimate (prob) | EXPECTATION VALUE IN k$ | EXPECTATION VALUE IN Days | Prob Range |  | Prob RMS | 80% CL | 85% CL | 90%CL
ACCEL-011 | 3328 | Threat | Inadequate AD Engineering Resources | FY12-FY14 |  |  | M | L | N | N | N | 24 | Ron Ray | 0 | 60 | 10% | 0 | 6 | -2.5% | 22.5% | 7.217% | 0 | 0 | 0
ACCEL-012 | 3329 | Threat | Mu2e beam comissioning delayed. |  |  | Transfer to operations | M | H | N | H | L | 24 | S. Werkema | 0 |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
ACCEL-014 | 3330 | Threat | Radiation damage to fiber optics communication lines | FY13-FY20 | 10000 |  | L | N | M | N | N | 10 | C. Johnstone, B. Drendel | 100000 |  | 50% | 50000 | 0 | 37.5% | 62.5% | 7.217% | 87.95 | 91 | 95.5
ACCEL-015 | 3331 | Threat | Injection damper required for Delivery Ring | FY16-FY19 |  |  | L | N | N | VH | N | 24 | J. Morgan | 185000 | 0 | 10% | 18500 | 0 | -2.5% | 22.5% | 7.217% | 32.5415 | 33.67 | 35.335
ACCEL-016 |  | Threat | Delivery Ring tunes cannot be measured to the required accuracy. |  |  |  | L | N | L | N | N | 3 | B. Drendel |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-017 | 3332 | Threat | Radiation levels outside of Mu2e facility too high. |  |  | Transfer to operations | L | N | N | VH | N | 24 | T. Leveling | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
ACCEL-020 | 3333 | Threat | Cannot use TLMs to control beam losses. | FY14-FY19 | 20000 |  | L | N | VH | N | N | 24 | T. Leveling | 2000000 |  | 10% | 200000 | 0 | -2.5% | 22.5% | 7.217% | 351.8 | 364 | 382
ACCEL-021 | 3334 | Opportunity | Availability of the shielding steel blocks on site |  |  | Realized | M | N | M | N | N | 10 | J.Annala | -134000 |  | 0% | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-022 | 3335 | Threat | Large beam loss from Resonant Extraction. | FY19-FY20 |  | Transfer to operations | M | N | N | H | N | 24 | v. Nagaslaev |  |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
ACCEL-023 |  | Threat | Resonant extraction leaves an inacceptably large fraction of the beam circulating in the Delivery Ring |  |  | Retired | L | N | N | M | N | 0 | V. Nagaslaev, J. Morgan |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-024 |  | Threat | Inability to locate and reuse all the necessary tooling and infrastracture hardware for the ES septum fabrication |  |  | Retired | M | N | M | N | N | 0 | v. Nagaslaev |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-025 |  | Threat | Capability to ramp Delivery Ring sextupoles required. |  |  | Retired | L | N | L | N | N | 0 | V. Nagaslaev |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-026 | 3336 | Threat | Cannot adequately maintain proton beam position and angle on production target. |  | Implementation of auto tune | Retired | M | N | N | H | L | 24 | C. Johnstone |  |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
ACCEL-027 |  | Threat | Inability to clear Delivery ring quads with extracted beam orbit |  |  | Retired | L | N | N | M | N | 0 | C. Johnstone, V. Nagaslaev |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-028 | 3337 | Opportunity | Assumed refurbishment of SQ magnets not required. |  |  | Realized | M | N | VL | N | N | 3 | J.Annala | 13000 |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-029 | 3338 | Threat | Need to build 6 CDA-like magnets from scratch |  |  | DELETED | M | N | VH | N | N | 0 | J.Annala | 0 |  | 0% | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-030 | 3339 | Opportunity | Reduced cost of 6-3-120 magnets preparation |  |  | Realized | L | N | L | N | N | 3 | J.Annala | 30000 |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-031 |  | Threat | Need to build 10 Q18 magnets |  |  | Retired | M | N | M | N | N | 0 | J.Annala |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-032 | 3340 | Opportunity | Reduced cost of Large aperture quads |  |  | Realized | L | N | L | N | N | 3 | J.Annala | 200000 |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-033 |  | Threat | Inability to stage magnets in the Accumulator enclosure during g-2 operation |  |  |  | VL | N | L | N | N | 1 | C. Johnstone |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-034 | 3341 | Threat | Unable to perform the orbit and optics control with proposed reduced number of position monitors |  |  | DELETED | L | N | H | M | N | 12 | C. Johnstone | 0 |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-035 | 3342 | Threat | Failure of extinction system to sufficiently eliminate out of time beam |  |  | Transfer to operations | L | N | N | VH | N | 40 | E. Prebys | 0 |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
ACCEL-036 | 3343 | Opportunity | No need in internal extinction collimation |  |  | Realized | M | N | M | N | N | 10 | E. Prebys | -1000000 |  | 50% | -500000 | 0 | 37.5% | 62.5% | 7.217% | -879.5 | -910 | -955
ACCEL-037 |  | Threat | Extinction monitor fails to perform to requirements. |  |  | Transfer to operations | VL | N | N | H | N | 4 | P. Kasper |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-038 | 3344 | Threat | Radiated target will not survive in the Beam. | FY14-FY20 |  |  | L | N | M | N | N | 6 | R. Coleman | 175000 |  | 10% | 17500 | 0 | -2.5% | 22.5% | 7.217% | 30.7825 | 31.85 | 33.425
ACCEL-041 |  | Threat | Heat and radiation shield insufficient to protect the Production Solenoid |  |  | Transfer to operations | L | N | N | L | N | 3 | R. Coleman |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-042 | 3345 | Threat | Mechanical design of the heat and radiation shield inadequate to sustain loads generated during Production and Transport Solenoid quenches. |  |  | Retired | VL | N | N | VH | N | 8 | R. Coleman, M. Lamm | 0 |  | 5% | 0 | 0 | -7.5% | 17.5% | 7.217% | 0 | 0 | 0
ACCEL-043 |  | Threat | Production solenoid quenching. |  |  | Retired | VL | N | N | VH | N | 0 | R. Coleman, M. Lamm |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-140 | 3346 | Threat | Proton beam not available for beam studies in FY2013 |  |  |  | L | N | N | M | N | 6 | S. Werkema | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
ACCEL-141 |  | Threat | Extraction Lambertson scope returns to Mu2e Scope |  |  | Retired | L | L | VH | VL | N | 0 | S. Werkema |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CAL-108 | 3347 | Threat | INFN cannot deliver full in-kind scope. |  |  |  | M | N | H | H | N | 24 | R. Ray | 1000000 |  | 50% | 500000 | 0 | 37.5% | 62.5% | 7.217% | 879.5 | 910 | 955
CAL-111 | 3348 | Threat | Pileup in the calorimeter |  |  | Transfer to operations | L | N | N | L | N | 6 | S. Miscetti | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
CAL-148 | ? | Threat | Cannot develop UV-extended solid state photodetector that is blind to longer wavelengths |  | 100000 |  | M | M | N | H | N |  | D. Hitlin
CAL-113 | 3349 | Threat | Radiation damage to calorimeter photosensors |  | 50000 | Transfer to operations | L | N | N | M | N | 6 | S. Miscetti | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
CONST-047 |  | Threat | Errors & omissions In design of conventional facilities by A&E firm. |  |  |  | L | N | L | N | N | 3 | T. Lackowski |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CONST-048 | 3350 | Threat | Significant injury or death associated with civil construction. | FY14-FY16 |  |  | VL | M | M | N | VH | 8 | T. Lackowski | 100000 |  | 5% | 5000 | 0 | -7.5% | 17.5% | 7.217% | 8.795 | 9.1 | 9.55
CONST-049 | 3351 | Opportunity | Conventionl construction bids are lower than estimated cost. | FY14 |  |  | M | N | M | N | N | 10 | T. Lackowski | -1200000 |  | 50% | -600000 | 0 | 37.5% | 62.5% | 7.217% | -1055.4 | -1092 | -1146
CONST-050 | 3352 | Threat | Conventionl construction bids exceed estimated cost. | FY14 |  |  | L | N | M | N | N | 6 | T. Lackowski | 1200000 |  | 10% | 120000 | 0 | -2.5% | 22.5% | 7.217% | 211.08 | 218.4 | 229.2
CONST-051 |  | Threat | Civil contractor cannot complete work satisfactorily or defaults on contract. |  |  |  | VL | N | L | N | N | 1 | T. Lackowski |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CONST-054 |  | Threat | Conventional Systems performance does not meet criteria |  |  |  | VL | N | H | M | N | 4 | T. Lackowski |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CONST-055 |  | Threat | Final design of conventional facilities delayed. |  |  | Retired | L | M | N | N | N | 0 | T. Lackowski |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CONST-058 |  | Threat | Unforeseen/undocumented subsurface conditions discovered during excavation for conventional construction. |  |  |  | VL | M | M | N | N | 2 | T. Lackowski |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CONST-059 |  | Threat | Disruptions To Fermilab utilities, facilities or operations |  |  | Retired | L | L | N | N | N | 0 | T. Lackowski |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CONST-063 |  | Threat | Storm Water Pollution |  |  | Retired | VL | N | N | N | N | 0 | T. Lackowski |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CONST-064 |  | Threat | Severe Weather impacts civil construction. |  |  |  | L | L | L | N | N | 3 | T. Lackowski |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CONST-065 | 3353 | Threat | Feeder 24 from MSS to F3 not adequate |  |  | Move to Muon Campus Scope | M | N | M | N | N | 10 | T. Lackowski | 0 |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
MUON-083 | 3354 | Threat | Significantly larger gas loads in warm bore of DS than anticipated. |  | 50000 | Transfer to operations | M | N | M | N | N | 10 | G. Ginther | 0 |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
MUON-084 | 3355 | Threat | Vacuum leak. |  |  | Transfer to operations | M | M | M | N | N | 10 | J. Brandt | 0 | 0 | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
MUON-085 | 3356 | Threat | Inadequate pumping speed to maintain required vacuum in PS. |  |  | Transfer to operations | M | N | M | N | N | 10 | J. Brandt | 0 |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
MUON-086 | 3357 | Threat | PS vacuum window failure. |  |  | Transfer to operations | VL | N | H | H | VH | 8 | J. Brandt | 0 |  | 5% | 0 | 0 | -7.5% | 17.5% | 7.217% | 0 | 0 | 0
MUON-088 | 3358 | Threat | Background from neutrons higher than anticipated inside detector Solenoid. |  | 20000 |  | M | N | H | N | N | 10 | R. Bossert | 1000000 |  | 50% | 500000 | 0 | 37.5% | 62.5% | 7.217% | 879.5 | 910 | 955
MUON-089 |  | Threat | RETIRED- Distortion of DS magnetic field. |  |  | Retired | L | N | M | N | N | 0 | R. Bossert |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
MUON-090 | 3359 | Threat | Detector components move after installation. |  | 200000 | Transfer to operations | L | N | N | M | N | 6 | R. Bossert | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
MUON-138 | 3360 | Threat | Detector installation takes longer than expected. |  |  |  | M | M | M | N | N | 10 | G. Ginther | 400000 | 0 | 50% | 200000 | 0 | 37.5% | 62.5% | 7.217% | 351.8 | 364 | 382
MUON-143 | ? | Threat | Background rates in Cosmic Ray Veto higher than anticipated |  | 3000000 | Transfer to operations | L | N | VH | M | M |  | G. Ginther |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
MUON-144 | ? | Threat | Damage to surrounding elements during installation | FY20-21 | 50K | Transfer to operations | VL | VH | VH | VH | VH |  | N. Andreev/R. Bossert |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
MUON-145 | ? | Threat | Shielding installation impacts beamline alignment |  | 30k | Transfer to operations | L | N | M | N | N |  | G. Ginther/K. Krempetz |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
MUON-146 | ? | Threat | Rates exceed Muon Stopping Target Monitor capabilities |  |  |  | L | N | M | M | N |  | J. Miller | 200000 |  | 17% | 34000 | 0 | 4.5% | 29.5% | 7.217% | 59.806 | 61.88 | 64.94
MUON-147 | ? | Threat | Degrader needed for calibration |  |  |  | M | N | M | M | VL |  | G. Ginther | 250000 |  | 50% | 125000 | 0 | 37.5% | 62.5% | 7.217% | 219.875 | 227.5 | 238.75
PM-001 |  | Threat | Project funds not available at the beginning of fiscal year. |  |  |  | M | L | N | N | N | 5 | Ron Ray |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
PM-002 | 3361 | Opportunity | DOE advances project funding profile, providing money sooner than anticipated. |  |  |  | M | M | N | N | N | 10 | Ron Ray | 0 |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
PM-003 |  | Threat | CD-3a funds not available as assumed. |  |  | Retired | M | H | N | N | N | 0 | Ron Ray |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
PM-004 |  | Threat | Project is not granted a Categorical Exclusion and has to write an Environmental Assessment (EA) |  |  | Retired | L | N | M | N | N | 0 | Ron Ray |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
PM-005 | 3362 | Threat | Construction funds not available as assumed. | FY14 |  |  | L | H | H | N | N | 12 | Ron Ray | 3000000 | 60 | 10% | 300000 | 6 | -2.5% | 22.5% | 7.217% | 527.7 | 546 | 573
PM-007 | 3363 | Threat | CD-4 float inadequate. |  |  |  | L | M | L | N | N | 6 | Ron Ray | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
PM-008 | 3364 | Threat | Additional resources required in Project Office to manage Project. |  |  |  | L | N | M | N | N | 6 | Ron Ray | 500000 |  | 10% | 50000 | 0 | -2.5% | 22.5% | 7.217% | 87.95 | 91 | 95.5
PM-009 | 3365 | Opportunity | Fewer Resources than anticipated required in Project Office to manage Project. |  |  |  | L | N | M | N | N | 6 | Ron Ray | -500000 |  | 10% | -50000 | 0 | -2.5% | 22.5% | 7.217% | -87.95 | -91 | -95.5
PM-010 | 3366 | Threat | Unexpected increase in Fermilab overhead rates |  |  |  | M | N | H | N | N | 24 | Ron Ray | 2000000 | 0 | 50% | 1000000 | 0 | 37.5% | 62.5% | 7.217% | 1759 | 1820 | 1910
PM-142 | 3757 | Threat | Currency fluctuations on foreign procurements |  |  |  | M | N | M | N | N | 12 | Ron Ray | 200000 | 0 | 50% | 100000 | 0 | 37.5% | 62.5% | 7.217% | 175.9 | 182 | 191
SOL-066 | 3367 | Threat | Critical path delayed due to solenoid schedule delay. | FY18-FY20 | 20000 |  | L | H | H | N | N | 24 | M. Lamm | 4000000 | 360 | 20% | 800000 | 72 | 7.5% | 32.5% | 7.217% | 1407.2 | 1456 | 1528
SOL-067 |  | Threat | Too Few bidders on DS/PS design and construction. |  |  |  | VL | H | H | N | N | 4 | M. Lamm |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
SOL-068 |  | Threat | Conductor for Mu2e PS and DS solenoids does not have a market in industry. There may not be a sufficient business interest to invest in the tooling etc. to make this conductor |  |  | Retired | L | H | H | N | N | 0 | M. Lamm |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
SOL-070 | 3368 | Threat | Interface problems with the solenoids. | FY14-FY19 |  |  | L | H | H | N | N | 24 | M. Lamm | 3000000 | 360 | 15% | 450000 | 54 | 2.5% | 27.5% | 7.217% | 791.55 | 819 | 859.5
SOL-071 |  | Threat | Tevatron HTS leads cannot be adapted to mu2e PS. |  |  | Retired | M | N | L | N | N | 0 | M. Lamm |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
SOL-072 | 3369 | Threat | Tevatron HTS leads do not perform to Mu2e specifications. | FY13-FY15 | 20000 |  | L | N | M | N | N | 24 | M. Lamm | 200000 | 0 | 20% | 40000 | 0 | 7.5% | 32.5% | 7.217% | 70.36 | 72.8 | 76.4
SOL-074 | 3370 | Threat | Field mapping unit does not perform to specification |  |  | Transfer to operations | M | N | N | M | N | 10 | M. Lamm | 0 |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
SOL-077 |  | Threat | Thermal Siphon approach to cooling in PS does not work properly |  |  | Transfer to operations | VL | N | N | H | N | 4 | M. Lamm |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
SOL-078 | 3371 | Threat | Minimal approach to TS mapping proves to be inadequate with poor transmission of muon beam to stopping target. |  | 200000 | Operations | M | N | N | M | N | 10 | M. Lamm | 0 |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
SOL-080 | 3372 | Threat | Insufficient testing of DS and/or PS at Vendor | FY18-FY20 | 50000 |  | L | H | H | N | N | 12 | M. Lamm | 3000000 | 360 | 15% | 450000 | 54 | 2.5% | 27.5% | 7.217% | 791.55 | 819 | 859.5
SOL-137 | 3373 | Threat | Solenoid fringe field impacts performance of nearby equipment | FY17-FY20 | 100000 |  | L | N | L | L | VL | 6 | K. Krempetz | 75000 |  | 10% | 7500 | 0 | -2.5% | 22.5% | 7.217% | 13.1925 | 13.65 | 14.325
SOL-148 | ? | Threat | Production Solenoid must be installed through PS hatch using a large rented crane. | FY18-19 |  |  | M | N | H | N | N |  | T. Page | 300000 |  | 50% | 150000 | 0 | 37.5% | 62.5% | 7.217% | 263.85 | 273 | 286.5
TRACK-091 | 3382 | Threat | Simulations indicate that tracker occupancy higher than expected |  |  | Transfer to operations | L | N | N | H | N | 12 | D.Brown | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
TRACK-093 |  | Threat | Straw leak rate too high. |  |  |  | VL | H | M | H | N | 4 | A. Mukherjee, G. Ginther |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-094 |  | Threat | Change in cost of straw material |  |  |  | VL | N | L | N | N | 1 | A. Mukherjee |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-095 | 3384 | Opportunity | Change in cost of straw material |  |  | DELETED | M | N | M | N | N | 10 | A. Mukherjee | -175000 |  | 50% | -87500 | 0 | 37.5% | 62.5% | 7.217% | -153.9125 | -159.25 | -167.125
TRACK-096 | 3385 | Threat | Detector support structure not sufficiently rigid or stable |  |  | Transfer to operations | VL | L | N | M | N | 6 | A. Mukherjee | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
TRACK-097 | 3386 | Threat | Catastrophic mechanical failure of Tracker. |  |  |  | VL | VH | VH | VH | N | 8 | A. Mukherjee | 4000000 | 400 | 1% | 40000 | 4 | -11.5% | 13.5% | 7.217% | 70.36 | 72.8 | 76.4
TRACK-098 | 3387 | Opportunity | 2nd prototype ASIC run not needed |  | Savings is captured in TRACK-099 | DELETED | L | M | M | N | N | 6 | Y. Kolomensky | -175000 |  | 10% | -17500 | 0 | -2.5% | 22.5% | 7.217% | -30.7825 | -31.85 | -33.425
TRACK-099 | 3388 | Opportunity | Tracker readout can be fully implemented in commercial off-the-shelf parts. |  |  | Realized | L | M | L | N | N | 6 | Y. Kolomensky | -300000 |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-100 |  | Threat | Localized tracker electronics failure |  |  |  | L | N | N | L | N | 3 | Y. Kolomensky |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-101 |  | Threat | Excessive heat load from inaccessible tracker electronics inside DS vacuum. |  |  |  | VL | N | L | M | N | 2 | A. Mukherjee |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-102 | 3389 | Threat | Failure in a single straw tube prevents operating a large region of the tracker |  | 100000 | Move to Operations | L | N | N | H | N | 12 | A. Mukherjee | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
TRACK-103 |  | Threat | Widespread tracker electronics failure |  |  |  | VL | N | N | M | N | 2 | Y. Kolomensky |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-104 | 3390 | Threat | Gain loss in tracker. |  | 5000 | Move to Operations | L | N | N | H | N | 12 | A. Mukherjee | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
TRACK-105 |  | Threat | Tracker breakdown due to detector aging |  |  | Retired | N | N | N | M | N | 0 | A. Mukherjee |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-106 | 3391 | Threat | High rate variations are seen by the tracker from pulse-to-pulse. |  | 5000 | Move to Operations | VL | N | N | L | N | 6 | A. Mukherjee | 0 |  | 83% | 0 | 0 | 70.5% | 95.5% | 7.217% | 0 | 0 | 0
TRACK-107 |  | Threat | Catastrophic Tracker high voltage failure |  |  | Retired | L | N | N | N | N | 0 | A. Mukherjee |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-139 | 3392 | Threat | Mylar creep limits tracker lifetime |  | 5000 |  | L | N | H | H | N | 24 | A. Mukherjee | 390000 | 100 | 10% | 39000 | 10 | -2.5% | 22.5% | 7.217% | 68.601 | 70.98 | 74.49
TRIG-128 | 3393 | Threat | Insufficient manpower for DAQ software. | FY14-FY19 |  |  | M | N | M | N | N | 14 | M. Bowden | 500000 |  | 50% | 250000 | 0 | 37.5% | 62.5% | 7.217% | 439.75 | 455 | 477.5
TRIG-130 | 3394 | Threat | Insufficient DAQ online processing. | FY14-FY19 |  |  | L | N | L | N | N | 6 | M. Bowden | 75000 |  | 20% | 15000 | 0 | 7.5% | 32.5% | 7.217% | 26.385 | 27.3 | 28.65
TRIG-131 | 3395 | Threat | Higher than expected data rates to the DAQ. | FY14-FY19 |  |  | L | N | M | M | N | 6 | M. Bowden | 130000 |  | 10% | 13000 | 0 | -2.5% | 22.5% | 7.217% | 22.867 | 23.66 | 24.83
TRIG-132 | 3396 | Opportunity | Use of surplus equipment. | FY14-FY19 |  |  | H | N | L | N | N | 6 | M. Bowden | -30000 |  | 50% | -15000 | 0 | 37.5% | 62.5% | 7.217% | -26.385 | -27.3 | -28.65
TRIG-134 | 3397 | Opportunity | Lower cost commercial PCIe card for DTC. | FY14-FY19 |  |  | M | N | L | N | N | 6 | M. Bowden | -20000 |  | 25% | -5000 | 0 | 12.5% | 37.5% | 7.217% | -8.795 | -9.1 | -9.55
TRIG-135 | 3398 | Opportunity | Slow Controls development in common with other experiments. | FY14-FY19 |  |  | L | N | L | N | N | 3 | M. Bowden | -40000 |  | 10% | -4000 | 0 | -2.5% | 22.5% | 7.217% | -7.036 | -7.28 | -7.64
TRIG-136 | 3399 | Opportunity | Efficient Calorimeter Trigger reduces online processing requirements. | FY14-FY19 |  |  | L | N | M | N | N | 6 | M. Bowden | -40000 |  | 10% | -4000 | 0 | -2.5% | 22.5% | 7.217% | -7.036 | -7.28 | -7.64
VETO-114 | 3400 | Threat | Simulations indicate that neutron flux at the CRV is too high. | FY12-FY20 | 2000000 |  | L | N | H | H | N | 24 | C. Dukes | 0 | 0 | 10% | 0 | 0 | -2.5% | 22.5% | 7.217% | 0 | 0 | 0
VETO-115 |  | Threat | RETIRE-Cosmic ray background estimation incomplete by CD2. |  |  | Retired | L | N | M | N | N | 0 | C. Dukes |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
VETO-117 |  | Threat | Additional coverage is needed for Cosmic Ray Veto |  |  |  | L | N | L | N | N | 3 | C. Dukes |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
VETO-118 | 3401 | Threat | Simulations indicate that scintillator-based Cosmic Ray Veto does not have required efficiency. |  |  | Retired | L | N | M | H | N | 12 | C. Dukes | 0 | 0 | 0% | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
VETO-119 |  | Threat | Assembly room at Virginia is inadequate for CRV module construction. |  |  |  | L | N | L | N | N | 3 | C. Group |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
VETO-120 |  | Threat | RETIRE-Cosmic ray test stand needs to be fabricated |  |  | Retired | L | N | L | N | N | 0 | C. Group |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
VETO-121 |  | Threat | RETIRE-Existing flycutter cannot be obtained |  |  | Retired | L | N | L | N | N | 0 | C. Group |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
VETO-122 | 3402 | Threat | Need to use inferior fibers | FY15 |  |  | L | N | N | M | N | 6 | C. Dukes | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
VETO-127 | 3403 | Opportunity | Less cosmic ray veto coverage is needed | FY14-FY15 |  |  | M | N | L | N | N | 5 | C. Dukes |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-020 | 3333 | Threat | Retire- Cannot use TLMs to control beam losses. | FY14-FY19 | 20000 | Retired | L | N | VH | N | N | 24 | T. Leveling | 2000000 |  | 10% | 200000 | 0 | 10% | 25% | 4.33% | 351.8 | 364 | 382
VETO-127 | 3403 | Opportunity | Less cosmic ray veto coverage is needed | FY14-FY15 |  | Retired | M | N | H | N | N | 24 | C. Dukes | -500000 |  | 10% | -50000 | 0 | 25% | 75% | 14.43% | -226.5 | -236.6667 | -251.6667
ACCEL-140 | 3346 | Threat | Proton beam not available for beam studies in FY2013 | FY-13-FY14 |  | Retired | L | N | N | M | N | 6 | S. Werkema | 0 |  | 17% | 0 | 0 | 10% | 25% | 4.33% | 0 | 0 | 0
2014-09-23
SOL-072 | 3369 | Threat | Tevatron HTS leads do not perform to Mu2e specifications. | FY13-FY15 | 20000 | Retired | L | N | M | N | N | 6 | M. Lamm | 200000 | 0 | 20% | 40000 | 0 | 10% | 25% | 4.33% | 41.8467 | 43.0667 | 44.8667
PM-005 | 3362 | Threat | Construction funds not available as assumed. | FY14 |  | Retired | L | H | VH | N | N | 24 | Ron Ray | 500000 | 120 | 10% | 50000 | 12 | 10% | 25% | 4.33% | 87.95 | 91 | 95.5
2014-09-29
ACCEL-033 | 3832 | Threat | Inability to stage magnets in the Accumulator enclosure during g-2 operation | FY16-FY18 |  | Retired | L | N | H | M | N | 12 | C. Johnstone | 400000 |  | 20% | 80000 | 0 | 10% | 25% | 4.33% | 83.6933 | 86.1333 | 89.7333
CONST-050 | 3352 | Threat | Conventionl construction bids exceed estimated cost. | FY14 |  | Retired | L | N | VH | N | N | 24 | T. Lackowski | 1200000 |  | 10% | 120000 | 0 | 10% | 25% | 4.33% | 205.2486 | 211.08 | 218.4
2014-12-10
CONST-165 | 4425 | Threat | Cost growth of conventional construction facilities because of changing stakeholder requirements. | FY15 |  | Retired | L | M | M | M | VL | M | T. Lackowski | 276000 | 140 | 10% | 27600 | 14 | 10% | 25% | 4.33% | 47.2072 | 48.5484 | 50.232 | 47.2072
2015-06-12
ACCEL-020 | 3333 | Threat | Cannot use TLMs to control beam losses. | FY16 |  | Retired | VL | N | VH | N | N | H | T. Leveling | 2000000 |  | 2% | 40000 | 0 | 0% | 10% | 2.887% | 108.054 | 114.5333 | 122.6667
2015-09-11
SOL-205 | 5038 | Threat | TS Prototype Coil Module test failure | FY15 |  | Current Risk | L | L | M | N | N |  | M.Lamm | 100000 | 60 | 10% | 10000 | 6 | 10% | 25% | 4.33% | 17.1041 | 17.59 | 18.2 | 17.1041
TRACK-139 | 3392 | Threat | Mylar creep limits tracker lifetime | FY15-FY17 | 5000 | Current Risk | L | VL | VL | H | N | M | A. Mukherjee | 50000 | 30 | 10% | 5000 | 3 | 10% | 25% | 4.33% | 8.552 | 8.795 | 9.1

## Transfered Risk Events
Risk | [6 empty] | Post-mitigation | [5 empty] | Details | [7 empty] | NOTES:
ID | DocDb # | Type | Title | Date of Risk | Mitigation Cost (included in plan) | Category | Probability | Delay in data taking | Cost | Technical | ESH&Q | Score | Owner | Point estimate (cost k$) | Point Estimate (sched-days) | Point estimate (prob) | EXPECTATION VALUE IN k$ | EXPECTATION VALUE IN Days | RMS Cost (k$) | Variance Cost (k$)
ACCEL-035 | 3342 | Threat | Failure of extinction system to sufficiently eliminate out of time beam | FY21 |  | Transfer to operations | VL | M | M | H | N | Low | E. Prebys | 175 | 120 | 0.05 | 8.75 | 6 | 30 | 900 | AD
MUON-088 | 3358 | Threat | Background from neutrons higher than anticipated inside detector Solenoid. | FY21 | 20000 | Transfer to operations | L | L | L | M | N | Low | R. Bossert | 75 | 60 | 0.17 | 12.75 | 10.2 | 10 | 100 | PPD
ACCEL-012 | 3329 | Threat | Mu2e beam comissioning delayed. | FY20 |  | Transfer to operations | M | L | L | VL | N | Low | S. Werkema | 75 | 60 | 0.5 | 37.5 | 30 | 10 | 100 | AD
ACCEL-017 | 3332 | Threat | Radiation levels outside of Mu2e facility too high. | FY21 |  | Transfer to operations | L | L | L | M | M | Low | T. Leveling | 75 | 60 | 0.17 | 12.75 | 10.2 | 10 | 100 | AD/PPD
ACCEL-022 | 3335 | Threat | Large beam loss from Resonant Extraction. | FY19-FY20 |  | Transfer to operations | M | L | VL | M | N | Low | v. Nagaslaev | 25 | 60 | 0.5 | 12.5 | 30 | 10 | 100 | AD
ACCEL-150 | 3839 | Threat | Need to install additional DR tunnel shielding (list C) | FY21 |  | Transfer to operations | L | M | H | M | N | Moderate | T. Leveling | 77 | 135 | 0.17 | 13.09 | 22.95 | 50 | 2500 | AD
MUON-083 | 3354 | Threat | Significantly larger gas loads in warm bore of DS than anticipated. | FY21-FY25 | 50000 | Transfer to operations | M | M | M | M | N | Moderate | G. Ginther | 200 | 135 | 0.5 | 100 | 67.5 | 30 | 900 | PPD
MUON-084 | 3355 | Threat | Vacuum leak. | FY21 |  | Transfer to operations | M | M | M | L | N | Moderate | D. Pushka | 175 | 135 | 0.5 | 87.5 | 67.5 | 30 | 900 | PPD
MUON-085 | 3356 | Threat | Inadequate pumping speed to maintain required vacuum in PS. | FY21 |  | Transfer to operations | M | M | M | M | N | Moderate | D. Pushka | 175 | 135 | 0.5 | 87.5 | 67.5 | 30 | 900 | PPD
SOL-074 | 3370 | Threat | Field mapping unit does not perform to specification | FY20 |  | Transfer to operations | VL | M | L | M | N | Low | M. Lamm | 75 | 135 | 0.05 | 3.75 | 6.75 | 10 | 100 | PPD
ACCEL-014 | 3330 | Threat | Radiation damage to fiber optics communication lines | FY21-FY25 | 10000 | Transfer to operations | L | N | M | N | N | Low | B. Drendel | 100 | 0 | 0.15 | 15 | 0 | 30 | 900 | AD
MUON-086 | 3357 | Threat | PS vacuum window failure. | FY20-FY25 |  | Transfer to operations | VL | VH | H | VH | H | Moderate | D. Pushka | 375 | 365 | 0.05 | 18.75 | 18.25 | 50 | 2500 | PPD
CAL-111 | 3348 | Threat | Pileup in the calorimeter | FY21 |  | Transfer to operations | VL | N | L | M | N | Low | S. Miscetti | 25 | 0 | 0.05 | 1.25 | 0 | 10 | 100 | PPD
CAL-113 | 3349 | Threat | Radiation damage to calorimeter photosensors | FY21-FY25 | 50000 | Transfer to operations | L | N | M | M | N | Low | S. Miscetti | 175 | 0 | 0.17 | 29.75 | 0 | 30 | 900 | PPD
MUON-090 | 3359 | Threat | Detector components move after installation. | F21-FY25 | 200000 | Transfer to operations | L | VL | VL | M | N | Low | R. Bossert | 25 | 15 | 0.17 | 4.25 | 2.55 | 10 | 100 | PPD
ACCEL-152 | 3838 | Threat | Need to install additional Delivery Ring tunnel shielding (list B) | FY21 | 50000 | Transfer to operations | L | M | M | M | N | Low | T. Leveling | 175 | 0 | 0.17 | 29.75 | 0 | 5.0575 | 25.5783 | REDUNDANT WITH "NEED TO INSTALL ADD'L DR SHIELDING (LIST C)"
ACCEL-037 |  | Threat | Extinction monitor fails to perform to requirements. | FY21 |  | Transfer to operations | VL | VL | M | H | N | Low | P. Kasper | 175 | 15 | 0.05 | 8.75 | 0.75 | 30 | 900 | PPD
ACCEL-041 |  | Threat | Heat and radiation shield insufficient to protect the Production Solenoid | FY21-FY25 |  | Transfer to operations | VL | M | N | M | N | Low | R. Coleman | 0 | 135 | 0.05 | 0 | 6.75 | 0 | 0 | AD
MUON-143 | 3840 | Threat | Background rates in Cosmic Ray Veto higher than anticipated | FY21 | 3000000 | Transfer to operations | L | M | VH | M | N | Moderate | G. Ginther | 750 | 135 | 0.17 | 127.5 | 22.95 | 100 | 10000 | PPD
MUON-144 | 3841 | Threat | Damage to surrounding elements during installation | FY20-FY21 | 50000 | Transfer to operations | VL | VH | VH | VH | N | Moderate | N. Andreev/R. Bossert | 750 | 365 | 0.01 | 7.5 | 3.65 | 100 | 10000 | PPD
MUON-145 | 3842 | Threat | Shielding installation impacts beamline alignment | F21 | 30000 | Transfer to operations | L | L | M | L | N | Low | G. Ginther/K. Krempetz | 175 | 60 | 0.17 | 29.75 | 10.2 | 30 | 900 | AD
TRACK-206 | 5211 | Threat | Straws collapse due to over pressurizing of the DS during a backfill. | F21-FY25 | 15000 | Transfer to operations | VL | VH | VH | VH | L | Moderate | Aseet Mukherjee | 5000 | 500 | 0.01 | 50 | 5
[16 empty] | Sum(Cost) | 698.34 | k$
[16 empty] | Var(Cost) | 32925.5783
[16 empty] | RMS(Cost) | 181.4541 | k$
[16 empty] | 90% CL | 934.2303 | 1-sided (k$)
[16 empty] | 95% CL | 988.6665 | 1-sided (k$)

## Realized Risk events
[19 empty] | y | Include Opportunities?
Risk | [6 empty] | Post-mitigation | [5 empty] | Details | [5 empty] | Risk Contingency | [6 empty] | NOTES:
ID | DocDb # | Type | Title | Date of Risk | Mitigation Cost (included in plan) | Category | Probability | Schedule-Delays Level 3 Milestone or Project Critical Path by X Days | Cost | Technical | ESH&Q | Score | Owner | Point estimate (cost k$) | Point Estimate (sched-days) | Point estimate (prob) | EXPECTATION VALUE IN k$ | EXPECTATION VALUE IN Days | Prob Range |  | Prob RMS | 80% CL | 85% CL | 90%CL | 100% Realized
ACCEL-011 | 3328 | Threat | Inadequate AD Engineering Resources | FY12-FY14 |  |  | M | L | N | N | N | 24 | Ron Ray | 0 | 60 | 10% | 0 | 6 | -2.5% | 22.5% | 7.217% | 0 | 0 | 0
ACCEL-012 | 3329 | Threat | Mu2e beam comissioning delayed. |  |  | Transfer to operations | M | H | N | H | L | 24 | S. Werkema | 0 |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
ACCEL-014 | 3330 | Threat | Radiation damage to fiber optics communication lines | FY13-FY20 | 10000 |  | L | N | M | N | N | 10 | C. Johnstone, B. Drendel | 100000 |  | 50% | 50000 | 0 | 37.5% | 62.5% | 7.217% | 57692.6635 | 59515.9583 | 62213.5883
ACCEL-015 | 3331 | Threat | Injection damper required for Delivery Ring | FY16-FY19 |  |  | L | N | N | VH | N | 24 | J. Morgan | 185000 | 0 | 10% | 18500 | 0 | -2.5% | 22.5% | 7.217% | 21346.2855 | 22020.9046 | 23019.0277
ACCEL-016 |  | Threat | Delivery Ring tunes cannot be measured to the required accuracy. |  |  |  | L | N | L | N | N | 3 | B. Drendel |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-017 | 3332 | Threat | Radiation levels outside of Mu2e facility too high. |  |  | Transfer to operations | L | N | N | VH | N | 24 | T. Leveling | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
ACCEL-020 | 3333 | Threat | Cannot use TLMs to control beam losses. | FY14-FY19 | 20000 |  | L | N | VH | N | N | 24 | T. Leveling | 2000000 |  | 10% | 200000 | 0 | -2.5% | 22.5% | 7.217% | 230770.6538 | 238063.8334 | 248854.3532
ACCEL-021 | 3334 | Opportunity | Availability of the shielding steel blocks on site |  |  | Realized | M | N | M | N | N | 10 | J.Annala | -134000 |  | 0% | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-022 | 3335 | Threat | Large beam loss from Resonant Extraction. | FY19-FY20 |  | Transfer to operations | M | N | N | H | N | 24 | v. Nagaslaev |  |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
ACCEL-023 |  | Threat | Resonant extraction leaves an inacceptably large fraction of the beam circulating in the Delivery Ring |  |  | Retired | L | N | N | M | N | 0 | V. Nagaslaev, J. Morgan |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-024 |  | Threat | Inability to locate and reuse all the necessary tooling and infrastracture hardware for the ES septum fabrication |  |  | Retired | M | N | M | N | N | 0 | v. Nagaslaev |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-025 |  | Threat | Capability to ramp Delivery Ring sextupoles required. |  |  | Retired | L | N | L | N | N | 0 | V. Nagaslaev |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-026 | 3336 | Threat | Cannot adequately maintain proton beam position and angle on production target. |  | Implementation of auto tune | Retired | M | N | N | H | L | 24 | C. Johnstone |  |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
ACCEL-027 |  | Threat | Inability to clear Delivery ring quads with extracted beam orbit |  |  | Retired | L | N | N | M | N | 0 | C. Johnstone, V. Nagaslaev |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-028 | 3337 | Opportunity | Assumed refurbishment of SQ magnets not required. |  |  | Realized | M | N | VL | N | N | 3 | J.Annala | -13000 |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-029 | 3338 | Threat | Need to build 6 CDA-like magnets from scratch |  |  | DELETED | M | N | VH | N | N | 0 | J.Annala | 0 |  | 0% | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-030 | 3339 | Opportunity | Reduced cost of 6-3-120 magnets preparation |  |  | Realized | L | N | L | N | N | 3 | J.Annala | -30000 |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-031 |  | Threat | Need to build 10 Q18 magnets |  |  | Retired | M | N | M | N | N | 0 | J.Annala |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-032 | 3340 | Opportunity | Reduced cost of Large aperture quads |  |  | Realized | L | N | L | N | N | 3 | J.Annala | -200000 |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-033 |  | Threat | Inability to stage magnets in the Accumulator enclosure during g-2 operation |  |  |  | VL | N | L | N | N | 1 | C. Johnstone |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-034 | 3341 | Threat | Unable to perform the orbit and optics control with proposed reduced number of position monitors |  |  | DELETED | L | N | H | M | N | 12 | C. Johnstone | 0 |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-035 | 3342 | Threat | Failure of extinction system to sufficiently eliminate out of time beam |  |  | Transfer to operations | L | N | N | VH | N | 40 | E. Prebys | 0 |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
ACCEL-036 | 3343 | Opportunity | No need in internal extinction collimation |  |  | Realized | M | N | M | N | N | 10 | E. Prebys | -1000000 |  | 50% | -500000 | 0 | 37.5% | 62.5% | 7.217% | -576926.6345 | -595159.5835 | -622135.883
ACCEL-037 |  | Threat | Extinction monitor fails to perform to requirements. |  |  | Transfer to operations | VL | N | N | H | N | 4 | P. Kasper |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-038 | 3344 | Threat | Radiated target will not survive in the Beam. | FY14-FY20 |  |  | L | N | M | N | N | 6 | R. Coleman | 175000 |  | 10% | 17500 | 0 | -2.5% | 22.5% | 7.217% | 20192.4322 | 20830.5854 | 21774.7559
ACCEL-041 |  | Threat | Heat and radiation shield insufficient to protect the Production Solenoid |  |  | Transfer to operations | L | N | N | L | N | 3 | R. Coleman |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-042 | 3345 | Threat | Mechanical design of the heat and radiation shield inadequate to sustain loads generated during Production and Transport Solenoid quenches. |  |  | Retired | VL | N | N | VH | N | 8 | R. Coleman, M. Lamm | 0 |  | 5% | 0 | 0 | -7.5% | 17.5% | 7.217% | 0 | 0 | 0
ACCEL-043 |  | Threat | Production solenoid quenching. |  |  | Retired | VL | N | N | VH | N | 0 | R. Coleman, M. Lamm |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
ACCEL-140 | 3346 | Threat | Proton beam not available for beam studies in FY2013 |  |  |  | L | N | N | M | N | 6 | S. Werkema | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
ACCEL-141 |  | Threat | Extraction Lambertson scope returns to Mu2e Scope |  |  | Retired | L | L | VH | VL | N | 0 | S. Werkema |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CAL-108 | 3347 | Threat | INFN cannot deliver full in-kind scope. |  |  |  | M | N | H | H | N | 24 | R. Ray | 1000000 |  | 50% | 500000 | 0 | 37.5% | 62.5% | 7.217% | 576926.6345 | 595159.5835 | 622135.883
CAL-111 | 3348 | Threat | Pileup in the calorimeter |  |  | Transfer to operations | L | N | N | L | N | 6 | S. Miscetti | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
CAL-148 | ? | Threat | Cannot develop UV-extended solid state photodetector that is blind to longer wavelengths |  | 100000 |  | M | M | N | H | N |  | D. Hitlin
CAL-113 | 3349 | Threat | Radiation damage to calorimeter photosensors |  | 50000 | Transfer to operations | L | N | N | M | N | 6 | S. Miscetti | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
CONST-047 |  | Threat | Errors & omissions In design of conventional facilities by A&E firm. |  |  |  | L | N | L | N | N | 3 | T. Lackowski |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CONST-048 | 3350 | Threat | Significant injury or death associated with civil construction. | FY14-FY16 |  |  | VL | M | M | N | VH | 8 | T. Lackowski | 100000 |  | 5% | 5000 | 0 | -7.5% | 17.5% | 7.217% | 5769.2663 | 5951.5958 | 6221.3588
CONST-049 | 3351 | Opportunity | Conventionl construction bids are lower than estimated cost. | FY14 |  |  | M | N | M | N | N | 10 | T. Lackowski | -1200000 |  | 50% | -600000 | 0 | 37.5% | 62.5% | 7.217% | -692311.9614 | -714191.5002 | -746563.0596
CONST-050 | 3352 | Threat | Conventionl construction bids exceed estimated cost. | FY14 |  |  | L | N | M | N | N | 6 | T. Lackowski | 1200000 |  | 10% | 120000 | 0 | -2.5% | 22.5% | 7.217% | 138462.3923 | 142838.3 | 149312.6119
CONST-051 |  | Threat | Civil contractor cannot complete work satisfactorily or defaults on contract. |  |  |  | VL | N | L | N | N | 1 | T. Lackowski |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CONST-054 |  | Threat | Conventional Systems performance does not meet criteria |  |  |  | VL | N | H | M | N | 4 | T. Lackowski |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CONST-055 |  | Threat | Final design of conventional facilities delayed. |  |  | Retired | L | M | N | N | N | 0 | T. Lackowski |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CONST-058 |  | Threat | Unforeseen/undocumented subsurface conditions discovered during excavation for conventional construction. |  |  |  | VL | M | M | N | N | 2 | T. Lackowski |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CONST-059 |  | Threat | Disruptions To Fermilab utilities, facilities or operations |  |  | Retired | L | L | N | N | N | 0 | T. Lackowski |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CONST-063 |  | Threat | Storm Water Pollution |  |  | Retired | VL | N | N | N | N | 0 | T. Lackowski |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CONST-064 |  | Threat | Severe Weather impacts civil construction. |  |  |  | L | L | L | N | N | 3 | T. Lackowski |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
CONST-065 | 3353 | Threat | Feeder 24 from MSS to F3 not adequate |  |  | Move to Muon Campus Scope | M | N | M | N | N | 10 | T. Lackowski | 0 |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
MUON-083 | 3354 | Threat | Significantly larger gas loads in warm bore of DS than anticipated. |  | 50000 | Transfer to operations | M | N | M | N | N | 10 | G. Ginther | 0 |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
MUON-084 | 3355 | Threat | Vacuum leak. |  |  | Transfer to operations | M | M | M | N | N | 10 | J. Brandt | 0 | 0 | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
MUON-085 | 3356 | Threat | Inadequate pumping speed to maintain required vacuum in PS. |  |  | Transfer to operations | M | N | M | N | N | 10 | J. Brandt | 0 |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
MUON-086 | 3357 | Threat | PS vacuum window failure. |  |  | Transfer to operations | VL | N | H | H | VH | 8 | J. Brandt | 0 |  | 5% | 0 | 0 | -7.5% | 17.5% | 7.217% | 0 | 0 | 0
MUON-088 | 3358 | Threat | Background from neutrons higher than anticipated inside detector Solenoid. |  | 20000 |  | M | N | H | N | N | 10 | R. Bossert | 1000000 |  | 50% | 500000 | 0 | 37.5% | 62.5% | 7.217% | 576926.6345 | 595159.5835 | 622135.883
MUON-089 |  | Threat | RETIRED- Distortion of DS magnetic field. |  |  | Retired | L | N | M | N | N | 0 | R. Bossert |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
MUON-090 | 3359 | Threat | Detector components move after installation. |  | 200000 | Transfer to operations | L | N | N | M | N | 6 | R. Bossert | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
MUON-138 | 3360 | Threat | Detector installation takes longer than expected. |  |  |  | M | M | M | N | N | 10 | G. Ginther | 400000 | 0 | 50% | 200000 | 0 | 37.5% | 62.5% | 7.217% | 230770.6538 | 238063.8334 | 248854.3532
MUON-143 | ? | Threat | Background rates in Cosmic Ray Veto higher than anticipated |  | 3000000 | Transfer to operations | L | N | VH | M | M |  | G. Ginther |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
MUON-144 | ? | Threat | Damage to surrounding elements during installation | FY20-21 | 50K | Transfer to operations | VL | VH | VH | VH | VH |  | N. Andreev/R. Bossert |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
MUON-145 | ? | Threat | Shielding installation impacts beamline alignment |  | 30k | Transfer to operations | L | N | M | N | N |  | G. Ginther/K. Krempetz |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
MUON-146 | ? | Threat | Rates exceed Muon Stopping Target Monitor capabilities |  |  |  | L | N | M | M | N |  | J. Miller | 200000 |  | 17% | 34000 | 0 | 4.5% | 29.5% | 7.217% | 39231.0111 | 40470.8517 | 42305.24
MUON-147 | ? | Threat | Degrader needed for calibration |  |  |  | M | N | M | M | VL |  | G. Ginther | 250000 |  | 50% | 125000 | 0 | 37.5% | 62.5% | 7.217% | 144231.6586 | 148789.8959 | 155533.9708
PM-001 |  | Threat | Project funds not available at the beginning of fiscal year. |  |  |  | M | L | N | N | N | 5 | Ron Ray |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
PM-002 | 3361 | Opportunity | DOE advances project funding profile, providing money sooner than anticipated. |  |  |  | M | M | N | N | N | 10 | Ron Ray | 0 |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
PM-003 |  | Threat | CD-3a funds not available as assumed. |  |  | Retired | M | H | N | N | N | 0 | Ron Ray |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
PM-004 |  | Threat | Project is not granted a Categorical Exclusion and has to write an Environmental Assessment (EA) |  |  | Retired | L | N | M | N | N | 0 | Ron Ray |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
PM-005 | 3362 | Threat | Construction funds not available as assumed. | FY14 |  |  | L | H | H | N | N | 12 | Ron Ray | 3000000 | 60 | 10% | 300000 | 6 | -2.5% | 22.5% | 7.217% | 346155.9807 | 357095.7501 | 373281.5298
PM-007 | 3363 | Threat | CD-4 float inadequate. |  |  |  | L | M | L | N | N | 6 | Ron Ray | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
PM-008 | 3364 | Threat | Additional resources required in Project Office to manage Project. |  |  |  | L | N | M | N | N | 6 | Ron Ray | 500000 |  | 10% | 50000 | 0 | -2.5% | 22.5% | 7.217% | 57692.6635 | 59515.9583 | 62213.5883
PM-009 | 3365 | Opportunity | Fewer Resources than anticipated required in Project Office to manage Project. |  |  |  | L | N | M | N | N | 6 | Ron Ray | -500000 |  | 10% | -50000 | 0 | -2.5% | 22.5% | 7.217% | -57692.6635 | -59515.9583 | -62213.5883
PM-010 | 3366 | Threat | Unexpected increase in Fermilab overhead rates |  |  |  | M | N | H | N | N | 24 | Ron Ray | 2000000 | 0 | 50% | 1000000 | 0 | 37.5% | 62.5% | 7.217% | 1153853.269 | 1190319.1669 | 1244271.766
PM-142 | 3757 | Threat | Currency fluctuations on foreign procurements |  |  |  | M | N | M | N | N | 12 | Ron Ray | 200000 | 0 | 50% | 100000 | 0 | 37.5% | 62.5% | 7.217% | 115385.3269 | 119031.9167 | 124427.1766
SOL-066 | 3367 | Threat | Critical path delayed due to solenoid schedule delay. | FY18-FY20 | 20000 |  | L | H | H | N | N | 24 | M. Lamm | 4000000 | 360 | 20% | 800000 | 72 | 7.5% | 32.5% | 7.217% | 923082.6152 | 952255.3335 | 995417.4128
SOL-067 |  | Threat | Too Few bidders on DS/PS design and construction. |  |  |  | VL | H | H | N | N | 4 | M. Lamm |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
SOL-068 |  | Threat | Conductor for Mu2e PS and DS solenoids does not have a market in industry. There may not be a sufficient business interest to invest in the tooling etc. to make this conductor |  |  | Retired | L | H | H | N | N | 0 | M. Lamm |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
SOL-070 | 3368 | Threat | Interface problems with the solenoids. | FY14-FY19 |  |  | L | H | H | N | N | 24 | M. Lamm | 3000000 | 360 | 15% | 450000 | 54 | 2.5% | 27.5% | 7.217% | 519233.9711 | 535643.6251 | 559922.2947
SOL-071 |  | Threat | Tevatron HTS leads cannot be adapted to mu2e PS. |  |  | Retired | M | N | L | N | N | 0 | M. Lamm |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
SOL-072 | 3369 | Threat | Tevatron HTS leads do not perform to Mu2e specifications. | FY13-FY15 | 20000 |  | L | N | M | N | N | 24 | M. Lamm | 200000 | 0 | 20% | 40000 | 0 | 7.5% | 32.5% | 7.217% | 46154.1308 | 47612.7667 | 49770.8706
SOL-074 | 3370 | Threat | Field mapping unit does not perform to specification |  |  | Transfer to operations | M | N | N | M | N | 10 | M. Lamm | 0 |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
SOL-077 |  | Threat | Thermal Siphon approach to cooling in PS does not work properly |  |  | Transfer to operations | VL | N | N | H | N | 4 | M. Lamm |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
SOL-078 | 3371 | Threat | Minimal approach to TS mapping proves to be inadequate with poor transmission of muon beam to stopping target. |  | 200000 | Operations | M | N | N | M | N | 10 | M. Lamm | 0 |  | 50% | 0 | 0 | 37.5% | 62.5% | 7.217% | 0 | 0 | 0
SOL-080 | 3372 | Threat | Insufficient testing of DS and/or PS at Vendor | FY18-FY20 | 50000 |  | L | H | H | N | N | 12 | M. Lamm | 3000000 | 360 | 15% | 450000 | 54 | 2.5% | 27.5% | 7.217% | 519233.9711 | 535643.6251 | 559922.2947
SOL-137 | 3373 | Threat | Solenoid fringe field impacts performance of nearby equipment | FY17-FY20 | 100000 |  | L | N | L | L | VL | 6 | K. Krempetz | 75000 |  | 10% | 7500 | 0 | -2.5% | 22.5% | 7.217% | 8653.8995 | 8927.3938 | 9332.0382
SOL-148 | ? | Threat | Production Solenoid must be installed through PS hatch using a large rented crane. | FY18-19 |  |  | M | N | H | N | N |  | T. Page | 300000 |  | 50% | 150000 | 0 | 37.5% | 62.5% | 7.217% | 173077.9904 | 178547.875 | 186640.7649
TRACK-091 | 3382 | Threat | Simulations indicate that tracker occupancy higher than expected |  |  | Transfer to operations | L | N | N | H | N | 12 | D.Brown | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
TRACK-092 | 3383 | Threat | No manufacturer able to produce straws to desired tolerances |  |  | Retired | L | H | H | N | N | 0 | A. Mukherjee |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-093 |  | Threat | Straw leak rate too high. |  |  |  | VL | H | M | H | N | 4 | A. Mukherjee, G. Ginther |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-094 |  | Threat | Change in cost of straw material |  |  |  | VL | N | L | N | N | 1 | A. Mukherjee |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-095 | 3384 | Opportunity | Change in cost of straw material |  |  | DELETED | M | N | M | N | N | 10 | A. Mukherjee | -175000 |  | 50% | -87500 | 0 | 37.5% | 62.5% | 7.217% | -100962.161 | -104152.9271 | -108873.7795
TRACK-096 | 3385 | Threat | Detector support structure not sufficiently rigid or stable |  |  | Transfer to operations | VL | L | N | M | N | 6 | A. Mukherjee | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
TRACK-097 | 3386 | Threat | Catastrophic mechanical failure of Tracker. |  |  |  | VL | VH | VH | VH | N | 8 | A. Mukherjee | 4000000 | 400 | 1% | 40000 | 4 | -11.5% | 13.5% | 7.217% | 46154.1308 | 47612.7667 | 49770.8706
TRACK-098 | 3387 | Opportunity | 2nd prototype ASIC run not needed |  | Savings is captured in TRACK-099 | DELETED | L | M | M | N | N | 6 | Y. Kolomensky | -175000 |  | 10% | -17500 | 0 | -2.5% | 22.5% | 7.217% | -20192.4322 | -20830.5854 | -21774.7559
TRACK-099 | 3388 | Opportunity | Tracker readout can be fully implemented in commercial off-the-shelf parts. |  |  | Realized | L | M | L | N | N | 6 | Y. Kolomensky | -300000 |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-100 |  | Threat | Localized tracker electronics failure |  |  |  | L | N | N | L | N | 3 | Y. Kolomensky |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-101 |  | Threat | Excessive heat load from inaccessible tracker electronics inside DS vacuum. |  |  |  | VL | N | L | M | N | 2 | A. Mukherjee |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-102 | 3389 | Threat | Failure in a single straw tube prevents operating a large region of the tracker |  | 100000 | Move to Operations | L | N | N | H | N | 12 | A. Mukherjee | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
TRACK-103 |  | Threat | Widespread tracker electronics failure |  |  |  | VL | N | N | M | N | 2 | Y. Kolomensky |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-104 | 3390 | Threat | Gain loss in tracker. |  | 5000 | Move to Operations | L | N | N | H | N | 12 | A. Mukherjee | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
TRACK-105 |  | Threat | Tracker breakdown due to detector aging |  |  | Retired | N | N | N | M | N | 0 | A. Mukherjee |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-106 | 3391 | Threat | High rate variations are seen by the tracker from pulse-to-pulse. |  | 5000 | Move to Operations | VL | N | N | L | N | 6 | A. Mukherjee | 0 |  | 83% | 0 | 0 | 70.5% | 95.5% | 7.217% | 0 | 0 | 0
TRACK-107 |  | Threat | Catastrophic Tracker high voltage failure |  |  | Retired | L | N | N | N | N | 0 | A. Mukherjee |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
TRACK-139 | 3392 | Threat | Mylar creep limits tracker lifetime |  | 5000 |  | L | N | H | H | N | 24 | A. Mukherjee | 390000 | 100 | 10% | 39000 | 10 | -2.5% | 22.5% | 7.217% | 45000.2775 | 46422.4475 | 48526.5989
TRIG-128 | 3393 | Threat | Insufficient manpower for DAQ software. | FY14-FY19 |  |  | M | N | M | N | N | 14 | M. Bowden | 500000 |  | 50% | 250000 | 0 | 37.5% | 62.5% | 7.217% | 288463.3173 | 297579.7917 | 311067.9415
TRIG-130 | 3394 | Threat | Insufficient DAQ online processing. | FY14-FY19 |  |  | L | N | L | N | N | 6 | M. Bowden | 75000 |  | 20% | 15000 | 0 | 7.5% | 32.5% | 7.217% | 17307.799 | 17854.7875 | 18664.0765
TRIG-131 | 3395 | Threat | Higher than expected data rates to the DAQ. | FY14-FY19 |  |  | L | N | M | M | N | 6 | M. Bowden | 130000 |  | 10% | 13000 | 0 | -2.5% | 22.5% | 7.217% | 15000.0925 | 15474.1492 | 16175.533
TRIG-132 | 3396 | Opportunity | Use of surplus equipment. | FY14-FY19 |  |  | H | N | L | N | N | 6 | M. Bowden | -30000 |  | 50% | -15000 | 0 | 37.5% | 62.5% | 7.217% | -17307.799 | -17854.7875 | -18664.0765
TRIG-134 | 3397 | Opportunity | Lower cost commercial PCIe card for DTC. | FY14-FY19 |  |  | M | N | L | N | N | 6 | M. Bowden | -20000 |  | 25% | -5000 | 0 | 12.5% | 37.5% | 7.217% | -5769.2663 | -5951.5958 | -6221.3588
TRIG-135 | 3398 | Opportunity | Slow Controls development in common with other experiments. | FY14-FY19 |  |  | L | N | L | N | N | 3 | M. Bowden | -40000 |  | 10% | -4000 | 0 | -2.5% | 22.5% | 7.217% | -4615.4131 | -4761.2767 | -4977.0871
TRIG-136 | 3399 | Opportunity | Efficient Calorimeter Trigger reduces online processing requirements. | FY14-FY19 |  |  | L | N | M | N | N | 6 | M. Bowden | -40000 |  | 10% | -4000 | 0 | -2.5% | 22.5% | 7.217% | -4615.4131 | -4761.2767 | -4977.0871
VETO-114 | 3400 | Threat | Simulations indicate that neutron flux at the CRV is too high. | FY12-FY20 | 2000000 |  | L | N | H | H | N | 24 | C. Dukes | 0 | 0 | 10% | 0 | 0 | -2.5% | 22.5% | 7.217% | 0 | 0 | 0
VETO-115 |  | Threat | RETIRE-Cosmic ray background estimation incomplete by CD2. |  |  | Retired | L | N | M | N | N | 0 | C. Dukes |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
VETO-117 |  | Threat | Additional coverage is needed for Cosmic Ray Veto |  |  |  | L | N | L | N | N | 3 | C. Dukes |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
VETO-118 | 3401 | Threat | Simulations indicate that scintillator-based Cosmic Ray Veto does not have required efficiency. |  |  | Retired | L | N | M | H | N | 12 | C. Dukes | 0 | 0 | 0% | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
VETO-119 |  | Threat | Assembly room at Virginia is inadequate for CRV module construction. |  |  |  | L | N | L | N | N | 3 | C. Group |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
VETO-120 |  | Threat | RETIRE-Cosmic ray test stand needs to be fabricated |  |  | Retired | L | N | L | N | N | 0 | C. Group |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
VETO-121 |  | Threat | RETIRE-Existing flycutter cannot be obtained |  |  | Retired | L | N | L | N | N | 0 | C. Group |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
VETO-122 | 3402 | Threat | Need to use inferior fibers | FY15 |  |  | L | N | N | M | N | 6 | C. Dukes | 0 |  | 17% | 0 | 0 | 4.5% | 29.5% | 7.217% | 0 | 0 | 0
VETO-127 | 3403 | Opportunity | Less cosmic ray veto coverage is needed | FY14-FY15 |  |  | M | N | L | N | N | 5 | C. Dukes |  |  |  | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0
[5 empty] | 5955000 | [8 empty] | 24123000 | 1700 |  | 4191500 | 206 | 1091500 | 7291500 | 622467.1594 | 4836375.9772 | 4989222.7882 | 5215365.1072
2014-12-10
CONST-049 | 3351 | Opportunity | Conventional construction bids are lower than estimated cost. | FY15 |  | Realized | M | N | VH | N | N | H | T. Lackowski | -1200000 |  | 50% | -600000 | 0 | 25% | 75% | 14.43% | -684.162 | -703.6 | -728
2014-05-15
SOL-155 | 3954 | Opportunity | Cryo Distribution Box Funded by Cryo AIP | FY15-FY17 |  | Realized | M | N | VH | N | N | H | M. Lamm | -1972000 |  | 100% | -1972000 | 0 | 25% | 75% | 14.43% | -1452.9729 | -1484.916 | -1525.0133 | -1972000

## Risk Mapping
ACCEL-011 | 475.02W
ACCEL-014 | 1.02.03.01, 1.02.08.06
ACCEL-015 | 475.02.03.02
ACCEL-020 | 475.02.04
ACCEL-033 | 475.02W.07
ACCEL-038 | 475.02W
ACCEL-140 | 475.02.03, 475.02.04, 475.02.05, 475.02.07
ACCEL-151 | 475.02.09.02, 475.02.09.03, 475.02.09.04
CAL-108 | 475.7
CAL-148 | 475.7
CONST-049 | 475.03
CONST-050 | 475.03
MUON-138 | 475.05.11
MUON-146 | 475.05W.06
MUON-147 | 475.5.7
PM-005 | 47501.3.2.001198
PM-007 | 475.01W.4.3.001110
PM-008 | 47501.3.1.001220, 47501.4.1.001010, 47501.4.1.001040, 47501.4.1.001070, 47501.4.1.001080, 47501.4.1.001095, 47501.4.1.001200
PM-009 | 47501.3.1.001220, 47501.4.1.001010, 47501.4.1.001040, 47501.4.1.001070, 47501.4.1.001080, 47501.4.1.001095, 47501.4.1.001200
PM-010 | 475
PM-048 | 475.03
PM-142 | 475.01W
PM-153 | 475.02, 475.04.03, 475.05, 475.06.02.01
PM-154 | 475.02, 475.04.03, 475.05, 475.06.02.01
SOL-066 | 475.04.02, 475.04.03, 475.04.04
SOL-070 | 475.04.02, 475.04.03, 475.04.04
SOL-072 | 475.04W.05.01
SOL-080 | 475.04.02, 475.04.04
SOL-137 | 475.04W,475.05W.02
SOL-148 | 475.04.10
SOL-155 | 475.04.05.07
SOL-157 | 475.04.02
TRACK-097 | 475.6.3.4, 475.6.06
TRACK-139 | 475.6.2
TRIG-128 | 475.09
TRIG-130 | 475.09W.04
TRIG-131 | 475.09W.03
TRIG-132 | 475.09W.04
TRIG-134 | 475.09W.03
TRIG-135 | 475.09W.05
TRIG-136 | 475.09W
VETO-114 | 475.08W
VETO-122 | 475.08W.04,475.08W.05
VETO-127 | 475.08W.03, 475.08W.04, 475.08W.05
VETO-156 | 475.08W.03
VETO-158 | 475.08W.05,475.08W.06
VETO-159 | 475.08W.05,475.08W.04
VETO-160 | 475.08W.06
VETO-161 | 475.08W.07
VETO-162 | 475.08W.05
VETO-163 | 475.08W.03,475.08W.02, 475.08W.04, 475.08W.05, 475.08W.06, 475.08W.07, 475.08W.08
VETO-164 | 475.08.07, 475.08.03, 475.08.04, 475.08.05, 475.08.06, 475.08.08

## Deleted Items
Risk | [6 empty] | Post-mitigation | [5 empty] | Details | [5 empty] | Risk Contingency | [5 empty] | NOTES:
ID | DocDb # | Type | Title | Date of Risk | Mitigation Cost (included in plan) | Category | Probability | Schedule-Delays Level 3 Milestone or Project Critical Path by X Days | Cost | Technical | ESH&Q | Score | Owner | Point estimate (cost k$) | Point Estimate (sched-days) | Point estimate (prob) | EXPECTATION VALUE IN k$ | EXPECTATION VALUE IN Days | Prob Range |  | Prob RMS | 85% CL | 90% CL | 95%CL
SOL-157 | 4225 | Threat | PS conductor first article does not meet specifications | FY15-FY16 | 400000 | Same as Sol-172 | M | VH | VH | M | N | 40 | M. Lamm | 2000000 | 250 | 25% | 500000 | 62.5 | 25% | 75% | 14.43% | 1006 | 1046.6667 | 1106.6667
SOL-066 | 3367 | Threat | Critical path delayed due to solenoid schedule delay. | FY18-FY20 | 20000 | should be eliminated since it is a global catch all that we now break into more detail | M | H | VH | N | N | 40 | M. Lamm | 1384383 | 200 | 50% | 692191.5 | 100 | 25% | 75% | 14.43% | 811.7099 | 839.859 | 881.3905
SOL-080 | 3372 | Threat | Insufficient testing of DS and/or PS at Vendor | FY18-FY20 | 50000 | remove, it is part of the new analysis | L | VH | VH | N | N | 24 | M. Lamm | 2000000 | 200 | 10% | 200000 | 20 | 10% | 25% | 4.33% | 351.8 | 364 | 382

## Chart
Low | 30
Medium | 25
High | 13
Retired | 36
Realized Opportunities | 8

## Sheet2
Risk | [6 empty] | Post-mitigation | [11 empty] | Risk Contingency $ |  |  |  |  | NOTES:
Risk ID | Risk Form DocDb # | Type | Title | Date of Risk | Mitigation Cost (Included in baseline) | Category | Probability | Schedule-Delays Level 3 Milestone or Project Critical Path by X Days | Cost | Technical | ESH&Q | Score | Owner | Point estimate (cost k$) | Point Estimate (sched-days) | Point estimate (prob) | EXPECTATION VALUE IN k$ | EXPECTATION VALUE IN Days | Prob Range |  | Prob RMS | 80%CL
ACCEL-011 | 3328 | Threat | Inadequate AD Engineering Resources | FY15-FY19 |  | Current Risk | M | L | N | N | N | L | Ron Ray | 75000 | 60 | 25% | 18750 | 15 | 25% | 75% | 14.43% | 36.5101
ACCEL-020 | 3333 | Threat | Cannot use TLMs to control beam losses. | FY15-FY16 |  | Current Risk | VL | N | VH | N | N | H | T. Leveling | 2000000 |  | 2% | 40000 | 0 | 0% | 10% | 2.887% | 108.054
ACCEL-200 | 4589 | Threat | Need to add new power supplies to the beam line. | FY15-FY16 | 20000 | Current Risk | M | VL | H | VL | N | H | D. Still | 400000 | 20 | 60% | 240000 | 12 | 25% | 75% | 14.43% | 241.3873
ACCEL-201 | 4590 | Threat | Need to fabricate additional magnets to the beam line. | FY15-FY16 | 20000 | Current Risk | L | VL | M | VL | N | M | D. Still | 200000 | 20 | 20% | 40000 | 4 | 10% | 25% | 4.33% | 40.8748
ACCEL-202 | 4591 | Opportunity | Replace the Diagnostic Absorber dipole with an existing magnet | FY15-FY16 | 5000 | Current Risk | M | VL | M | VL | N | M | D. Still | -110000 | 20 | 50% | -55000 | 10 | 25% | 75% | 14.43% | -62.7148
ACCEL-203 | 4592 | Opportunity | Availability of spare sextupole magnets for use in Mu2e | FY15-FY16 |  | Current Risk | L | N | M | N | N | M | V.Nagaslaev | -166000 |  | 15% | -24900 | 0 | 10% | 25% | 4.33% | -31.1594
ACCEL-204 | 4593 | Threat | Need to add 2 more collimators to the Extinction section | FY15-FY16 |  | Current Risk | L | N | M | N | N | M | E.Prebys | 160000 |  | 10% | 16000 | 0 | 10% | 25% | 4.33% | 27.3665 | #REF!
CAL-148 | 3834 | Threat | Cannot develop UV-extended solid state photodetector that is blind to longer wavelengths | FY15 | 100000 | Current Risk | M | M | N | H | N | H | D. Hitlin | 0 | 40 | 50% |  | 20 | 25% | 75% |  | 0
PM-048 | 3350 | Threat | Significant injury or death associated with Mu2e construction/assembly. | FY15-FY20 | 25000 | Current Risk | VL | H | VH | N | VH | M | R. Ray | 1000000 | 260 | 1% | 10000 | 2.6 | 0% | 10% | 2.887% | 50.6937
SOL-155 | 3954 | Opportunity | Cryo Distribution Box Funded by Cryo AIP | FY15-FY17 |  | Current Risk | M | N | VH | N | N | H | M. Lamm | -2500000 |  | 50% | -1250000 | 0 | 25% | 75% | 14.43% | -1425.3375
SOL-205 | 5038 | Threat | TS Prototype Coil Module test failure | FY15 |  | Current Risk | L | L | M | N | N |  | M.Lamm | 100000 | 60 | 10% | 10000 | 6 | 10% | 25% | 4.33% | 17.1041 | #REF!
TRACK-091 | 3382 | Threat | Simulations indicate that tracker occupancy higher than expected | FY15-FY16 |  | Current Risk | VL | L | L | N | N | L | D.Brown | 50000 | 30 | 5% | 2500 | 1.5 | 0% | 10% | 2.887% | 3.2014
TRACK-092 | 3383 | Threat | Need to switch straw manufacturer | FY15-FY16 |  | Current Risk | L | H | VL | N | N | M | A. Mukherjee | 100000 | 250 | 5% | 5000 | 12.5 | 10% | 25% | 4.33% | 15.4374
TRACK-096 | 3385 | Threat | Detector support structure not sufficiently rigid or stable | FY15-FY17 | 62000 | Current Risk | L | N | M | M | N | M | A. Mukherjee | 100000 |  | 25% | 25000 | 0 | 10% | 25% | 4.33% | 22.1041
TRACK-104 | 3390 | Threat | Gain loss in tracker. | FY15-FY17 | 5000 | Current Risk | L | M | H | L | N | M | A. Mukherjee | 500000 | 40 | 10% | 50000 | 4 | 10% | 25% | 4.33% | 85.5203
TRACK-139 | 3392 | Threat | Mylar creep limits tracker lifetime | FY15-FY17 | 5000 | Current Risk | L | VL | VL | H | N | M | A. Mukherjee | 50000 | 30 | 10% | 5000 | 3 | 10% | 25% | 4.33% | 8.552
TRACK-166 | 4445 | Threat | High crosstalk | FY15-FY16 | 5000 | Current Risk | M | N | L | M | N | M | A. Mukherjee | 50000 | 0 | 25% | 12500 | 0 | 25% | 75% | 14.43% | 24.3401
TRACK-168 | 4447 | Opportunity | Drop in price of 3D printing | FY15-FY16 |  | Current Risk | M | N | M | N | N | M | A. Mukherjee | -100000 | 0 | 50% | -50000 | 0 | 25% | 75% | 14.43% | -57.0135
TRACK-169 | 4444 | Threat | Background levels >4x expectation necessitate additional Tracker stations | FY15-FY16 |  | Current Risk | M | N | VH | M | N | H | A. Mukherjee | 1000000 | 0 | 25% | 250000 | 0 | 25% | 75% | 14.43% | 486.8017 | 606.0474
TRIG-134 | 3397 | Opportunity | Lower cost commercial PCIe card for DTC. | FY15-FY19 |  | Current Risk | M | N | L | N | N | L | M. Bowden | -20000 |  | 25% | -5000 | 0 | 25% | 75% | 14.43% | -9.736
TRIG-135 | 3398 | Opportunity | Slow Controls development in common with other experiments. | FY15-FY19 |  | Current Risk | L | N | L | N | N | L | M. Bowden | -40000 |  | 10% | -4000 | 0 | 10% | 25% | 4.33% | -6.8416
TRIG-136 | 3399 | Opportunity | Efficient Calorimeter Trigger reduces online processing requirements. | FY15-FY19 |  | Current Risk | L | N | L | N | N | L | M. Bowden | -40000 |  | 10% | -4000 | 0 | 10% | 25% | 4.33% | -6.8416 | 439.261
VETO-122 | 3402 | Threat | Need to use inferior fibers | FY15-FY20 |  | Current Risk | L | N | L | VL | N | M | C. Dukes | 50000 |  | 20% | 10000 | 0 | 10% | 25% | 4.33% | 10.2187
VETO-159 | 4260 | Threat | Photoelectron yield does not meet requirements. | FY15 |  | Current Risk | L | N | L | N | N | L | C. Dukes | 150000 | 0 | 20% | 30000 | 0 | 10% | 25% | 4.33% | 30.6561
VETO-162 | 4259 | Opportunity | Photoelectron yield exceeds requirements. | FY15 |  | Current Risk | M | N | L | N | N | L | C. Dukes | -100000 | 0 | 50% | -50000 | 0 | 25% | 75% | 14.43% | -57.0135
VETO-163 | 4263 | Opportunity | Wider counters can be extruded that meet specifications. | FY15 |  | Current Risk | M | N | L | N | N | L | C. Dukes | -200000 | 0 | 50% | -100000 | 0 | 25% | 75% | 14.43% | -114.027
Note on D26: The photoelectron yield is less than expected. This would require a larger diameter fiber (and larger associated SiPM only in the case that a custom SiPM size is required).
Note on D27: The photoelectron yield is greater than expected due to the availability of SiPMs with higher PDEs. This would allow a smaller diameter fiber and perhaps a smaller SiPM to be used.
Note on D28: The gaps between counters are too large to allow the efficiency requirement to be met. The easiest way to mitigate this would be to fabricate wider counters, 6 cm to 7 cm, which allow wider gaps without adversely affecting the efficiency requirement. This would require minor redesigns to various components of the CRV, including items such as counter motherboards, modules, and the support structure. The increased cost would be offset by the smaller number of fibers, SiPMs, and front-end boards.