## Slide 1: DUNE Project Management Meeting
Outline:
System Reports:
      Far Detector Jim/Tim
      Near Detector Sanjib
      Prototypes Thomas
Management priorities Eric/Steve
      CD-3a Preparation Russ/Terri/Milind
      ProtoDUNE Reviews preparation
AOB

## Slide 2: Management Priorities
DUNE project team building
CD-3a (TB meeting 9/30, ARUP comments 10/9)
ProtoDUNE design/construction/organization, detector FDRs
Need “Lessons Learned” from 35-ton, develop more complete QA plans for ProtoDUNE and DUNE
Identify financial and personnel synergies with SBN
Engage international partners

## Slide 3: Near term schedule
8/20/2015 |  | SBND-DUNE Cold Electronics meeting
8/31/2015 |  | Collaboration meeting, FNAL; SBND-DUNE meeting
9/7/2015 |  | Engineering meeting #1, BNL
9/14/2015 |  | 9/15 DUNE/SBND PD electronics, Yale visit 9/18
9/28/2015 |  | TechBoard 9/30: (grounding, DAQ, Control Room)
10/5/2015 |  | FSCF Prel. Design comments; FSCF DUNE meeting 10/9
10/12/2015 |  | Dir.Rev. talks posted; Nova/MINOS visit 10/15
10/19/2015 |  | SPSC meeting (CERN, 10/20-21)
10/26/2015 |  | Dir.Rev. CD-3a SURF (10/27-29); NNN15 SBU 10/28-31
11/9/2015 |  | Engineering meeting #2, CERN
11/16/2015 |  | SBN Director's Review, FNAL
11/30/2015 |  | CD-3a 12/2-4; protoDUNE Cryostat review, FNAL, 12/7-8
12/7/2015 |  | Cold Electronics ASIC design review
1/11/2016 |  | Collaboration meeting (UTA 1/12-15 LBNC 1/11)