## Slide 1: Close-out Report LArIAT Operational Readiness Review
D. Glenzinski
for the Review Committee
14 October, 2015

## Slide 2: Introduction
The committee thanks the LArIAT collaboration for their very nice presentations and their prompt replies to our questions.
The committee thanks Pushpa Bhat, Steve Geer, and Crae Tate for all their help in preparing for and running the review in such an organized manner.
LArIAT is to be congratulated on their rapid commissioning and successful Run 1 data taking.

## Slide 3: Introduction
The committee believes that LArIAT is in a good position to capitalize on Run 2 and deliver on many of its physics goals.
The committee is impressed with the organization, professionalism, and enthusiasm of the LArIAT collaboration.
The committee recognizes that LArIAT sits in a bit of a grey area between a test-beam and fully formalized experiment.
It is the impression of the committee that LArIAT has a lot of work to do over the coming several months and faces competition for resources.

## Slide 4: Question 1
Is there a completed Experiment Operations Plan (EOP) document? The document should include (a) a description of operations tasks and how they will be covered, (b) ES&H activities and how they will be managed, (c) organization charts showing the management structure for the experiment and how it interfaces with the laboratory, (d) the model for data processing and analysis including the budget and effort required, (e) a list of the identified resources available, and (f) a description of the roles and responsibilities of each institution together with a list of the support required by each institution from the funding agencies.

## Slide 5: Question 1
Findings
  There is an EOP document dated October 1, 2015 with 22 pages that includes an appropriately detailed discussion of most of the required aspects.
Is there a completed Experiment Operations Plan (EOP) document?
Yes

## Slide 6: Question 1
Comments
  (a) EOP document include brief description of the operations plan, while no detailed information about resources required for Run II is provided.
  (b) There is no information about ES&H activities or how they will be managed in the EOP
  (c) There is the collaboration organizational chart provided in the EOP and documents on TSW exist. The chart provided is for Run I and it is not clear who will play some of the roles for Run II. While TSW with computing divisions is recent, the test beam TSW is old (early 2013) and does not fully represent current status of the activities
  (d) While analysis of the Run I data is actively progressing EOP does not include model for the data processing and analysis and there is no information about budget or efforts required
  (e) The list of the identified resources from the collaboration groups is available in EOP
  (f) There is a list of resources collaboration groups provide in the EOP, while EOP contains no information on the resources required to operate the experiment, including data analysis. EOP also does not contain information on support required from the funding agencies

## Slide 7: Question 1
Recommendations
  The EOP should be updated to include a more detailed discussion of the ESH organization, functional roles, and personnel.
  In consultation with Program Planning, the EOP should be updated to address the other deficiencies identified in the Comments above.

## Slide 8: Question 2
Has it been demonstrated that the detector is ready for physics-quality data taking? If not, what actions are required to make the detector ready? Is there a clear plan for monitoring the data quality and has the associated infrastructure been tested? If not, what actions are required to adequately monitor the data quality?

## Slide 9: Question 2
Findings
  The LArIAT beamline detectors were commissioned in a 2w run in August 2014.
  The full suite of LArIAT detectors, including the TPC, were commissioned and took 6 weeks of high quality data from May-July 2015 (Run-1).
  Online and Offline DQ tools were used to monitor data quality and Ar purity during Run-1.
  Preliminary results were shown using Run-1 data from the MWPC, TOF, Halo Veto, TPC, and TPC-LC systems.
  There is a short list of detector improvements for Run-2, including some to the TPC, which has been disassembled.
  For a limited number of detector components there are no spares.

## Slide 10: Question 2
Has it been demonstrated that the detector is ready for physics-quality data taking? If not, what actions are required to make the detector ready? Is there a clear plan for monitoring the data quality and has the associated infrastructure been tested? If not, what actions are required to adequately monitor the data quality?
The LArIAT detectors took physics quality data in 2015. Assuming a smooth reassembly and commissioning, they will be ready for physics-quality data taking in 2016. A clear monitoring and DQ plan exists and the required tools were successfully employed in 2015.

## Slide 11: Question 2
Comments
  Prior to Run-2 implement the Aerogel Cerenkov reconstruction to verify its physics performance for low momentum muon/pion separation.
Recommendations
  For components that have no spares, either identify tenable backup plans or work with ND to purchase the required components.
  Develop a prioritized plan in preparation for Run-2. Identify the people to do the work. Integrate with the Run-1 analysis plans and other competition for resources. Understand your fallback positions.

## Slide 12: Question 3
Is there a well-understood run plan for FY16, consistent with accelerator schedule and performance? Have adequate resources from the laboratory and the collaboration been identified for an efficient and safe running of the experiment and for maintenance of the detector, and is it clear who is responsible for what?

## Slide 13: Question 3
Findings
  The Run II goal is to collect 6 x the statistics as Run-I in a 10-14 week period. While a comprehensive list of physics goals exists, the detailed beam settings for Run-2 will be fleshed out only after analyzing data from Run-1.
  A few repairs/improvements are needed before Run-2. Some of the people involved in the detector maintenance are also analyzing Run-I data.
  The current FNAL accelerator schedule accommodates sufficient beam to LArIAT from mid-February to October of 2016 with a summer accelerator down period.

## Slide 14: Question 3
Findings
  The EOP includes an org chart that specifies a lead person for each of the detector subsystems, the trigger, and DAQ. It also specifies an Accelerator liason.
  The EOP includes sections that summarize the responsibilities of the relevant FNAL divisions as well as a table that specifies institutional responsibility for the detector subsystems.
  The addition of some steel in the upstream portion of the LArIAT beamline could significantly reduce beam halo at the detector, resulting in a significantly improved beam quality.

## Slide 15: Question 3
Is there a well-understood run plan for FY16, consistent with accelerator schedule and performance? Have adequate resources from the laboratory and the collaboration been identified for an efficient and safe running of the experiment and for maintenance of the detector, and is it clear who is responsible for what?
The 2016 goals are to collect 6x the statistics as 2015. A comprehensive list of physics goals exists but a detailed run plan will be developed only after analyzing data from Run 1. Most the required resources have been identified but a shortfall in Run Coordinator needs to be addressed. It may be prudent to formalize laboratory commitments. Responsibilities are clearly specified.

## Slide 16: Question 3
Comments
  Since the beam settings for Run-II are informed by the Run-I analysis, it is critical to finish the Run-I analysis in a timely fashion.
  In order to collect 6x the statistics in a 10-14 week run, the accelerator duty cycle, beam quality and LArIAT data collection efficiencies must collectively provide a factor of 3 or 4 improvement.
  Some LArIAT collaborators are working on detector improvements and analysis simultaneously. Prioritizing tasks is paramount for the success of Run-II, however we note that, for the most part, the improvements are small and not time-consuming. An exception is for the cryo system modifications, which are projected to take 4-6w and if they are not done will have no physics impact. However, having a schedule for all the detector work will help the collaboration prioritize tasks and identify resources.
  LArIAT and MicroBooNe experiments share personnel and close communication will be critical during simultaneous operations of LArIAT and MicroBooNe to ensure resource demand conflicts are understood well in advance of a crisis.
  The TSW for LArIAT and the Test Beam Facility details the FNAL and non-FNAL responsibilities for the experiment, however there is no mention of the Neutrino Division in it as it didn’t exist at the time.

## Slide 17: Question 3
Recommendations
  A clear statement of run time and beam needs for 2016 should be made when Run I analysis is far enough along. This includes developing an understanding of the tuning of the beam/beamline element parameters to optimize Run-II operations based on experience from Run-I operations and physics priorities.
  The shielding to suppress beam halo background appears to be critical to the efficient collection of the required statistics. This should be actively pursued for Run-2.
  We encourage LArIAT to work within their collaboration and Fermilab to identify the resource short fall for Run Coordinator. We note the Fermilab Neutrino Division is now a major stakeholder in LArIAT results and should be part of resource planning.

## Slide 18: Question 4
Are there robust plans for data processing and data analysis? Have adequate resources from the laboratory and the collaboration been identified for data analysis to meet these goals?

## Slide 19: Question 4
Findings
  Good progress has been demonstrated with the preliminary analysis of Michel electrons from cosmic rays and the initial analysis of pion-argon cross sections.
  The collaboration has an enumeration of analysis topics that different institutions are interested in or involved in.
  The collaboration has identified the need for centralized data processing and Monte Carlo production to support their analysis activities.
  They have identified a group of four individuals (1 senior scientist, 3 post doctoral researchers) who will carry out the data processing activities for the current (Run 1) dataset.
  The scope of the data processing/reprocessing efforts have been partially demonstrated by reprocessing of the cosmic ray data from 2 months of running. Using current resources this effort took approximately 1 week of calendar time.
  The estimated size of the raw LArIAT dataset for a 12-14 week run is ~10 TB.

## Slide 20: Question 4
Question: Are there robust plans for data processing and data analysis? Have adequate resources from the laboratory and the collaboration been identified for data analysis to meet these goals?
Yes, good progress has been made in establishing a robust data processing and analysis plan. The data reprocessing plan seems reasonable. The resources are quite modest and appear to be adequate.

## Slide 21: Question 4
Comments
  The number of studies/analysis projects that were enumerated along with their institutional involvement are large in number when compared to the size of the collaboration. The impact of these projects to the primary analysis efforts should be understood, especially with respect to decisions that must be made regarding the Run-2 data taking plans.
  The Monte Carlo effort needs to be coordinated across physics groups. Additional simulation FTE levels and high priority simulation samples need to be identified.

## Slide 22: Question 4
Recommendations
  The experiment should formally measure the resources required to reconstruct event/spill data in terms of computation time, event sizes, inflation factors, etc… The experiment should project their resource requirements based on the current Run-I data and projected Run-2 data assuming 6x the current statistics is collected.

## Slide 23: Question 5
Are there clear goals set for reporting and publishing the results from the experiment in a timely fashion?

## Slide 24: Question 5
Findings
  The LArIAT collaboration has identified a set of physics goals that include scattering cross sections of pions and kaons with argon, discrimination between electron and photon initiated showers, investigation of recombination effects, energy calibration of charge and light measurements and validation of GEANT4.
  LArIAT has identified a short list of “Fast-track” analyses and “Foundational” analyses that they are pursuing at high priority.
  LArIAT’s goal is to publish within 6 months of the end of Run-1 data taking. They are aiming to have a publication quality pion-argon scattering cross section result by January 2016.
  The preparations for Run-2 are also needed by early 2016.
  The LArIAT collaboration is discussing their internal approval procedures.

## Slide 25: Question 5
Are there clear goals set for reporting and publishing the results from the experiment in a timely fashion?
LArIAT has established a clear set of reporting and publishing goals in the near term using Run-1 data. While it appears that fast-track analyses will be ready for early 2016, it seems unlikely that the full suite of goals will be completed within 6 months.

## Slide 26: Question 5
Comments
  Establish realistic publication goals and priorities for the Run-1 data set. Identify people to do the work. Integrate with the Run 2 preparation plans and other competition for resources.
Recommendations
  Finalize the internal approval procedures to ensure expediency without compromising quality.
  Develop a plan to ensure a strong showing at the LAr Workshop in January 2016.

## Slide 27: Question 6
Does the proposed scope and run plan serve the purpose of the neutrino community? Does the committee recommend further actions to ensure full exploitation of the LArIAT program?

## Slide 28: Question 6
Findings
  The amount of data that are required to achieve the stated physics sensitivities of the individual analyses have been determined to be 6x the Run-I physics data.
  A prioritized list of physics goals for Run-II was presented.
  There is significant overlap in the personnel who are on LArIAT and who are on other experiments within the neutrino community.
  There is a strong demand in the LAr community for an R&D facility in which to test a wide variety of detector and analysis ideas that might affect the design and optimization of future experiments.

## Slide 29: Question 6
Question: Does the proposed scope and run plan serve the purpose of the neutrino community? Does the committee recommend further actions to ensure full exploitation of the LArIAT program?
Yes. Many of the presented goals appear consistent with the needs of the neutrino community, but the degree to which these will be addressed is not completely clear. This issue will be addressed at the proposed January LAr workshop. The 2016 run will not address the full list of possible studies. There needs to be a coordinated effort to prioritize and address the remaining items.

## Slide 30: Question 6
Comments
  Efforts must be made to develop a run plan that directly addresses the highest priority goals of the experiment while minimizing the risks associated with delays or set backs in the analysis efforts.
  LArIAT should understand the pros and cons with having personnel deeply involved in LAr efforts outside of the LArIAT program.

## Slide 31: Question 6
Recommendations
  Participate in the January 2016 LAr Workshop.
  The relevant stakeholders in the LAr community in consultation with the laboratory and the funding agencies should develop a prioritized list of R&D studies of importance to future LAr-based experiments. This list should be mapped onto planned LAr facilities/experiments. There should be an evaluation of the need for an LAr R&D facility at MCenter (or similar) beyond 2016.

## Slide 32: Closing
These will be posted to Indico after any required fixes.
Committee will develop a draft of the written report by 23 October.
  Will be shared with Spokespersons for fact checking.
Final report will be issued by 30 October.
The recommendations will be followed by Program Planning via the EMG meetings.
Thank you!