## Slide 1: PIP-II Overview: Goals, Status, and Strategy
Steve Holmes
PIP-II Collaboration Meeting
9 November 2015

## Slide 2: Outline
Update since Last Meeting (June 2014)
PIP-II Status and Strategy
FY16-17 Goals and Budgets
Meeting Goals and Agenda
Our websites:
http://pip2.fnal.gov/
(See Collaboration Information for useful links)
Meeting website:
https://indico.fnal.gov/conferenceDisplay.py?confId=10586

## Slide 3: News Since June (2014)
Reference Design Report (RDR)
  Released in May in advance of the DOE Review
  http://pip2-docdb.fnal.gov/cgi-bin/ShowDocument?docid=1
PIP-II Machine Advisory Committee (P2MAC)
  Met in March 2015 (3rd meeting)
  Review of Reference Design and associated R&D Program
  https://indico.fnal.gov/categoryDisplay.py?categId=366
Notes: Test
3

## Slide 4: News Since June (2014)
DOE Independent Review of PIP-II/June 16-17, 2015
  https://indico.fnal.gov/conferenceDisplay.py?confId=9939
  Review based on:
    RDR
    Cost Estimate with offsets for international contributions
    Construction period FY2019-FY2023
  Proposed cost range: $465-$695M
    (cost to DOE after international contributions)
  Review committee report:
    “The proposed concept is well advanced, beyond what is required at this stage…most likely will satisfy the P5 recommendation”
    “The presented cost range appears reasonable. For the most part, the scheduling strategy fits with other major projects at FNAL.”
    “After the funding profile for the higher end of the TPC of $695M was established, the Committee judged that the project is ready to proceed to CD-0…”
Notes: Test
4

## Slide 5: News Since June (2014)
CD-0
  Subsequent to the review the upper end of the cost range was lowered to $650M
    We provided a funding profile consistent with this number
  Mission Need Statement approved by the Office of Science
  ESAAB scheduled for November 12
PXIE
  LEBT beam characterized
  and meets requirements
  RFQ has arrived and is
  under vacuum at PXIE!
  MEBT magnets received
  from BARC
Notes: Test
5

## Slide 6: News Since June (2014)
SRF
  Two SSR1 cavities
  received from IUAC
  SSR1 dressed cavity
  successfully tested
  Lab 2 renovation going
  great guns
  Preparing for SSR1
  string assembly in FY16
  Preparing for HWR string assembly in FY16 (ANL)
  Significant advances in high-Q0 and resonance control programs
Indian Collaboration
  “Annex I” signed by DOE and DAE
  Project Plan for R&D phase signed (DOE and DAE)
  7 Indian engineers at Fermilab for 2-year residencies
    650 MHz C&CM, LLRF, Cryo, Accel Phys (PXIE)
Notes: Test
6

## Slide 7: News Since June (2014)
Personnel Changes
  New Technical Division Head: Sergey Belomestnykh
    Replaces Hasan Padamsee (retired)
  SRF Program Management Team:
    TD PIP-II Coordinator: Allan Rowe
    325 MHz cavities and cryomodules: Leonardo Ristori
    650 MHz cavities and cryomodules: Tom Nicol
    SRF Development Department: Slava Yakovlev
      Cavity Performance and Testing: Anna Grasselino
      Resonance Control: Yuriy Pischalnikov
Notes: Test
7

## Slide 8: PIP-II Status and Strategy
Reference Design Report describes:
  An 800-MeV superconducting linac, constructed of CW-capable components, operated initially in pulsed mode
  Modifications to Booster/Recycler/Main Injector to accommodate higher intensities
    New Booster injection region to accept 800-MeV beam
    Upgrades to Booster damper and collimator systems
    LCW system upgrades (reliability)
    Recycler RF upgrade for slip-stacking at 0.7 sec cycle time
    MI RF power upgrade
    MI gt-jump system
  Increase of Booster repetition rate to 20 Hz
    Maintain 1 MW down to 60 GeV or,
    Provide factor of 2.5 increase in power to 8 GeV program

## Slide 9: PIP-II Status and Strategy/Site Layout

## Slide 10: PIP-II Status and Strategy/Performance Goals
Performance Parameter | PIP | PIP-II | 
Linac Beam Energy | 400 | 800 | MeV
Linac Beam Current | 25 | 2 | mA
Linac Beam Pulse Length | 0.03 | 0.5 | msec
Linac Pulse Repetition Rate | 15 | 20 | Hz
Linac Beam Power to Booster | 4 | 18 | kW
Linac Beam Power Capability (@>10% Duty Factor) | 4 | ~200 | kW
Mu2e Upgrade Potential (800 MeV) | NA | >100 | kW
Booster Protons per Pulse | 4.3×1012 | 6.5×1012 | 
Booster Pulse Repetition Rate | 15 | 20 | Hz
Booster Beam Power @ 8 GeV | 80 | 160 | kW
Beam Power to 8 GeV Program (max) | 32 | 80 | kW
Main Injector Protons per Pulse | 4.9×1013 | 7.6×1013 | 
Main Injector Cycle Time @ 60-120 GeV | 1.33* | 0.7-1.2 | sec
LBNF Beam Power @ 60-120 GeV | 0.7* | 1.0-1.2 | MW
LBNF Upgrade Potential @ 60-120 GeV | NA | >2 | MW
*NOvA operations at 120 GeV

## Slide 11: PIP-II Status and Strategy/Technology Map
Section | Freq | Energy (MeV) | Cav/mag/CM | Type
RFQ | 162.5 | 0.03-2.1 |  | 
HWR (opt=0.11) | 162.5 | 2.1-10.3 | 8/8/1 | HWR, solenoid
SSR1 (opt=0.22) | 325 | 10.3-35 | 16/8/ 2 | SSR, solenoid
SSR2 (opt=0.47) | 325 | 35-185 | 35/21/7 | SSR, solenoid
LB 650 (g=0.61) | 650 | 185-500 | 33/22/11 | 5-cell elliptical, doublet*
HB 650 (g=0.92) | 650 | 500-800 | 24/8/4 | 5-cell elliptical, doublet*
*Warm doublets external to cryomodules All components CW-capable |  |  |  | 
Notes: Multiple corrections to the table and picture

## Slide 12: PIP-II Strategy
PIP-II will be executed as a DOE 413.3b project
Strategy
  Develop/evolve concepts aligned with community needs
  Undertake R&D targeting major technical/cost risk elements
  RDR defines concept for meeting community requirements, and provides context for R&D
  Coordinate with other Fermilab projects and programs
Status
  PIP-II endorsed by P5 as a key element in the U.S. neutrino program
  R&D program underway
  P2MAC review of RDR and R&D program (March)
  Strong collaboration with Indian and U.S. laboratories
    Possible collaboration with Europe
  Project Office established

## Slide 13: Project Strategy/R&D
Goal is to mitigate risk: Technical/cost/schedule
Technical Risks
  Front End
    Delivery of beam with required characteristics, quality, and reliability
  Operate (high Q0) SC Linac in pulsed mode at low current
    Primary issue is resonance control in cavities
  Booster/Recycler/Main Injector beam intensity
    50% per pulse increase over current operations
    Longitudinal emittance from Booster for slip-stacking
    Transition crossing
    Beam loss/activation
  Develop requisite capabilities of international partners and vendors
Cost Risks
  Superconducting RF
    Cavities, cryomodules, RF sources represent a major portion of construction costs
Goal: Be prepared for a construction start in 2019
  R&D deliverables milestones established

## Slide 14: Project Strategy/PXIE
Collaborators
ANL: HWR
LBNL:LEBT, RFQ
SNS: LEBT
BARC: MEBT
IUAC: SSR1
PXIE will address the address/measure the following:
  LEBT pre-chopping: Demonstrated
  Vacuum management in the LEBT/RFQ region: Demonstrated
  Validation of chopper performance
    Bunch extinction, effective emittance growth
  MEBT beam absorber
    Reliability and lifetime
  MEBT vacuum management
  CW operation of HWR
    Degradation of cavity performance
    Optimal distance to 10 kW absorber
  Operation of SSR with beam
    CW and pulsed operation
    Resonance control and LFD compensation in pulsed operations
  Emittance preservation and beam halo formation through the front end
40 m, ~25 MeV
30 keV
RFQ
MEBT
HWR
SSR1
HEBT
LEBT
2.1 MeV
10 MeV
25 MeV
2017
2016
2015
Now
2018

## Slide 15: Project Strategy/SRF Development Status (6/1/15)
Legend: green = done, yellow = in process

## Slide 16: Project Strategy/Preliminary Schedule

## Slide 17: FY2016-17 Goals
Fill out project organization and achieve CD-1
  CDR, alternatives study, cost range, RLS
  Other supporting documentation
Initiate work toward CD-2
  Detailed design
  Site characterization
  NEPA documentation and permitting
  EVMS implementation
Advance PXIE
  Commission RFQ with beam and characterize in MEBT
  Complete MEBT installation
  Deliver HWR and SSR1 prototype cryomodules
  Complete cryogenic infrastructure
Complete HB650 cryomodule design (w/ India) and initiate procurements
Integrate seven Indian engineers at Fermilab for two year residencies

## Slide 18: FY2016-17 Budgets
FY2016 $19.5M
  Budget allocations specified at L3 of WBS
Adjustments required to meet budget guidance:
Deliverable | Old Date | New Date
PXIE warm: beam out of MEBT-1 | Q2FY16 | Q4FY16
SSR1: Resonance control testing definitive results | Q4FY16 | Q4FY16
PXIE warm: beam to end of MEBT-2 | Q4FY16 | Q4FY16
PXIE warm: beam to end of final MEBT | Q4FY17 | Q4FY17
PXIE Cold: HWR CM and associated infrastructure (cryo, RF, power, etc.) | Q3FY17 | Q3FY17*
PXIE Cold: SSR1 CM and associated infrastructure (cryo, RF, power, etc.) | Q3FY17 | Q1FY18*
HB650 Dressed Cavities and associated infrastructure (HTS-2, rf) | Q3FY17 | Q4FY18
HM650 CM to CMTS | Q4FY18 | Q1FY20
CD-1 activities: CDR, Site Characterization, civil construction drawings | Q4FY16 | Q3FY17
* Requires augmented funding in FY2016

## Slide 19: FY2016-17 Budgets
FY2017 $19.5M
  Detailed budget plan does not yet exist
  Priority will be on completing elements in prior table scheduled for FY2017 and on getting to CD-1
  There will be slippage elsewhere
FY2018
  We have been advised that FY2018 will be: $22.0-25.0M

## Slide 20: Meeting Goals
Reorientation from Project X to PIP-II has a significant impact on the roles of the various collaborating institutions on PIP-II.
  We would like to use this meeting to facilitate the realignment of collaborator roles, in particular during the R&D phase of PIP-II.
Meeting Goals
  Review status of the R&D program
  Develop plan, including the role of collaborators, in the R&D program
Coverage
  PXIE
  SRF
  LLRF/resonance control
  RF sources
  Instrumentation
  Controls
  Cryogenic systems
  Booster/Recycler/Main Injector
We have organized three working groups to help achieve these goals

## Slide 21: Meeting Goals/Working Groups
Conveners are responsible for organizing their sessions. Each group should:
  Review, and modify as necessary, goals and deliverables for the R&D phase
  Develop a work plan that defines the sharing of responsibilities among the collaborators for the R&D phase
WG1: PXIE/P. Derwent, A. Shemyakin
Warm components
Integration of HWR and SSR1
Instrumentation
Controls
Experimental program
WG2: Superconducting Linac/S. Mishra, V. Yakovlev, F. Garcia
SSR1, SSR2
LB650, HB650
Test Stands: HTS-2, STC
LLRF/resonance control – joint with WG1
RF sources
Cryogenic systems
WG3: Rings/V. Lebedev, I. Kourbanis
Beam dynamics and modelling
Booster injection
RF systems
Collimation systems
Dampers
Transition crossing

## Slide 22: Collaboration Meeting Agenda
Monday, November 9
  Plenary Session: Overview 08:30-11:30
  Lunch
  WG-1: PXIE 12:30-17:00
    Floating Point (IARC, 3rd floor east)
  WG-2: SCLinac 12:30-18:00
    IARC Auditorium
  WG-3: Rings 12:30-17:30
    IARC 1W (IARC, 1st floor west)
  Afternoon break will be outside IARC Auditorium Wednesday, June 4
Tuesday, November 10 8:30-10:00
  WG-1
  WG-2
  WG-3
Adjourn 10:30
  https://indico.fnal.gov/conferenceDisplay.py?confId=10586

## Slide 23: Our Inspiration…
Hello Steve,
Do you have any idea whether there will be a PIP-II collaboration meeting this summer and, if yes, any guess when?
My daughter is planning her wedding in June and asks when it would be most convenient for me.

## Slide 24: Our Inspiration…
I don't think your daughter should be choosing a wedding date based on the PIP-II Collaboration Meeting!
In any event, I think it is unlikely we will have the meeting in June. July or August is more likely.
Cheers,
Steve

## Slide 25: Our Inspiration…
Steve,
She is aware of the power of science...