## Slide 1: PXIE Cryogenics
Mike White
PIP-II Collaboration Meeting
Nov. 9, 2015

## Slide 2: Overview
Show major cryogenic components
Discuss space constraints
Specification Outline
Installation Outline
Commissioning Outline

## Slide 3: PXIE Cave Area Cryo Components
Distribution Box (Existing)
Mycom Compressor Header (Future)
PXIE Transfer Line (Future)
CMTS Transfer Line
(Existing)
Kinney Pump Header (Existing)
HWR Cryomodule (Future)
SSR Cryomodule (Future)
Cavity Relief Vents (Future)

## Slide 4: Penetration into PXIE Cave
BEAM
East supplemental shielding installed early
Darker section of piping indicates prefabricated section craned into slot
Covering blocks (not shown) can be craned in over piping
Field weld locations are accessible

## Slide 5: Penetration into PXIE Cave
BEAM
Cryo distribution
Relief lines (2) and He Suction

## Slide 6: Penetration into PXIE Cave
BEAM
Does not affect design of roof layers
Significant bump-out to East of existing cave

## Slide 7: Space along East Wall
990 mm
758 mm

## Slide 8: Space along Ceiling
3200 mm (10’6”)
Edge of wall past HWR and SSR
Limited clearance for pulling U-tubes
Limited space for SSR 2K Relief System
Assume cryo takes up all this space

## Slide 9: HWR Ports

## Slide 10: HWR Connections to Distribution System
BEAM
U-tube
Pipe
Bayonet Can
Conceptual Cartoon

## Slide 11: SSR Connections to Distribution System
All SSR Bayonets
2K Relief
Conceptual Cartoon

## Slide 12: Valves and Instrumenation
Due to tight space constraints inside cave, as much as possible keep control valves, relief valves, expansion joints, and instrumentation in cans at these three locations

## Slide 13: Lines Available in PXIE Transfer Line Stub
There are no control valves for PXIE in the distribution box (all lines have direct path to refrigerator)
Number of valves required for PXIE is highly correlated with independence required from CMTS operations

## Slide 14: Conclusions on Space Constraints
Installation order of components is important
Walking along east wall of cave not practical
Tight spaces for welding
U-tube installation/removal may require removing roof
  U-tube may need to be lifted by crane after pulling to store elsewhere
  People likely have to stand on HWR lid
  HWR u-tubes heavy enough that several people required
Keep as many components as possible out of cave due to space limitation
  Counterpoint: It is also difficult to access points at elevation, since room for lifts in and around cave is almost nonexistent

## Slide 15: Specification Steps Outlined
Review current cryomodule FRS
Write overall TRS for distribution system
  Define allowable interdependence between PXIE and CMTS operations
  Define heat load measurement accuracy
  Cooldown constraints (fast, slow, either)
  Resolve any other missing or ambiguous specifications
Create key process documents
  PID
  Valve & Instrument list
  Define pipe sizes
Write TRS for vendor to supply major distribution system components
  Define allowable envelope
  Define interface locations
  Define support locations
  Schedule requirements
  Other standard specifications

## Slide 16: Installation Steps Outlined
Vendor supplied distribution system components
  Select vendor
  Ship FNAL-supplied components to vendor
  Design review
  Fabrication
  Testing
FNAL Mechanical (independent of vendor or cryomodule)
  Run cavity relief vent header into cave
  Run Mycom suction header into cave
  Install supports for transfer line & headers
  Prefab of U-tubes
  Install connection to Kinney vacuum pump?
FNAL Mechanical (dependent on vendor and/or cryomodule)
  Join transfer line sections
  Final welding of U-tubes
  Install cryomodule cavity reliefs & connect to relief vent header
  Connect all relief and vent ports to Mycom header
  Run pneumatic tubing for control valves

## Slide 17: Installation Steps Outlined
FNAL Electrical & Controls (independent of vendor or cryomodule)
  Prepare instrumentation and controls cabinets
  Install cabinets at CMTF
  Create ACNET variables & Synoptic pages
  Create control loops
  Input temperature sensor calibration data
FNAL Electrical & Controls (dependent on vendor and/or cryomodule)
  Run & terminate cables from cabinets to instrumentation & control valves

## Slide 18: Commissioning Steps Outlined
  Engineering documents (distribution system and cryomodule)
  Piping notes
  Vacuum Vessel notes
  Pressure Vessel notes (cryomodule only)
  ODH notes
  Cryogenic System Review notes
Testing
  Helium leak checks
  Pressure tests
  Electrical check-out
Operations
  U-tube installation/removal procedures
  Cooldown/Warmup guidelines