## Slide 1: Radiation Improvements Review – Executive Session
Ron Ray
Mu2e Project Manager
10/20/15

## Slide 2: Scope
The Radiation Safety subsystem is to design and implement radiation safety upgrades that are required to permit the operation of the muon campus with a beam power of 8 kW. The scope of work includes:
Design, fabrication, and implementation of an AP1 to Delivery Ring Total Loss Monitor (TLM) radiation safety system.
Design, fabrication, and implementation of the Delivery Ring radiation safety system upgrades, which includes a Delivery Ring TLM radiation safety system and in-tunnel shielding of known beam loss points.
Design, fabrication, and implementation of the external (M4) beamline radiation safety system, which includes M4 beamline safety system interlocks, M4 beamline TLM system, and M4 beamline in-tunnel shielding.
Design, fabrication, and implementation of the Mu2e proton target hall radiation safety interlock system.
ODH systems for the Mu2e building.
Deployment of Friskers, Wallflowers, and Air Monitors

## Slide 3: Charge
Is the scope of the Radiation Safety Improvements subproject adequate to meet the requirements of the Fermilab Radiological Controls Manual (FRCM)?
Is the design, fabrication, and implementation of the TLM systems for the AP1 to Delivery Ring, Delivery Ring, and M4 beam line technically sound and mature enough to be considered a final design? Are there any remaining issues that require attention prior to the fabrication and installation of TLM systems?
Is the design of the Electrical and Radiation Safety Systems for the Delivery Ring, M4 beam line, Production Solenoid Room, Transport Solenoid Room, and Detector Solenoid Room technically sound and mature enough to be considered a final design? Are there any remaining issues that require attention prior to the fabrication and installation of these systems?

## Slide 4: Charge
Is the design of the ODH systems for the Production Solenoid, Transport Solenoid, and Detector Solenoid rooms technically sound and mature enough to be considered a final design?
Is the plan to deploy Friskers, Wallflowers, and Air Monitors technically sound and mature enough to be considered a final design?
Has the design of in-tunnel shielding systems been adequately reviewed? Can these designs be considered final designs?
MARS simulations have recently been completed for the Production Solenoid room shielding berm. Supplemental concrete and steel shielding masses have been included as a result of the latest simulations. Is the final simulation result compliant with the requirements of the FRCM? Was the final simulation completed using acceptable modeling techniques?
The committee is requested to submit a report containing its answers to the charge questions and its recommendations to the Mu2e Accelerator project manager within two weeks after the conclusion of the review.

## Slide 5: Schedule
Mu2e received CD-2 in March 2015.
CD-3c scheduled for next summer
  Timing of CD-3c is based on when the solenoids are ready, but other components have to be mature on that timescale as well.
Installation of beamline components from FY17-FY20
Commissioning in FY20
  Radiation systems must be in place in time for commissioning
  Commissioning begins with beam delivered to the diagnostic absorber
  Commissioning to the Mu2e detector will start at low power.

## Slide 6
Schedule
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
FY15 FY16 FY17 FY18 FY19 FY20 FY21 FY22
CD-2/3b
Project Complete
Detector Construction
Solenoid Infrastructure
PS Fabrication and QA
PS/DS Final Design
CD-3c
Fabricate and QA Superconductor
Detector Hall Construction
CD-4
22 months of float
Fabricate and QA TS Modules, Assemble TS
DS Fabrication and QA
PS Installation
Critical Path
KPPs Satisfied
TS Installation
Solenoid Commissioning
DS Installation
Cryo and Power hookup
Cosmic Ray System Test
Accelerator and Beamline Construction
PO issued for TS Module Fabrication

## Slide 7
Thank you for your help this week! Peer review is a key to successful projects.