## Slide 1
Target Summary/Status
Chris Densham STFC/RAL
Mu2e Target, Remote Handling, and Heat & Radiation Shield Review Nov 16-18 2015

## Slide 2: Schedule for Target Program
Contract 3 Phase 1
Design & Test
Contract 3 Phase 2
Design & Test
Emissivity measurements
Pulsed lifetime test
Silicon-Carbide coatings
Vacuum/leak test
Helium cooled target concept
Intermediate report
Alternative coating technology
Creep/sag tests
Creep/sag tests
Prototype springs
Optimise + prototype target mount system
Final Report

## Slide 3: Target Research Status (I)
 Emissivity measurements for tungsten
  Operating temperature determined for plain target at 7.7 kW beam power ✔
  Micro-fins enhance emissivity (lower T) but questions over fatigue life ✔
 High T pulsed fatigue performance of tungsten test samples
  Sufficient for > 1 year lifetime ✔
  Encouraging data at increased pulse intensity
 Sag/creep tests
  Tests underway
  Available data does not cause concern
  If there is a problem, design can be modified e.g. support from Airy points
 Radiation damage of tungsten – high DPA rate, He, H2 production
  c.10x faster rate than in ISIS targets, higher T may be better due to high diffusion
 ‘Bicycle’ wheel target concept
  Simple installation into HRS/ easy remote handling ✔
  Spoke manufacture ✔
  Spoke tensioning system (2 options) ✔

## Slide 4: Target Research Status (II)
 Operating conditions of radiation cooled target vs requirements
  Vacuum level of 1e-5 torr expected by vacuum group
  Vacuum level of 1e-6 mbar known to result in minimal tungsten oxidation
  Uncertainty on target lifetime for actual operating conditions
 Oxidation -> contamination of HRS
  Target coating to mitigate oxidation
   SiC: strong, high emissivity coating (lower T), performs well at 1e-7 mbar
     Coating rapidly degrades at 1e-4 mbar, not suitable as anti-oxidation coating
   Ir coating: much less reactive than W at high temperatures
    few µm layer achieved by sputter coating
    c.100 µm required for evaporation/diffusion tolerance
      CVD being investigated, promising
 Backup options: convective cooling to eliminate oxidation
  Water or helium feasible
  ‘Back door’ kept open to incorporate cooling system

## Slide 5: Helium cooled target
proton beam : 8GeV 8kW 1mm sigma
heat load = 588W
helium mass flow = 1g/s
max helium velocity = 356m/s
pressure drop = 0.2bar
max tungsten temperature = 368°C
temperature variation per pulse = 58°C
max von Mises stress = 10MPa
stress fluctuation = 6MPa

## Slide 6: Target research status (III) Convectively cooled back-up
 | Radiation cooled | Water cooled | Helium cooled
Material | Tungsten Graphite (low yield) | Gold Ta clad tungsten | Tungsten
Physics (yield) |  |  c.5% pion loss |  c.1% pion loss
Chemistry |  High temperature, poor vacuum |  Some chemistry (W/H2O) |  No chemistry
Operating temperature | High  W properties  Graphite | Low  W properties  Au properties | Low  W properties
Ease of remote handling |  |  Water connections, pipes |  Helium connections, pipes
Plant issues |  None |  Known tech. |  Complexity, price
Diagnostics |  None? | ΔT, activity | ΔT, activity
Contamination /activation |  Ox. in poor vacuum  OK in good vacuum |  Water activation  Issues with leaks |  Low activation  Low leak concerns
Experience, data |  Little data | Data on Ta clad W  Little gold data |  Data on pure W
Upgradeability |  No |  Yes |  Yes

## Slide 7: Radiation cooled target schedule (2 year float)

## Slide 8: Radiation cooled target schedule (2 year float)
Contract 4
Full Target Prototype
Contract 5
Manufacture 1st Production Target
Detail Design
Manufacture Prototype Target
Intermediate Report
Thermal Testing of prototype
Final Report
Manufacture And Assemble Parts
Ship to FNAL
Mid FY 2018