## Slide 1: LCLS-II 3.9 GHz Cryomodule PDR
Camille M Ginsburg (FNAL)
  FNAL LCLS-II Deputy Team Lead – Cryomodules
  Cryomodule Control Account Manager
19 November 2015
Project Management Topics

## Slide 2: Review Committee
Ed Daly (JLab) - Chair Elmar Vogel (DESY) (Remote) Jacek Sekutowicz (DESY) (Remote) Paolo Pierini (INFN/DESY) Cho-Kuen Ng (SLAC)

## Slide 3: Outline: 3.9 GHz Cryomodule Project
Scope of work
Organization and staffing
Schedule and cost
Risks
Cryomodule reviews, prior and planned
This review

## Slide 4: Fermilab cryomodules: lead-in to LCLS-II
FNAL has been working with XFEL/ILC/TESLA-type designs for ~10 years in ILC context
    Two 1.3 GHz cryomodules built and tested: CM1 and CM2
      80 9-cell cavities procured
      Many 100’s bare 9-cell cavity tests (vertical test)
      Many 10’s dressed 9-cell cavity tests (horizontal test)
    One 3.9 GHz cryomodule was built for DESY/FLASH; in operation
For LCLS-II, the 1.3 GHz has its final design review in May
  3.9 GHz builds on this experience to the extent possible
FNAL responsible for the 3.9 GHz CM design, procurement, fabrication and test
The 3.9 GHz effort follows that of 1.3 GHz for efficiency

## Slide 5: XFEL CM Modifications for LCLS-II (components/CM)
Component design – leverage existing designs optimally
  Cavities [Solyak/Grimm/Foley]
  Helium vessel [Grimm/Peterson/He/Solyak]
  HOM coupler, can, feedthrough [Solyak]
  Fundamental power coupler [Solyak]
  Magnetic shielding, Q0 [Grassellino]
  Tuner [Pishalnikov]
  BPM [Solyak]
  HOM absorber [Solyak]
  Cryo-mechanical design [Peterson]

## Slide 6: FNAL LCLS-II 3.9 GHz cryomodule team

## Slide 7
Four slides containing cost/schedule omitted

## Slide 8: FNAL Cryomodule Risks (in Risk Registry) (1/2)
CM/cavity performance/schedule
Cavities do not achieve/sustain Q0 performance; heat loads underestimated [LCLS.CryoMod-005,016]
    Mitigation: Adequate testing; also see high-level cryo capacity management strategy
Prototype CM does not meet specification; redesign/rework req’d before prod [LCLS.CryoMod-014]
    Mitigation: Provide significant performance margin, build FNAL/JLab prototypes asap
Production CM fails test in QC step, e.g. leak tests, after shipping, or in test at CMTF, requiring disassembly, repair, and reassembly and test [LCLS.CryoMod-001]
    Mitigation: Include prototype CM’s at FNAL/JLab; 1st 3 production CM’s have longer duration to finalize assembly/QC procedures
  Tunnel remanent mag field too high; mag shielding inadequate to maintain Q0 [LCLS.CryoMod-019]
  Mitigation: Compensation magnetic coils on each cryomodule will be included in baseline
During transport FNAL-to-SLAC a CM is damaged, delaying CM delivery to SLAC [LCLS.CryoMod-010]
  Mitigation: Perform dry-runs under realistic conditions, investigate potential impacts, find alternate transport scheme(s)
Cryomodule production rate cannot meet schedule, delaying CD4 [LCLS.CryoMod-011]
  Mitigation: Prototype CM being built by both partner labs in FY15 for capability and redundancy

## Slide 9: FNAL Cryomodule Risks (in Risk Registry) (2/2)
Components performance/schedule
FPC’s have fab problems and/or are delayed; CM assembly delayed, causing cost/schedule growth [LCLS.Linac-004]
    Mitigation: Vendor qualification, extensive Q&A during fabrication effort. Plan early delivery.
FPCs fail during CM testing impacting CM production schedule and increasing cost to rework [LCLS.CryoMod-017]
  Mitigation: Procure SSAs for CW testing; develop CW FPC test plan & procedure by Oct.2015
Cavity tuner failures in prototype CM tests, tuner repair requires CM reass’y [LCLS.CryoMod-018]
  Mitigation: implement accelerated lifetime testing for tuner. Include tuner access ports in prototype CM to permit in situ tuner replacement
Management
New: Niobium import to cavity fabricators incurs duties
FNAL’s two ongoing SRF based efforts, LCLS II and PIP II (R&D stage), interfere [LCLS.PM-011]
  Mitigation: LCLS II is Fermilab’s highest priority; FNAL/SRF creating facility and skills redundancy; monitor resource allocation continually

## Slide 10: Past Reviews (1/2) – 1.3 GHz CM and/or 3.9 GHz CM
  LCLS-II Director’s CD-1 Review – 9-11.Dec. 2013
  LCLS-II DOE CD-1 Review – 4-6.Feb. 2014
  Prototype 1.3 GHz dressed cavity – 5. Apr. 2014
    Cavity, helium vessel, preliminary tuner
    https://indico.fnal.gov/conferenceDisplay.py?confId=8598
Prototype 1.3 GHz Cryomodule – 6.Jun. 2014
  CM cryomechanical issues
  https://indico.fnal.gov/conferenceDisplay.py?confId=8398
LCLS-II Cryogenic System Preliminary Design Review 13-15.Aug. 2014
LCLS-II DOE Status Review – 19-20.Aug.2014
Helium vessel procurement – 4.Nov 2014
  https://indico.fnal.gov/conferenceDisplay.py?confId=9247
GHRP and vacuum vessel (prototype CM) – 4. Dec. 2014
  https://indico.fnal.gov/conferenceDisplay.py?confId=9151
BPM and gate valve – 12.Dec. 2014
  https://indico.fnal.gov/conferenceDisplay.py?confId=9156
Notes: Timergali Khabiboulline, T. Nicol (chair), Leonardo Ristori, Ed Daly, J. Preble
Elvin Harms (chair), John Mammosser, Joel Fuerst, Tom Nicol, and Jerry Makara

## Slide 11: Past Reviews (2/2) – 1.3 GHz CM and/or 3.9 GHz CM
Prototype 1.3 GHz cryomodule 20-21.Jan. 2015 – Final Design
  https://indico.fnal.gov/conferenceDisplay.py?confId=9245
LCLS-II FAC Review at SLAC 5-6.Feb.2015
LCLS-II Director’s CD3B Review at SLAC 17-19.Feb.2015
LCLS-II DOE CD3B Review at SLAC 6-9.Apr.2015
1.3 GHz cryomodule cavity tuner 15.Apr. 2015 – Final Design
  https://indico.fnal.gov/conferenceDisplay.py?confId=9769
1.3 GHz cryomodule magnet 16.Apr. 2015 – Final Design
  https://indico.fnal.gov/conferenceDisplay.py?confId=9808
1.3 GHz Production CM Final Design Review May 12-14 2015
  https://indico.fnal.gov/conferenceDisplay.py?confId=9874
Today: 3.9 GHz CM Preliminary Design Review
Response to the one 3.9 GHz review recommendation next
Notes: Timergali Khabiboulline, T. Nicol (chair), Leonardo Ristori, Ed Daly, J. Preble
Elvin Harms (chair), John Mammosser, Joel Fuerst, Tom Nicol, and Jerry Makara

## Slide 12: Review recommendations for 3.9 GHz CM

## Slide 13: LCLS-II 3.9 GHz CM PDR Committee Charge
Evaluate preliminary 3.9 GHz CM design readiness to approve implementation, procurement, fabrication & installation activities.
Technical Scope
  Are all design specifications, requirements, performance, and interface documents identified and reviewed at PDR level? EH, TP
  Is design sufficiently mature and technically sound to meet performance specs EH, NS, CG, YP, MF, AG, TP, YH
    HOM, coupler heating, CM heat load NS, TP
    Chimney size for larger heat load TP, YH
    Cavity geometry mods increase HOM power generated or multipacting activity? NS
    Materials used sufficiently rad hard? YP
    1.3 GHz CM beamline absorber effective? NS
  Installation issues identified/addressed? TP, YH
  Design differences with earlier generation CM’s identified? Strategies for further analysis/testing? TP, NS
  Major interfaces identified and incorporated? TP, YH
Design Management
  Is the design team organized and staffed to successfully complete the project? CMG
  Have all of the major risks been identified and managed? CMG
  Are procurements and production appropriately planned? CMG
  Is the development of associated drawing packages sufficiently mature? TP, YH, CG, MF
Cost and Schedule: Reasonable to achieve planned scope? CMG et al.
ES&H
  Are all related ES&H aspects being properly addressed? JT et al.
Miscellaneous: All previous design review action items/comments addressed? Other issues that must be addressed? CMG
Overall Readiness: Is the design sufficiently mature for Preliminary Design Review approval? All

## Slide 14: Design Review Definitions (LCLSII-1.1-QA-0009-R0)
Preliminary Design Review [~30-50% Design Maturity]
  Documented technical and interface requirements
  Mechanical/structural/thermal design and analyses
  Preliminary layouts, drawings
  Reliability, maintainability
  Assessment of risk areas
  Plan for obtaining safety approval
Final Design Review [~90-100% Design Maturity]
  Requirements of PDR plus…
  Final detailed design
  Final implementation plans including engineering models, prototypes and spares
  Engineering model test results and design margins

## Slide 15: For this review
Please consider also whether this review may serve as a dressed cavity FDR
  Niobium and cavity fabrication are near the critical path and high priority for us
Evaluate design readiness of the dressed cavity to approve implementation, procurement, fabrication and installation activities. The dressed cavity is understood to include the niobium and niobium titanium of the bare cavity, as well as the titanium helium vessel with chimney up to and including the SS tee connection to the 2-phase pipe.
Technical Scope
Are the designs mature and technically sound to satisfy design specifications?
Is the design likely to meet performance expectations?
Have installation issues been adequately addressed?
Have all the major interfaces been identified and incorporated into the design?
Are all design specifications, requirements, performance, and interface documents reviewed, approved and released?
Design Management
Is the design team organized and staffed to successfully complete the project?
Have all of the major risks been identified and managed?
Are procurements appropriately planned?
Is the development of associated drawing packages sufficiently mature?
Cost and Schedule
Cost/schedule reasonable to achieve the planned scope? Technical reasonableness assessment, not detailed cost/schedule review.
ES&H
Are all related ES&H aspects being properly addressed?
Miscellaneous
Have all the previous design review action items/comments been addressed?
Have lessons learned been addressed?
Are there any other issues that have been identified that need to be addressed?
Overall Readiness: Design sufficiently mature so as to allow Final Design Review approval

## Slide 16: Review Agenda
Start | End | Time | Item | Contact
8:30:00 AM | 9:00:00 AM | 0:30 | Executive Session | Ed Daly
9:00:00 AM | 9:20:00 AM | 0:20 | Introduction | Camille Ginsburg
9:20:00 AM | 9:50:00 AM | 0:30 | Cryomodule Safety Framework | Jay Theilacker
9:50:00 AM | 10:20:00 AM | 0:30 | 3.9 GHz Cryomodule Functional Requirements | Elvin Harms
10:20:00 AM | 10:35:00 AM | 0:15 | Coffee Break | 
10:35:00 AM | 11:35:00 AM | 1:00 | 3.9 GHz Cryomodule Components Design | Nikolay Solyak
11:35:00 AM | 12:05:00 PM | 0:30 | Dressed Cavity Final Design | Chuck Grimm
12:05:00 PM | 12:30:00 PM | 0:25 | 3.9 GHz Cavity Tuner | Yuriy Pischalnikov
12:30:00 PM | 2:00:00 PM | 1:30 | Lunch | 
2:00:00 PM | 2:15:00 PM | 0:15 | Niobium Drawings and Material Specification | Mike Foley
2:15:00 PM | 2:35:00 PM | 0:20 | Cavity Surface Processing and Magnetic Shielding Requirement | Anna Grassellino
2:35:00 PM | 3:20:00 PM | 0:45 | Cryomechanical Design | Tom Peterson/Yun He
3:20:00 PM | 3:30:00 PM | 0:10 | Coffee Break | 
3:30:00 PM | 4:30:00 PM | 1:00 | Executive Session | Ed Daly
4:30:00 PM | 5:00:00 PM | 0:30 | Closing Summary | Ed Daly

## Slide 17: Conclusions
3.9 GHz CM design has been expedited to the extent possible
  Cryomechanical design as close as possible to 1.3 GHz CM (which completed final design review)
  Component design effort and technical risk minimized by using existing designs with minimal modification
  Substantial requirements documentation written
Cost/schedule/plan derived from experience; extensively reviewed
Thanks in advance for your help; we anticipate a productive review