## Slide 1: Conductor procurement and QC from CERN
B. Bordini, A. Ballarino, M. Macchini, D. Richter
Joint LARP CM26/Hi-Lumi Meeting at SLAC – 18th– 21st May 2016

## Slide 2: Outline
Wire Technical Specs
  Main Parameters
  Magnet Margin
Received 108/127 RRP Wire
  Data From OST
  First Verification Measurements by CERN
The bundle-barrier PIT
Status of the wire Procurement
Conclusions

## Slide 3: Wire Technical Specs Main Parameters
Jc(4.22 K, 12 T)≈2450 A/mm2
Jc(4.22 K, 15 T)≈1280 A/mm2
 | MQXF Quadrupole
Wire diameter Φ | 0.850 ± 0.003 mm
Nominal sub-element diameter | < 55 µm
Copper to non-copper ratio | 1.2 ± 0.1
Wire twist pitch | 19 ± 3 mm
Wire twist direction | Right-handed screw
Minimum critical current @ 4.22K, 12T | 632 A
Minimum critical current @ 4.22K, 15T | 331 A
RRR (after full heat treatment) | > 150
n-value @ 4.22K, 12T | > 30

## Slide 4: Wire Technical Specs Magnet Margin
4.9 K Temperature Margin and 22.3% Margin on the Load-Line

## Slide 5: Received 108/127 RRP Wire IC @ 12 T, 4.22 K & RRR – OST Data 1/2
The average Ic value is about 14% larger than specification; the RMS value is 3% of the average value
The average RRR value is almost two times the spec value; the RMS value is 18% of the average value
0.85 mm RRP | Value
Quantity [km] | 73.83
n° billets | 9
Layout | 108
Average Ic , RMS [A] | 720.1, 22.4
Ic spec [A] | 632
Average RRR, RMS | 290, 51.4
RRR spec | 150
Average Jc, RMS [A/mm2] | 2760, 85.0
Average Bc2, RMS [T] | 25.6, 0.45
For the RRP Prototypes and the series magnets the 108/127 layout will be used

## Slide 6: Received 108/127 RRP Wire IC @ 12 T, 4.22 K & RRR – OST Data 2/2
Different Markers
Different Billets
632 A
The lowest measured Ic value is more than 6% larger than spec
The lowest measured RRR is larger than 200

## Slide 7: Received 108/127 RRP Wire IC @ 15 T, 4.22 K & RRR – OST Data
Different Markers
Different Billets
At 15 T the average Ic value is about 391 A, 18% larger than specification; the RMS value is 5% of the average value
The lowest measured Ic value is more than 5% larger than spec
lso at 15 TThe lowest measured Ic value is more than 6% larger than spec
331 A

## Slide 8: Received 108/127 RRP Wire IC @ 12 T, 4.22 K – OST vs CERN data
Number of OST measurements per Billet
Average value
Max value
In Red CERN measurements
Min value
CERN measurements about 5% lower – in any case full in spec

## Slide 9: Received 108/127 RRP Wire IC @ 15 T, 4.22 K – OST vs CERN data
Number of OST measurements per Billet
Average value
Max value
In Red CERN measurements
Min value
CERN measurements about 7% lower – in any case full in spec

## Slide 10: Received 108/127 RRP Wire BC2 @ 4.22 K – OST vs CERN data
Lower Bc2 measured by CERN suggests that difference between OST and CERN is due to different strain on the superconductor
Number of OST measurements per Billet
Average value
Max value
In Red CERN measurements
Min value

## Slide 11: Received 108/127 RRP Wire RRR – OST vs CERN data
Number of OST measurements per Billet
Average value
Max value
In Red CERN measurements
Min value
The RRR value measured by CERN is about 10% lower; in any case full in spec

## Slide 12: Received 108/127 RRP Wire Cu to non-Cu – OST vs CERN data
Number of OST measurements per Billet
Average value
Max value
In Red CERN measurements
Min value
Good agreement between CERN and OST data

## Slide 13: Magnetization of the 127 RRP Wire
Magnetization Measurements are carried out only at CERN
The first 5 billets shipped to CERN were measured and, as expected, they showed a good reproducibility of the measured values
Billet 00012 (A03)
Billet | DM (3 T, 1.9 K)
11 | 303
12 | 300
13 | 297
15 | 303
16 | 304

## Slide 14
CERN/Bruker-EAS Collaboration for HL-LHC
Additional Nb barrier around the filaments’ bundle
The Bundle-Barrier PIT wire
Drastically reduced the effect on the Residual Resistivity Ratio (RRR) of:
  mechanical deformations
  The Heat Treatment (HT) cycle
Already a slightly larger critical current with respect to the previous generation of PIT wire; potential to further improve.
Chart: RRR
| 1.0 | 2.0 | 3.0 | 4.0 | 5.0
AE08S00005A01U- HT 243 | 157 | 153 | 150 | 151 | 150
AE08S00005A01U- HT 243 - rolled 15% | 152 | 153 | 149 | 148 | 149
AE08S00005A01U- HT 244 | 134 | 132 | 138 | 132 | 139
AE08S00005A01U- HT 244 - rolled 15% | 141 | 140 | 128 | 136 | 140
AE08S00005A01U- HT 245 | 141 | 139 | 128 | 132 | 127
AE08S00005A01U- HT 245 - rolled 15% | 137 | 138 | 137 | 143 | 137

## Slide 15: Status of the RRP wire Procurement 1/2
Received 73.660 km out of the 360 km ordered:
  64.68 km – in pieces of 840 m  77 piece lengths
  3.85 km – in pieces of 550 m  7 piece lengths
  5.130 km – in pieces of 190 m  27 piece lengths
Procurement limited in 2016 because of problems on the Nb raw material procured by OST for the sub-element diffusion barrier
  NbB particles that produce small tears in the barrier (low RRR)
  This problem never occurred in the past
  Most likely a new Nb ore source
  Established a polishing procedure that allows identifying particles in samples taken during processing of the ingot (and at final stage); OST is trying to replicate the technique so they may independently verify if necessary

## Slide 16: Status of the RRP wire Procurement 2/2
Recovery Plan (Best Guess by Mike Field OST):
Received 100.8 km of wire for 3 dummy coils
  good Ic , low RRR
Series Wire: Financial Committee December 2016

## Slide 17: Status of the PIT wire Procurement
Produced 65 km of bundle-barrier PIT wire for models
  Long piece lengths: 96 % above 840 m (CERN unit length) and 86 % above 1680 m (two times CERN unit length)
Ordering 220 km (march 2016 Financial Committee) of wire for prototypes (production already started)
Series Wire: Financial Committee December 2016

## Slide 18: Conclusions
For the RRP prototype and series magnets the 108/127 layout will be used
CERN has received 73.660 km of the 108/127 RRP out of the 360 km ordered (fulfil RRP prototype needs)
  Good wire performance
  OST experienced a problem in the procurement of the raw material for the diffusion barrier of the sub-element; that will limit the wire procurement in 2016
  The problem was identified and a recovery plan established, the foreseen delay will not have an impact on the cabling schedule
In collaboration with CERN, Bruker-EAS has developed a new PIT conductor that has solved the problem of RRR degradation due to: 1) mechanical deformation; 2) overreacting the superconductor
The bundle barrier PIT will be used for the PIT prototype;
  produced 65 km that will be used for models (long piece lengths)
  Finalizing a contract for 220 km (production already started)
Series Wire (RRP & PIT) : Financial Committee December 2016

## Slide 19: Thank You For Your Attention !
For the RRP prototype and series magnets the 108/127 layout will be used
CERN has received 73.660 km of the 108/127 RRP out of the 360 km ordered (fulfil RRP prototype needs)
  Good wire performance
  OST experienced a problem in the procurement of the raw material for the diffusion barrier of the sub-element; that will limit the wire procurement in 2016
  The problem was identified and a recovery plan established, the foreseen delay will not have an impact on the cabling schedule
In collaboration with CERN, Bruker-EAS has developed a new PIT conductor that has solved the problem of RRR degradation due to: 1) mechanical deformation; 2) overreacting the superconductor
The bundle barrier PIT will be used for the PIT prototype;
  produced 65 km that will be used for models (long piece lengths)
  Finalizing a contract for 220 km (production already started)
Series Wire (RRP & PIT) : Financial Committee December 2016