## Slide 1: Recap of the MICE Spectrometer Solenoid Review: Introduction
Mark Palmer
Fermilab
December 11, 2015

## Slide 2: The Failure
We have encountered a failure in one of five coils in one of the MICE Spectrometer Solenoids
September 13th quench event resulted in loss of ability to operate the Match 1 coil

## Slide 3: Review Context
MICE Spectrometer Solenoids
  Have had a long and colorful history
Terminated due to ice blockage in LHe return line
HTS Lead Failure
LTS Lead Failure
HTS Lead Failure – traced to thermal intercept issue and lead preparation QA
Successful training runs
Terminated due to ice blockage in LHe vent line
2010-2013: Re-build of magnets for improved thermal management
Anomalous Training Behavior
Thermal management issues identified
“Full” = 284 Amps
50 quench cycles before delivery

## Slide 4: The Review
Review held December 3-4 at Fermilab
Review web-site:
  https://indico.fnal.gov/conferenceDisplay.py?confId=10652
A preliminary report was presented during the closeout on December 4
  We expect the final report in roughly a week

## Slide 5: Review Goals
It is imperative that we execute a repair that can successfully get us through the MICE Cooling Demonstration
We must choose a repair solution that is robust and “good enough”
  However, we have neither the time nor the money to completely re-engineer this magnet
  At the same time, another failure would
    Seriously damage the research plans for a number of young researchers
    Negatively impact our options for deploying future muon accelerator capabilities
Time is critical if we are to arrive at a viable repair plan and execute it in an effective fashion so that the MICE Cooling Demo can be operational by 2018

## Slide 6: Review Committee
Committee:
  Herman ten Kate CERN
  Jim Kerby ANL
  Mike Anarella BNL
  Peter Wanderer BNL
  Tom Taylor CERN
  Cesar Luongo JLAB
  Peter McIntyre TAMU
  Luigi Muzzi ENEA-Frascati
Observers:
  Bruce Strauss DOE
  Josef Boehm RAL
  Oleg Kiricheck RAL/ISIS

## Slide 7: Key Elements of Review Charge
Evaluate the existing SS magnet power supply and quench protection scheme in light of the failure event. Examine modifications to the power and quench protection systems being proposed by the SS magnet group and assess the ability of the MICE experiment to safely operate the magnets in the Step IV configuration as well as the Cooling Demonstration configuration.
Evaluate the technical details of the magnet recovery plan as presented by the SS magnet team. In particular, please address the robustness of each of the presented modifications and repair steps. Also consider the degree of operational safety that will be provided by executing the recovery option as presented.

## Slide 8: Key Elements of Review Charge
Evaluate the balance of costs, schedule impact and risks associated with the recovery option based on the initial cost, schedule and risk analysis provided by the SS magnet team. Identify any elements of the plan that require further attention by the SS magnet group before finalizing the proposed recovery option.
Based on the overview and analysis presented by the SS magnet team, confirm whether the recovery option presented will provide a viable path forward for the MICE Experiment. Also, please identify any other magnet recovery options that should be evaluated prior to presenting the magnet recovery proposal to the MICE Collaboration and the funding agencies.