## Slide 1: DUNE Project Status
Eric James DUNE PMG Meeting
January 19, 2016

## Slide 2: Management Update – News
DUNE Collaboration and LBNC meetings took place last week in Arlington Texas
Lots of good discussions with an emerging general consensus that taking beam data with ProtoDUNE detectors at CERN in 2018 should be among highest collaboration priorities
Formal request was made for Expressions of Interests from collaborating institutes for becoming involved in ProtoDUNE efforts

## Slide 3: Management Update - News
New Single and Dual-Phase ProtoDUNE management teams becoming actively engaged in their new roles
A high-level schedule has been created to project the effort needed to construct, install, commission, and operate the Single-Phase ProtoDUNE detector on the timescale of 2018
Work now underway to build a fully resource-loaded schedule matched to the draft high-level schedule (goal is to have this in place by the end of January)
Next Step will be to integrate the Single-Phase ProtoDUNE schedule with the EHN1 (CERN neutrino platform) and Dual-Phase schedules
    The management teams are planning to spend the week of February 22nd at CERN to work on synchronizing schedules

## Slide 4: Management Update - News
Attempting to use better than expected FY16 budget to speed up critical-path activities for ProtoDUNE
  Add resources for APA construction activities
  Additional engineering support for CPA and Field Cage design activities
  Additional engineering support for Electronics Integration Issues (define needed QA/QC activities)
  University support for critical Photon Detector engineering studies
  University support for TPC integration facility at Ash River
  Accelerating development of COLDATA ASIC chips (DUNE)

## Slide 5: Management Update – News
ProtoDUNE cryostat review took place on December 17-18
Review of front-end and ADC ASIC designs will take place at BNL on January 21
DAQ Workshop at CERN on February 25-26
New L3 Manager for Photon Detection system identified (Leon Mualem – Cal Tech) with transition plan for FY16 in place
Working to obtain waiver that will allow for the duty-free entry of detector components produced outside of the U.S.
  Met with FESS/Property to identify requirements for shipping ProtoDUNE components to CERN

## Slide 6: Management Update – Budget (re-plan) Status; by L3 WBS
Chart: $000
| 35-ton Commissioning | DAQ & Monitoring | Project Management | Installation & Integration | Photon Detector | Cold Electronics | Time Projection Chamber
Sum of YTD Costs | 203.144 | 103.647 | 487.652 | 248.407 | 126.414 | 249.606 | 245.91
Sum of BUDGET PLAN | 247 | 87 | 1752 | 860 | 660 | 1840 | 2163

## Slide 7: Management Update – Budget Status, FY16 Costs vs. schedule
Actual
Scheduled
FY16 Budget

## Slide 8: Interfaces with LBNF – FSCF Interface Issues
Continue to refine requirements through the start of CF final design work in spring 2016
Detector interface issues requiring additional input prior to the start of the final design work are documented in LBNF change log
  Review of Computational Fluid Dynamics Calculations during last week’s DUNE Technical Board Meeting (have not identified a need for pumps on both sides of the far detector cryostats)
  Control Room workshop was held on December 16 and preliminary report is now available for comments (due today)

## Slide 9: Collaboration News
Collaboration meeting last week in Arlington, TX
  Mini-workshop on QC/QA planning for ProtoDUNE production including discussion of 35-ton lessons learned
    QA/QC process important as ProtoDUNE construction is intended to serve as the development platform for defining these processes for the far detectors
      ProtoDUNE = 6 APAs; 1 FD detector = 150 APAs
  Initial organizational discussions among members of Single-Phase Management team and upper-level DUNE management
    Dedicated parallel sessions on detector integration and installation activities that will need to take place at CERN
  “Expressions of Interest” for participation in ProtoDUNE activities from collaboration institutes

## Slide 10: 35-ton
3rd and 4th truckloads of LAr to be received Thursday and Friday of this week
Cool-down and filling currently scheduled to commence next Monday (January 25th)
More details in Michelle Stancari presentation