## Slide 1: MICE RF Module Update
Andrew Lambert
01/08/2016

## Slide 2: Items
Vacuum vessels
  1st shipment from Keller on 02/01/2016
Actuator production
RF coupler production
Clean room preparation
Assembly preparation

## Slide 3: Actuators
14 actuators are completed
  Vacuum tight
  Leak tight
  12 required for operation
2 working spares
2 additional spares that need repair
  Low priority
  Will fix once other welding tasks are completed (couplers, water feedthrough lines)

## Slide 4: RF Couplers
All welds on the first two RF couplers are complete, one is vacuum tight, the other is in repair for minor vacuum leaks
  Will begin assembly immediately after 2nd coupler is leak tight
  Ship two fully assembled couplers (minus cooling line fixtures) to FNAL MTA – do these go to RAL as spares when MTA testing is finished?
Continuing with the welding and assembly of the remaining 4 couplers
What will be done with the current RF couplers at the MTA?

## Slide 5: Clean room preparation
New curtains
  Ordered, waiting on arrival
Linoleum flooring
  Ordered, waiting on arrival
Ceiling work
  Additional ceiling filtration units in-hand
  Will begin installation next week
Changing tent
  Bids out, will purchase and install

## Slide 6: Assembly preparation work
Waiting on equipment from FNAL
  Items should arrive next week
Cleanroom item procurement
  Underway
Measured the two MICE cavities for tuner arm machining
  Tuner arms being machined to nominal dimension; shimmed into place during assembly
  Fabricating shims
Water feedthrough welds on cavity
  Starting this process

## Slide 7: Summary
Actuators
  Completed 12 + 2 spares
RF couplers
  2 for FNAL MTA near complete
  Next 4 for MICE underway
Clean room prep
  Underway
Assembly prep
  Tuner arm machining
  Feedthrough welding
  Staging