## Slide 1: Superconducting RF: LB650 and HB 650 Status
Tom Nicol
PIP-II Machine Advisory Committee Meeting
15-17 March 2016

## Slide 2: Linac map

## Slide 3: General cryomodule parameters

## Slide 4: Cryomodule heat loads in CW

## Slide 5: Overview of 650 MHz related activities
Low beta cavities
  Fermilab – RF and end group design
  VECC – Bare and dressed cavity mechanical design and fabrication
High beta (0.92) cavities
  Fermilab – RF and bare and dressed mechanical design
  RRCAT – Bare and dressed cavity fabrication
High beta (0.90) cavities (beta 0.90 is an earlier design, superseded by 0.92 – both will be used in the first high beta cryomodule)
  Fermilab – Bare and dressed cavity design and fabrication
High beta cryomodule
  Fermilab and RRCAT – Complete cryomodule design
  There is no current effort on LB650 cryomodule design
Tuner design and fabrication
  Fermilab – Prototype tuner design and fabrication
Input coupler design and fabrication
  Fermilab – Prototype coupler design and fabrication

## Slide 6: LB650 cavity milestones
Low beta 0.61 cavities |  | 
Deliverable | Responsible | Date
Fabricate 1-cell bare cavity | VECC | Complete
Process and test 1-cell bare cavity | VECC and Fermilab | April 30, 2016
Cavity RF and end group design | Fermilab | February 29, 2016
Mechanical design of 5-cell cavity | VECC | June 30, 2016
Final design review of 5-cell cavity | VECC | August 31, 2016
Helium vessel and tuner interface design | VECC | September 30, 2016
Fabricate 1st 5-cell bare cavity | VECC | November 15, 2017
Process and VTS test 1st 5-cell bare cavity | VECC | March 30, 2018
Fabricate 1st 5-cell dressed cavity | VECC | September 30, 2018
Test 1st 5-cell dressed cavity | Fermilab | December 31, 2018
Fabricate 2nd 5-cell bare cavity | VECC | March 31, 2018
Process and VTS test 2nd 5-cell bare cavity | VECC | September 30, 2018
Fabricate 2nd 5-cell dressed cavity | VECC | March 31, 2019
Test 2nd 5-cell dressed cavity | Fermilab | May 31, 2019
Primary deliverables

## Slide 7: HB650 (0.92) cavity and cryomodule milestones
High beta 0.92 cavities |  | 
Deliverable | Responsible | Date
Cavity RF, end group, and mechanical design | Fermilab | Complete
Helium vessel and tuner interface design | Fermilab | June 30, 2016
Fabricate 1st 5-cell bare cavity | RRCAT | November 15, 2016
Process and VTS test 1st 5-cell bare cavity | RRCAT | May 15, 2017
Fabricate 1st 5-cell dressed cavity | RRCAT | December 15, 2017
Test 1st 5-cell dressed cavity | RRCAT and Fermilab | April 30, 2018
Fabricate, process, VTS, dress, high power test 1 cavity | RRCAT | September 30, 2018
Fabricate, process, VTS, dress, high power test 2 cavities | RRCAT | December 30, 2018
Fabricate 4 dressed cavities | RRCAT | December 31, 2017
Fabricate 4 tuner assemblies | RRCAT | March 31, 2018
High beta 0.92 cryomodules |  | 
Deliverable | Responsible | Date
Cryomodule design | RRCAT and Fermilab | July 31, 2017
Helium vessel and tuner interface design | Fermilab | June 30, 2016
Primary deliverables

## Slide 8: HB650 (0.90) cavity and ancillaries milestones
High beta 0.90 cavities |  | 
Deliverable | Responsible | Date
Cavity RF, end group, and mechanical design | Fermilab | Complete
Fabricate 4 bare cavities | Fermilab and AES | Compete
Fabricate 5 bare cavities | Fermilab and Pavac | April 30, 2016
Helium vessel and tuner interface design | Fermilab | May 30, 2016
Process first 4 cavities | ANL and AES | June 30, 2016
Fabricate 1st 5-cell dressed cavity | Fermilab | September 30, 2016
Ancillaries |  | 
Deliverable | Responsible | Date
Design prototype tuner for beta 0.61, 0.90, 0.92 | Fermilab | March 31, 2016
Fabricate prototype tuner | Fermilab | September 30, 2016
Design input coupler for beta 0.61, 0.90, 0.92 | Fermilab | September 30, 2016
Primary deliverables

## Slide 9: Performance parameters from the FRS (ED0001834)
Operational requirements from the FRS (ED0001834)

## Slide 10: Performance parameters from FRS (ED0001321)
Operational requirements from FRS (ED0001321)

## Slide 11: Low and high-b cryomodule general requirements
General |  | 
 | Physical beam aperture, mm | 118
 | Overall length (flange-to-flange), m | 9.5
 | Overall width, m | ≤1.6
 | Beamline height from the floor, m | 1.3
 | Cryomodule height (from floor), m | ≤2.00
 | Ceiling height in the tunnel, m | 3.20
 | Max allowed heat load to 70 K, W | 300
 | Max allowed heat load to 5 K, W | 25
 | Max allowed heat load to 2 K, W | 220
 | Maximum number of lifetime thermal cycles | 50
 | Intermediate thermal shield temperature, K | 45-80
 | Thermal intercept temperatures, K | 5 and 45-80
 | Cryo system pressure stability at 2 K (RMS), mbar | ≤0.1
 | Environmental contribution to internal field | 10 mG
 | Transverse cavity alignment error, mm RMS | <0.5
 | Angular cavity alignment error, mrad RMS | ≤1
Cavities |  | 
 | Number, total per cryomodule | 6
 | Frequency, MHz | 650
 | b geometric | 0.92
 | Operating temperature, K | 2
 | Operating mode | Pulsed and CW
 | Operating energy gain, MV/m | 17.7
 | Maximum cavity heat load to 2 K, W (each) | 30
Tables from FRS
General |  | 
 | Physical beam aperture, mm | 83
 | Overall length (flange-to-flange), m | 3.9
 | Overall width, m | ≤1.6
 | Beamline height from the floor, m | 1.3
 | Cryomodule height (from floor), m | ≤2.00
 | Ceiling height in the tunnel, m | 3.20
 | Max allowed heat load to 70 K, W | 100
 | Max allowed heat load to 5 K, W | 15
 | Max allowed heat load to 2 K, W | 100
 | Maximum number of lifetime thermal cycles | 50
 | Intermediate thermal shield temperature, K | 45-80
 | Thermal intercept temperatures, K | 5 and 45-80
 | Cryo-system pressure stability at 2 K (RMS), mbar | ~0.1
 | Environmental contribution to internal field | <0.1 mG
 | Transverse cavity alignment error, mm RMS | <0.5
 | Angular cavity alignment error, mrad RMS | ≤5
Cavities |  | 
 | Number, total per cryomodule | 3
 | Frequency, MHz | 650
 | b geometric | 0.61
 | Operating temperature, K | 2
 | Operating mode | CW and pulsed (0-100%)
 | Operating energy gain, MV/m | 17.7
 | Coupler power rating (TW, full reflection), kW | 120
High-b FRS: ED0001322
Low-b FRS: ED0001830

## Slide 12: 650 MHz Multi-cell Photos
Optical Inspection of 5-cell B=0.9 650 MHz cavity
5-cell B=0.9 650 MHz cavity prepared for vertical testing.
Four beta 0.9 cavities have been received from AES and are being prepared for processing
Notes: You should note who the vendor is on this.

## Slide 13: Low beta 650 MHz cavity end group
Lbeam_Pipe=183 mm
Ø=118 mm
Ø=72.9 mm
FPC end group
L=98 mm
L=160 mm
Power coupler end group design details developed at Fermilab and made available to VECC for low beta cavity design

## Slide 14
Field probe and tuner end group
Ø=118 mm
L=176 mm
L=91 mm
Ø=12 mm
L=89.5mm
Low beta 650 MHz cavity end group
Tuner end group design details developed at Fermilab and made available to VECC for low beta cavity design

## Slide 15: High beta 650 MHz dressed cavity
Beta 0.92 dressed cavity and tuner being developed at Fermilab
When completed, final design will be made available to RRCAT
Helium vessel and pipe connections are compatible with HTS-2
Tuner
Power coupler port

## Slide 16: High beta 650 MHz dressed cavity
Internal magnetic shield
Analysis work is ongoing to determine the effectiveness of an internal magnetic shield

## Slide 17: High beta 650 MHz cryomodule
High beta cryomodule being developed jointly between Fermilab and RRCAT
The design being developed will house both beta 0.90 and 0.92 dressed cavities
Tuner access ports
Valves and transfer line connections
Heat exchanger and relief line

## Slide 18: High beta 650 MHz cryomodule
Input coupler ports
Instrumentation ports
Vacuum relief
Beam gate valve

## Slide 19: Lab 2 cleanroom
Lab 2 in the Fermilab village is being converted to cleanroom, HPR, and cryomodule assembly space for both SSR and 650 MHz cavity activities

## Slide 20: Summary
Low beta cavities
  RF and end group designs have been made available to VECC
High beta (0.92) cavities
  Mechanical bare cavity design drawings have been made available to RRCAT
  Detailed design work has started at RRCAT
  Helium vessel and integration design is in-process at Fermilab
High beta (0.90) cavities
  Four bare cavities are in-house and Fermilab and are being processed
  Five more are in-process at Pavac
  Helium vessel and integration design is in-process at Fermilab
High beta cryomodule
  Detailed design work is in-process at Fermilab and RRCAT, loosely divided between cavity string and cold mass (Fermilab) and vacuum vessel and thermal shield (RRCAT)
Tuner design and fabrication
  Prototype design and analysis is in-process at Fermilab (Fermilab and RRCAT engineers)
  Goal is to have a common tuner design for all low and high beta cavities
Input coupler design and fabrication
  Previous coupler work needs to be restarted at Fermilab
  Goal is to have a common coupler design for all low and high beta cavities