## Slide 1: Spectrometer Solenoid Recovery
Mark Palmer
BNL
March 25, 2016

## Slide 2: Introduction
Update on the status of our efforts to repair the MICE Spectrometer Solenoid
December Review
  Confirmation that a plan to replace the existing damaged cold mass likely offered the only affordable route forward
    Replacement cold mass option preferred
    Option to attempt repair on existing cold mass as a backup
  Updates to Quench Protection System critical!!!
  December cost estimate >$2.1M
    Not enough time/effort allowed for cold mass construction
    US cost estimate (from now through start of operations) raised to $2.5 M based on this guidance (added contingency)

## Slide 3: Since the December Review
Enlisted BNL Magnet Division (with recent experience on a similar magnet – RHIC e-lens solenoid) to prepare documentation for:
  Bid package for vendors: As-Built package suitable for budgetary quotes and final bids
    Updated engineering package should be at a level suitable for delivery to vendors within the next few weeks
  Provide detailed input on the “lessons learned” from the existing magnet
    Electrical analysis
    Mechanical analysis
  Help prepare for a make-buy decision on the summer 2016 timescale
    NOTE: Sufficient MAP reserve funds for any major procurement would only become available at the start of FY17

## Slide 4: Today
Magnetic Design – R. Gupta
Mechanical Analysis – H. Witte/A. Marone (presented by P. Wanderer)
Overview – P. Wanderer