## Slide 1: Wrap-up
Steve, Paul, Shekhar, Valeri, Don, Steve, Fernanda, Allan, Jim, Luisella, Chris
PIP-II Budget Retreat
26 April 2016

## Slide 2: Summary of Total Request
FY2017 M&S Guidance (Direct) $3.6M
FY2017 M&S Request (Direct) $6.4M
FY2017 FTE Guidance 53.4
FY2017 FTE Request 72.6
In fully loaded dollars:
  FY2017 Guidance $18.2M
  FY2017 Request $26.7M
  Over-subscription: $8.5M

## Slide 3: Carryover
We are assuming $0.75M of carryover into FY17
  Requires regulating FTE to 58 (average over the year) = 60 FTE year balance
If we have additional underruns as we approach the end of FY16 we will engage in forward funding
  Easiest things to forward fund are items like HWR/ANL and T&M contracts
  We do not currently project major underruns beyond the SWF associated with above FTE

## Slide 4: Strategy for Further Adjustments
We do not have sufficient resources to meet our schedule goals
Develop an internally consistent plan that bring things together synchronously, with appropriate balance between R&D, IIFC, and CD-1 activities
Strategy
  Support FY17 M&O costs off-project
  Complete MEBT installation/commissioning in FY17
    Delay chopper testing to FY18
    Delay HEBT design to FY18
    Limit PXIE operations to 6 months in FY17
  Delay cryo operations in PXIE to Q3FY18
    Keep HWR pCM and PXIE cryo distribution proceeding in parallel: Q2FY18 delivery
      Note: MUST install cryo distribution before HWR
  Delay beam through HWR/SSR1 to FY19/20
    Attempt to keep SSR1 pCM delivery in Q2-4FY19
    Do we need beam through SSR1 at this point?
  Keep STC modifications and HB650 dressed cavitie(s) proceeding in parallel: early/mid FY18
    Delay HTS-2 prep into FY18
  Delay HB650 pCM to FY20
  Complete successful CD-1 DOE Review in FY17
  Delay CD-2 to FY19

## Slide 5: Strategy for Further Adjustments/Revised Milestones
Priorities/Target Dates
  PXIE warm: beam out of MEBT-1
  SSR1: Resonance control testing definite results
  PXIE warm: beam to end of MEBT
  PXIE cold: HWR CM and associated infrastructure (cryo, rf, power, etc.)
  SSR1 CM and associated infrastructure (rf, power, etc)
  HB 650 dressed cavities and associated infrastructure (HTS-2, rf)
  HB650 CM to CMTS
  CD-1 activities: CDR, Site Characterization, civil construction drawings
  Note: India is not a stand-alone priority; it is integrated into the work above
Q3FY16
Q2FY17
QFY17
Q3FY18
Q2FY19
Q4FY18
Q2FY20
Q3FY17

## Slide 6: Candidates for Further Adjustments
See Chris’ slides

## Slide 7: Resultant Bottom Line
FTE: 5.6 over
M&S: $725K over (direct)
Budget: $21.1 vs 18.2M

## Slide 8: Next Steps
Establish a budget at $18.2M
Division labor fairs over the next month
We will need you to update your FTE requests to match above guidance – you will get a request from Chris in the next week or two
Budget presentation to Directorate this summer
  Includes appeal for a larger budget