## Slide 1: MEBT – FY17 Budget Request
A. Shemyakin
PIP-II Budget Retreat
26 April, 2016

## Slide 2: Standard Presentation Outline
Resources required to meet target goals
Goals that can be met with the initial resources allocation

## Slide 3: PIP-II MEBT - FY17 Initial Goals
Support RFQ beam characterization
  Characterize the beam coming from RFQ with the LEBT bend installed
Test prototype kickers with beam
  Install MEBT-2; pass the beam through kickers; measure beam response
Install full length MEBT
  With prototype kickers and absorber; “dirty” but cleanable last sections
Finish MEBT absorber design
  Begin and finish the design; order major parts
    With the goal to test before SRF installation
Support CDR and RLS for MEBT program
Develop HEBT design
  Mechanical and optical model that includes all major parts
  Model of the dump with all radiation simulations
  RF design of separation cavity

## Slide 4: PIP-II MEBT – Resources Required to Meet Initial Goals
FTE- next slide

## Slide 5: PIP-II MEBT – FTE – By Job Category and Role
Mechanical engineering + design, 1.55 + 1.75 = 3.3 FTE
  Guide assembly work; remaining MEBT-3 design; MEBT absorber; HEBT
Scientists + operation, 3.85 + 0.5 = 4.35 FTE
  MEBT studies etc.; HEBT design
Electrical engineers + technicians, 1.5 + 0.85 = 2.35 FTE
  Kickers; MEBT studies

## Slide 6: PIP-II MEBT – Achievable Goals at Initial Target
Support RFQ beam characterization – full scope
Support CDR and RLS for MEBT - full scope
Test prototype kickers with beam- reduced scope (no CW)
Install full length MEBT - reduced scope
  e.g. no differential pumping
MEBT absorber design – no work
HEBT – no work
Main consequence: postpone tests with full power on absorber until after SRF installation

## Slide 7: Scenario with the scope reduced even more
Only passing the beam through the full – length MEBT
  Support RFQ beam characterization – full scope
  Support CDR and RLS for MEBT - full scope
  Install full length MEBT - reduced scope
  Test prototype kickers with beam- no work
No PXIE operation for a half of year
  Scientific and operation personnel need to find different projects
Additional decrease: 2.15 FTE, 20 k$
  To 4.6 FTE, including 1 for Indian visitor
  MEBT only; additional decrease in LEBT + RFQ may be ~0.5 FTE