## Slide 1: Muon Department Meeting
Jerry Annala
Transition to Operations
14 April 2016

## Slide 2: Reviews since our last Department meeting
Lab EVMS surveillance
  Mu2e did not have an Accelerator CAM called to present
  Extremely positive feedback for g-2
DR AIP internal review (February 25)
  Budget is in good shape
  Schedule end of project needs to be extended
g-2 Status review with DOE (April 6)
  Also very successful
  Close out stressed the importance of effort to transition to operations
Mu2e CD-3 Director’s review next week

## Slide 3: Critical Device Installation Lesson
M1 Beamline improvements called for new magnet string and power supply for F17B3
  RSO locked disconnect on yard transformer at F2
  C-magnet was changed as last shutdown
  Bus work to magnet was cut near the old power supply
  Old power supply was decommissioned.
  New power supply was installed and work included a new CD controller
  This work left us in a condition where the RSO lock was controlling an obsolete disconnect.
  We never lost control of the beam line, but there was quite a concern when RSO realized how far work had progressed.
  We need to understand the consequences of progressing too fast with any installation we are involved with.

## Slide 4: Path to permission for commissioning with beam
Running beam from RR to F17 before shutdown
  Work out an operating note with RSO ahead of time
  Specify intensities, rep rates, where the beam is dumped, etc
Running beam to target after the shutdown
  Should be the same level of approval as running to F17
  We will wan the dump installation to be complete
Running beyond the AP0 target (or possibly the M3 beam stop)
  Full approval from lab and DOE after an Accelerator Readiness Review.
  This is a 3 day review with outside experts. We will give presentations and spend time showing reviewers our work.

## Slide 5: Necessary for operational readiness review
Almost all new systems installed and tested (including software)
Safety systems in place and tested
Shielding assessment approved
SAD updated
Updated safety envelope approved
Procedures are written and approved
Train personnel involved with operating new facility
  Operators
  Muon department
  Technicians
Participate in external ARR
Finish punch list from review
Approval to run beam in M3 line

## Slide 6: ARR approval
After review, expect 2 to 3 weeks for permission to run
We should start the effort to schedule review about 3 months ahead
We need to start the process of setting up the review just after Thanksgiving
John Anderson will be our main resource for setting up this review
This review covers the entire program including the experiment