## Slide 1: LMQXF Plans and Options
G. Ambrosio
LMQXF Cold Mass Requirements and Conceptual Design Review
April 25, 2016
FNAL

## Slide 2: Outline
MQXF magnets
LMQXFA cold mass
Plans & options for cold mass tests
Remarks

## Slide 3: US Contribution to HL-LHC Inner Triplets baseline plan
Q1/Q3 cold masses by US (LMQXFA)
  magnetic length: 4.2 + 4.2 m (MQXFA)
Q2 cold masses by CERN
  magnetic length: 7.15 m (MQXFB)
All cryostats and integration by CERN
Max cold mass outer diameter: 630 mm
Operating temperature: 1.9 K
US cold mass

## Slide 4: MQXFA/B Main Parameters* Equal magnets in Q1/Q3 & Q2s
Parameter | Unit | MQXFA
Coil aperture | mm | 150
Magnetic length | m | 4.2
N. of layers |  | 2
N. of turns Inner-Outer layer |  | 22-28
Operation temperature | K | 1.9
Nominal gradient | T/m | 132.6
Nominal current | kA | 16.5
Peak field at nom. current | T | 11.4
Stored energy at nom. current | MJ/m | 1.2
Diff. inductance | mH/m | 8.2
Strand diameter | mm | 0.85
Strand number |  | 40
Cable width | mm | 18.15
Cable mid thickness | mm | 1.525
Keystone angle |  | 0.4
*MQXFS1 quadrupole design report
LARP DocDB 1074

## Slide 5: LMQXFA Cross Section
Helium vessel by welding two half SS shells

## Slide 6: MQXF Status
1st short model (MQXFS1) performed very well
1st prototype to be tested in Spring 2017

## Slide 7: MQXF  LMQXF
The Al-shell has features for longitudinal skin welding:
  Slots for accessing the yoke (for alignment)
  Grooves for the backing strip
The SS skin welding should make the He vessel with minimal impact on magnet stress distribution
  To be tested on short model MQXFS1c
Welding block
Slot for access to the yoke and support

## Slide 8: Q1/Q3 Cold Mass (LMQXFA)
Main features:
  Max OD: 630 mm
  SS shell thickness: 8 mm
  Length: 10.14 m
  Two magnets in one cold mass
Main challenges:
  Alignment (with two magnets in each cold mass)
  Welding & inspection
  Transportation without affecting alignment

## Slide 9: LMQXFA
Two magnets in one cold mass:
  Different wrt to Q2
  8.4 m magnets have excessive risk for a US project
Leads at each end

## Slide 10: Bus bars
Bus bars design and routing will be based on CERN design and plan.
Options were presented at Conceptual Design Review of the Magnet Circuits for the HL-LHC
  https://indico.cern.ch/event/477759/timetable/#20160321.detailed
Cold mass design including bus bars integration is starting at CERN in these weeks

## Slide 11: Inner Triplet Busbars Integration Proposal (until a 18kA cable is developed and proven)
Courtesy of Cedric Eymin
18kA
18kA
2kA
200A
2kA
200A
2.8kA,
12Hz fast decay
External busbars
(round cable type)
Splices
+ | 13
+ | 11
 | 2
 | 2
 | 2
 | 24
 | 36
 | 18
Total 108
Internal busbars
(stabilized Rutherford cable)
In Q2 cold masses

## Slide 12: Cold Mass Interfaces
The major interface is with the cryostat
Cryostat design is CERN responsibility, and is planned to start now
  CERN team had to design 11T cryostat first
We plan to have CM interfaces defined by the MQXF Review
  June 7-10, 2016 at CERN
Detailed mechanical layout is available
  LHCLSXH_0010-v0.3.pdf
Study of distance btw magnets is available
  HILUMILHC-Mil-MS39_final. pdf

## Slide 13: Budget Challenge
Preparation for Cold Mass assembly & test, and prototype Cold Mass assembly & test, to be performed by LARP
  Prototype CM test: Nov 2019
  LMQXFA1 test: July 2020
LARP has very tight budget in FY16/17/18(?)
US-HiLumi Project has even tighter budget at start
Option analysis
  - Balance btw costs and risks

## Slide 14: Tests Plan
Each US magnet (MQXFA) will be tested in vertical condition at 1.9 K
  At BNL Vertical Test Facility
  Current up 17.8 kA (108% of nominal current)
Each US cold mass (LMQXFA) will be tested in horizontal condition
  At FNAL, Test Stand 4
  Tests for requirement verification: TBD (see next slides)
Each cryostated CM will be cold tested at CERN
  Current up 17.8 kA (108% of nominal current)

## Slide 15: Option 1 – “Bare bones”
Only tests at room temperature:
Cold-mass alignment
  Can be achieved using AC SSW technique at 10 A
He leak tests (under pressure and vacuum)
Electrical tests

## Slide 16: Option 2 – “Cold, No power”
Cooldown of cold mass in re-usable cryostat:
Alignment, electrical and leakage tests at:
  a) 80 K in LN2
    alignment with most thermal changes
  b) 4.5 K in LHE
    alignment with all thermal changes, plus verify leak tightness
  c) 1.9 K in LHE
    additional benefit of checking superfluid helium leak tightness

## Slide 17: Option 3 – “Cold & Powered”
Cooldown in re-usable cryostat to 1.9 K
Powering test up to 15 kA
  Using existing 15 kA current leads
Magnetic measurements with 46 mm probe
  with minimal test stand modifications using existing bore tube
  QD DAQ upgrade likely needed
 Advantages: validation of SC bus and splices; test of heaters and CLIQ in final configuration

## Slide 18: Option 4 – “Full test”
Cooldown in re-usable cryostat to 1.9 K
Powering test up to 17.8 kA
Magnetic measurements with ~100 mm probe
  Needs upgrade of test facility above 15 kA
  Needs upgrade of feed can, return can, and warm bore
 Advantages: full qualification of US deliverable

## Slide 19: Baseline
Baseline is Option 3: “Cold & Powered”
Option 2 is a fall back
Option 4 is a possible upgrade

## Slide 20: Remarks
Next talks are going to present the conceptual design of the Cold Mass, Re-usable Cryostat, Test Facility, Test Equipment.
  Some requirements & interfaces to be finalized in June, no major changes expected
We are exploring options, and your feedback will be very appreciated:
  Is the risk of some options too high?
  Is the cost excessive wrt to the advantages?

## Slide 21: Back up Slides

## Slide 22
Internal/External integration were compared
Cable/Busbars technologies were compared
Integration solution proposed as “best compromise”:
  For high current : Rutherford cable stabilized busbars routed through the cold masses as long as an appropriate 18kA cable has been developed
  For lower current : external cables routed in a dedicated line on top of the cold masses [2kA cable to be developed]
Alternate circuit design eases the busbars integration
Splices quantity varies from 96 to 176. 101 to 108 could be achieved depending on the retained scheme
Cold masses design including the busbars integration will start in the coming weeks
To be studied: Integration of 18 kA busbars in the D1 and CP
Inner Triplet String Busbars Integration Summary