## Slide 1: Risk Modeling and Monte Carlo Analysis
Mohammed Elrafih
Mu2e CD-3c DOE IPR
14-16 June 2016

## Slide 2: Mohammed Elrafih – Background
Current roles
Project Controls Specialist, “LBNF – Cryogenics Infrastructure”
Fermilab Risk Manager in Training
  Enterprise risk, Lab-standard project risk process, risk register, tools
  Risk workshops, risk analysis, MC modeling, reviews
Honors Business Administration (HBA)
  Focus in Operations and Project Management
Project Coordinator & Project Controls Experience in:
  Major Oil & Gas Construction Projects

## Slide 3
Risk Modeling

## Slide 4: Risk Modeling – Objectives
Model probabilistic risk events and response plans in the project schedule using Monte Carlo (MC) techniques, in order to
Assess scenarios and risk responses
Aggregate cost and schedule impacts and determine the cost and schedule risk drivers
Determine contingency needed to deliver the project within budget and on time (at 80 % C.L.)
  Schedule contingency for risk
    Notably float before CD-4
  Cost contingency for risk
    Distinct from cost estimate uncertainty
Plan Risk Management
Identify
risks
Develop risk responses
Monitor and
Control risks
Analyze risks
Iterate / Communicate / Review / Improve

## Slide 5: Risk Modeling – Monte Carlo
Cost and schedule drivers
Costs of risks and contingency
Completion dates and float
P6 Project Plan includes all project activities, linked in time-sequence. The risk analysis uses a summary schedule derived from the full schedule.
P6
DB
Full
Schedule
Summary Schedule
Risk Model simulates probabilistic risk events, with ranges of impacts, in the project schedule
Risk Model
(Primavera Risk Analysis - PRA)
Risk
DB
Risk Register
(Web tool)
DocDB
More Details
(documents)
Risk Register captures risk probabilities, impacts, and response plans

## Slide 6
  1-point estimate
  60 % chance of no overrun
  40% chance of an overrun
  Overrun is exactly 3 M$
1
2
3
4
5
Impact
I (M$)
Probability, P
0
6
60% (risk does
not happen)
40% (risk
happens)
  1-point estimate
  60 % chance of no overrun
  40% chance of an overrun
  Overrun is exactly 3 M$

## Slide 7
1
2
3
4
5
I (M$)
0
6
60% (risk does
not happen)
40% (risk
happens)
Probability, P
  2-point estimate (range)
  60 % chance of no overrun
  40% chance of overrun
  Mean overrun is 3 M$
  Overruns from 2–4 M$ are all equally likely

## Slide 8
  3-point estimate (triangle)
  60 % chance of no overrun
  40% chance of overrun
  Most likely overrun is 3 M$
  Overrun as low as 1 M$ but this is unlikely
  Overrun as high as 6 M$ but this is unlikely
1
2
3
4
5
I (M$)
0
6
60% (risk does
not happen)
40% (risk
happens)
Probability, P
  3-point estimate (triangle)
  60 % chance of no overrun
  40% chance of overrun
  Overrun amount is probably small (up to a few M$)
  Small chance of a large overrun (up to 6M$)

## Slide 9
1
2
3
4
5
I (M$)
0
6
60% (risk does
not happen)
40% (risk
happens)
Probability, P
Schedule impacts are similarly modeled with 1-, 2-, and 3-point probability distributions
  3-point estimate (triangle)
  60 % chance of no overrun
  40% chance of overrun
  Overrun amount is probably small (up to a few M$)
  Small chance of a large overrun (up to 6M$)

## Slide 10: Risk Modeling – Monte Carlo
(2) Choose cost and schedule impacts from distributions
Repeat steps (1) – (3) 100,000 times and study the statistical behavior of many scenarios
Placeholder risk events are inserted into schedule with zero cost and zero duration
(1) Throw dice – if risk happens, risk activity is assigned risk impacts (cost and duration)
(3) Update entire schedule to generate one complete project outcome (scenario)
Primavera Risk Analysis (PRA) framework

## Slide 11
Risk Modeling Results – Cost

## Slide 12: Total cost of all Mu2e risks
Mu2e risk cost contingency = 5.7 M$ (at 80% C.L.)
5.7 M$

## Slide 13: Top 20 cost risks

## Slide 14
Risk Modeling Results – Schedule

## Slide 15: All LBNF/DUNE risks – Schedule contingency
Mu2e Project will finish before Dec 29 2022 (at 80% C.L)

## Slide 16
Risk Modeling Results – Burn Rate

## Slide 17: Burn rate – Mu2e Overall
Burn rate is the fixed cost per unit time incurred due to delays
Standing army costs for Project Offices and management of: subproject, control accounts, design, construction (50%)
Escalation costs of delayed expenditures – 3% on remaining work: blend of labor (2.7%/yr), M&S (1.9%/yr), and CF (3.4%/yr)
Mu2e average burn rate = 5.0 M$ / year
 Mu2e risk contingency for burn rate = 4.9 M$ (80% C.L.)
  (i.e. 11.8 months * 5.0 M$ / year)

## Slide 18
Summary

## Slide 19: Summary – the numbers
Risk contingency (at 90 % C.L.) | 
No. risks (High / Medium / Low) | 69
Cost contingency from risks | 5.7 M$
Cost contingency from burn rate | 4.9 M$
Total risk cost contingency | 10.65 M$
Risk schedule contingency | 16 months

## Slide 20: Questions?