## Slide 1: Installation of New Inflector Cold Mass: The Concept
Del Allspach, Hogan Nguyen, PPD
June 24th 2016

## Slide 2: 2 Major Steps
Extracting the Inflector Cryostat from Magnet Gap
To Be Performed Primarily by PPD Staff
Swapping the Inflector Cold Mass
To Be Performed Primarily by TD Staff

## Slide 3: Extracting the Inflector Cryostat From Magnet Gap
PPD Staff will be doing this step in Fall 2016
but in REVERSE
All the Tooling are essentially in Place
This Step is essentially known

## Slide 4
Perform `Cut’ thru the service
Line
To Inflector
Magnet
Lead
Can and
Valve
Box
Magnet Yoke

## Slide 5: `Cutting’ Thru Service Line
Cut Thru Vacuum Jacket
Remove MLI and Kapton
Disconnect Instrumentation Cables
Unsolder Superconductors
(To be done by TD Staff in E. Barzi’s Group)

## Slide 6
Rutherford Cable
Super Conductor
To Lead Box
And Valve Box
5K LHe Super
Conductor
Cooling Lines
50K He Gas Heat
Shield Cooling Lines
Cryogenic
Instrumentation Cables
Result Would Look Something Like This

## Slide 7: Super Conductors in the Inflector Service Line

## Slide 8
Aluminum D-Tube Cooling
Electrical
Isolator
Copper Cooling Tube
Rutherford
Cable
A Pair of Aluminum-Stabilized
Super Conductor, wrapped with
Aluminum strips and soldered
THE ALUMINUM SC IS NOT
ACID-ETCHED.
Heavily Soldered Region
Super Conductors in the Service Line (Part 1)
Continue Next Page

## Slide 9
Cu cooling tube
Rutherford Cable
To Lead/Valve Box
Perform Unsolder HERE
Rutherford Cable
Super Conductors in the Service Line (Part 2)
To Previous Page

## Slide 10: Slide Chamber Out from Magnet Gap Using the Rail System
Many detailed preparation steps related to the vacuum System and magnetic field system are omitted for Clarity
Slide out
On Rails
Rails
Rails

## Slide 11
Sliding Rail Details

## Slide 12: Swapping the Cold Mass
Access Panel to Remove
The Cold Mass
Note: We have never removed this access panel since it would change the inflector alignment. So we rely on (limited) drawings of the interior and guidance from BNL.

## Slide 13: Remove the Cold Mass Alignment Screw
Upstream
Downstream

## Slide 14
Pivot
Extract

## Slide 15: Remarks
We have limited drawings of how the Cold Mass is supported Off the Cryostat.
Emails from Chien Pai at BNL indicates:
Upstream End: Cold Mass is Cantilevered Off of G10 Support Blocks sitting on Teflon Slide
Down Stream End: Cold Mass is Cantilevered Off of G10 Supports bolted to an access port

## Slide 16: Upstream Support Block
Upstream Window
Support Bolts
Cold
Mass

## Slide 17: Upstream Block

## Slide 18: Down Stream Support
Pivot Point

## Slide 19: Down Stream Support
Support Bolts
Sliding Adjustment
Pivot Point

## Slide 20: Summary
There are many Superconductor Splices in the service line. New Windings made by TD will have to be soldered to existing Rutherford Cable SC.
The Steps to extract the Inflector Cryostat should be straight forward. PPD Staff is doing the Reverse Step this Fall.
There is limited information on how the Cold mass is supported. However, we feel that there is sufficient experience and expertise to figure this out.