## Slide 1: Magnetic-flux expulsion in SRF cavities
M. Ross
SLAC, 30 June 2016
LCLS-II Review

## Slide 2: Background:
LCLS-II is a Free-Electron-Laser Facility, planned first-light in late 2019.
Key component is CW 4 GeV, 300 uA Superconducting Linac
280 1.3 GHz cavities; 16 3.9 GHz cavities in 35+2 cryomodules
16 MV/m acceleration gradient
Uses nitrogen doping to reduce low cryogenic heat-load:
10W/cavity dynamic load, 3.7 kW @ 2.0K (Q0 2.7e10)
First two cryomodules (prototypes) to be tested summer / fall 2016.
First two production cryomodules to be tested spring 2017
(Cryogenics Systems Deliveries begin March 2017)
Last Cryomodule to be delivered to SLAC fall 2018.

## Slide 3: Introduction and Welcome
Welcome to the LCLS-II Review of Magnetic-flux expulsion in SRF cavities!
Tests (using production cavity material) show a significant risk that production cavities will have 20 to 30% greater cryogenic heat load than foreseen due to strong ambient-magnetic-field flux-trapping.
Prototype cavities expelled ambient magnetic field efficiently:
the difference may be caused by differences in the bulk crystalline structure.
A modest increase in heat-treatment temperature, e.g. from 800C to 900C, may cause enough re-crystallization to substantially improve flux expulsion – and thereby reduce 2.0K heat-load.

## Slide 4: Objective and Assumptions:
We are concerned about the risk to performance, and would like to consider a path forward, including studies, performed under strict constraints of an in-progress project.
LCLS-II cavity production is now well underway
Constraints  We should:
cause no more than minimal delay,
keep risk inherently low,
make changes that are applicable during the production cycle, so that the overall linac cryogenic heat-load is reduced. (It is not practical to apply changes to the early-production CM units.)

## Slide 5: Review Charge Questions:
1) Are the planned studies (together with initial test results) on the LCLS-II material single cell cavities likely to provide sufficient evidence for poor flux-expulsion? Does the proposed recipe mitigate the risk appropriately? Are further studies required for 9-cell cavities? Dressed cavities? Material samples?
2) What are the risks associated with increased heat-treatment temperature? What can be done to protect the precision tuning of soft(er) cavities? Is the flange sealing integrity ensured (for all 6 flanges)? Do any other mechanical risks need to be considered? Might the HOM spectra be negatively affected?
3) What steps and / or studies are necessary to build confidence the proposed actions meet the three constraints listed above, associated with the production process? What are the risks of doing nothing?

## Slide 6: Proposal to be reviewed (1/2):
Complete an assessment of the data taken up to present, including single-cell, nine-cell (a few), and ambient magnetic-field suppression studies.
      Collect heat-treatment records of the 16 prototype cryomodule cavities. (at least one has been heat-treated above the nominal 800C.)
      Collect mechanical tuning-stability records for these cavities.
      Develop VT technique (to be used during production) to measure the effects of magnetic field in 9-cell bare and dressed cavities.
      Complete metallurgical crystallization testing and analysis of LCLS-II Nb sheet samples.

## Slide 7: Proposal (2/2):
Prepare to modify the cavity de-gas/doping heat-treatment recipe so that the cavity weldment is pre-annealed, i.e. the oven temperature is raised above the baseline temperature.
      Fix recipe-modification details using single-cell test results
      Evaluate associated risks, (most of which are mechanical), and develop counter-measures and test them with single cells and nine cells.
Assuming the associated risks are properly addressed, identify which cavity in the planned production cycle should be the first to receive the modified recipe.
Trigger the modified recipe to be applied following a review of 1) to 3).

## Slide 8: Review Agenda:
Intro / Welcome - Marc Ross
Flux Expulsion - Problem Description - Sam Posen
LCLS-II Production Material Evalualtion - Ari Palczewski
Improving Flux Expulsion - Anna Grassellino, Sam Posen
Cavity Production Impact - Frank Marhauser
Discussion - All

## Slide 9: LCLS-II Schedule:
First delivery of dressed cavities: July 2016
Production Finished: October 2017
  (68 weeks)
  Production is proceeding well (see Frank Marhauser). Changes would not be practical before ~ 6th module. (3 Jlab / 3 Fermilab)
First two cryomodules (prototypes) to be tested summer / fall 2016.
First two production cryomodules to be tested spring 2017
(Cryogenics Systems Deliveries begin March 2017)
Last Cryomodule to be delivered to SLAC fall 2018.

## Slide 10: Thank you!
For agreeing to participate in this hastily convened Review
Thanks to Camille and Ed for making arrangements
Thanks to presenters
Jacek Sekutowicz will be the editor of written Review Report
to be received in two weeks (15 July 2016).
(Thank you Jacek!)