## Slide 1: STF-2 Cryomodule Construction ~Assembly, Alignment and Installation~
Kirk
Cavity Group: E. Kako, T. Shishido, Kirk
Cryogenics Group: H. Nakai, Y. Kondo, K. Hara
Alignment Group: S. Araki
Magnet Group: N. Kimura, A. Yamamoto, H. Hayano

## Slide 2: Outline
STF-2 Cyomodule Construction
Connection of Cavity String and Beampipe
Cavity Alignment
Module Alignment along Beamline
Summary

## Slide 3: Brief History for STF-2 Cryomodule
Date | Content
2011 ~ 2013 | V.T. for 12 cavities / RF conditioning for 12 couplers
Jun/2013 | Cleaning up STF tunnel
Jul/2013 ~ Apr/2014 | Cavity string assembly (three times)
Oct/2013 ~ Jan/2014 | Module assembly (CM1/CM2a), Cavity/Cryomodule Alignment
Jul/2014 | Complete certification for High pressure Gas Code
Oct/2014 ~ Dec/2014 | 1st cool-down / low power test
Apr/2015 ~ Jul/2015 | 5MW Klystron / Single waveguide system completed
Jul/2015 ~ Sep/2015 | Coupler conditioning at room temperature
Oct/2015 ~ Dec/2015 | 2nd cool-down / high power test (cavity performance check)
Jan/2016 ~ Jul/2016 | Multi-beam Klystron & Waveguide system completed
Jul/2016 ~ Sep/2016 | Coupler conditioning at room temperature
Sep/2016 ~ Nov/2016 | 3rd cool-down / LFD, Q0 measurement, 8 Cavities Operation & LLRF study
F.Y. 2017 | 4th cool-down test (?)
F.Y. 2018 ~ | Beamline construction / Beam operation starts (?)
Cavity string assembly was presented in detail in TTC Topical Workshop at CEA/Saclay in 2014.
(https://indico.in2p3.fr/event/10347/?ovw=True)

## Slide 4: Complicated situation in CM construction
Three cavity strings (4+4+4=12)
Four cryo-vessels (1/3+1/3+1/3+1/2=1.5)
five support posts (3+2=5)
constructed on ground floor
Four cavities per string
Tunnel hatch for half-size cryomodule
Construction of half-size cryomodule
constructed in tunnel
1/3 cryo-vessel
1/3 cryo-vessel
1/3 cryo-vessel
1/2 cryo-vessel
CM2a was constructed by the same way as S1-Global
1+1/2 cryomodule

## Slide 5: 1+1/2 Gas Return Pipe
Full-size gas return pipe
Half-size gas return pipe

## Slide 6: Construction of STF-2 CM1①
Cavity string installation
Lining two cavity strings on rail
Attachment of thermal shield
Leveling gas return pipe

## Slide 7
Cavity string/Beam pipe connection in clean booth
Ion pump
Ion pump
Use of simply local clean booth
  Local clean booth was used for four beampipe connection parts
Exchange of metal valve near cavity string #2
  Metal valve was a little bit bigger, disturbed thermal shield attachment
Extra Argon gas purging at gate valve opened
  Usually, when gate valve opens, both sides should be under vacuum
  but, we had to do Argon gas purging for the both sides
  due to complicated process of cryomodule assembly
Local clean booth
Three degraded cavities in series
A little bit bigger metal valve

## Slide 8: Alignment work for STF-2 CMs
S. Araki
Cat’s eye
Laser tracking system
Courtesy of S. Araki
Stand for cat’s eye near cavity

## Slide 9: Result of cavity alignment
CM1 Horizontal
CM2a Horizontal
CM1 Vertical
CM2a Vertical
ILC spec.
ILC spec.
Alignment result satisfied the ILC specification!
Courtesy of S. Araki
16 points are measured for 8 cavities

## Slide 10: Construction of STF-2 CM1②
Q-magnet attachment
(collaboration with FNAL)
Attachment of thermal shield
Carrying cryo-vessels
Installation into cryo-vessel

## Slide 11: Construction of STF-2 CM1③
Putting CM1 along beamline
Putting CM2a along beamline
Connecting CM1 and CM2a
Integrated leak check
Adjustment of position
Construction finished

## Slide 12: Result of cryomodule alignment
Horizontal
Vertical
ILC spec.
ILC spec.
Courtesy of S. Araki
Alignment result satisfied the ILC specification!
5 points are measured for 5 support posts

## Slide 13: Summary
STF-2 Cryomodule construction was too complicated
STF-2 Cryomodule construction successfully completed
Significant problems in cavity string connection
Cavity/Cryomodule alignment successfully done

## Slide 14: Back-up slides

## Slide 15: Definition of 3 axes in STF tunnel
Z
X
Y