## Slide 1: European XFEL procurement strategy – lessons learned
Detlef Reschke – DESY (with J. Iversen, A. Matheisen, H. Weise)
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)
Change the partner logos or add others in the last row.

## Slide 2: Cavity production: Preparation Phase
Define final cavity design => TESLA design with minor design changes
Establishing surface treatment recipes => based on app. 50 prototype cavities
Industrialization of main Electropolishing surface treatment => set up of EP facilities at 2 companies
Preparation of detailed specifications => mechanical fabrication, surface treatment, HT integration, transport concept
Finalize a concept for documentation and data transfer
Qualification + selection of Nb / NbTi material vendors in 3 steps => 2 new companies
Concept for fulfilling PED requirements
Establishing “Long pulse” vertical acceptance test => protect HOM feedthroughs
Single-cell cavity R&D program (several aims)
R&D on Large Grain Nb material
Courtesy W. Singer

## Slide 3: Cavity production
Contract allocated to Research Instruments (RI, Germany) and E.Zanon (EZ, Italy) in equal shares end 2010:
  560 series cavities
  24 cavities w/o He-tank for QC and further R&D (EU funded: “ILC-HiGrade”)
  Option: 240 series cavity => Order allocated end 2012/beginning 2013 in equal shares
All Nb / NbTi material provided by DESY (~ 24420 pieces) => includes ordering, PED-applicable QC + parts tracking, shipment
Order placed following “Build-to-Print” strategy:
  Production has to follow specifications precisely => close supervision by expert team + frequent visits + regular reporting (no resident expert at vendor)
  No performance guarantee by vendors

## Slide 4: Cavity Surface Preparation
Two schemes for the final surface treatment: - E. Zanon: Final 10µm BCP (“BCP Flash”) - Research Instr.: Final 40µm EP
Successful mechanical production and surface preparation at both vendors!
No performance guarantee resulted in DESY taking responsibility for:
  the risk of unexpected low gradient or field emission
  retreatment (good cooperation/agreements with both vendors)
Final EP
BCP Flash

## Slide 5: Quality Management + Documentation
Courtesy W. Singer
Key technical documents: Technical Specifications + Change Reports
Quality Process based on Quality Control Plan (also for PED) including:
  Vendor internal QA, QM system
  Microsoft Project Plan for tracking of progress + schedule
  Non Conformity Reports NCR: Documentation of all NC’s including a proposal for correction procedure
  Stepwise release of production (Acceptance Levels 1, 2, 3)
All production documents (specifications, protocols, PED data, etc.) recorded electronically in data management system (EDMS)
Data analysis in cavity data base
Request Tracked e-mail communication (“tickets”)
- RF test system - direct file transfer - (manual entry)

## Slide 6: Lessons Learned
6
Concept of Preparation Phase successful
  Pre-Qualification of cavity vendors and Nb/NbTi suppliers important
  Surface treatment recipes worked well
Communication with cavity vendors and notified body of upmost importance
  Trustful cooperation from tendering until (beyond) last cavity extremely helpful incl. solving problems together
  Frequent meetings + visits; request tracked e-mails; good balance between personal contact and well-defined documentation; ...
  Rough estimate: team of about 20 colleagues (INFN Milano + DESY)
Specification successful => make it precise wrt. to critical values and tolerances, but keep the infrastructure as generic as possible
  Few mechanical tolerances to tight (inner cell shape)
  RGA spec for m>50 to tight (modified on request from 1:1000 to 1:300)

## Slide 7: Lessons Learned II
7
Effort of documentation and data transfer underestimated
  Started late and not enough man power available
  Post-documentation required a lot of additional effort
Provision of “Cavity Tuning Machine” and “HaZeMeMa” by DESY
  Successful, but labor-intensive (now used for LCLS2, Mesa, Tarla cavities)
Pores in longitudinally welded Ti “2-phase pipe” caused significant rework
  Lonigitudinally welded pipes fulfilled Spec + PED, but during orbital weld pores “widened up” => out of PED => surprise, surprise …
  Solution: Rework with seamless pipes

## Slide 8: Additional slides

## Slide 9: Transportation + Incoming Inspection
9
Transportation:
  “Cavity ready for test” requires well-defined transport concept
  Transport under vacuum => avoid particle transport
  Dedicated boxes for horizontal transport by truck (Vendor => DESY => Saclay)
  No performance degradation observed
Incoming inspection at DESY
  Basic mechanical, electrical, RF checks + final vacuum leak check before test
  Idea: Check for damages during transport
  Found: - Assembly errors + contaminations - Mechanical + electrical damages - Few leaks
  Incoming Inspection is mandatory
=> 54 Cv‘s back to vendor
Notes: Remark:
Additional and comprehensive information about NC‘s + experiences with QC concept during production extend this talk => aware that this is missing

## Slide 10: 2-Phase Line (Service Pipe) Repair Work
seamless tube
standard intersection
X-ray to certify longitudinal weld
XFEL MAC & DESY MAC Meeting – May 7, 2014
Hans Weise, DESY

## Slide 11: RF Measurement and Field Flatness Tuning using DESY-provided Tools
Both machines ready to be used at the companies (CE certified).
Machines can be operated by Non-RF-Experts.
Considerably shorter measurement / tuning time.
Automation and documentation guaranteed.