## Slide 1: Incoming Inspection, Qualification, QA/QC
F. Marhauser, K. Davis
1.3 GHz Cryomodule Production Readiness Review
13-14 September, 2016

## Slide 2
Electronic data management system (EDMS) at FNAL and JLab:
  FNAL uses Vector
  JLab uses Pansophy
QC / Inspection Travelers
Receipt inspections are in place at both laboratories
Partner laboratories have been and are still in communication to bring consistency to what data are and need to be covered in the database for proper QC
Basis of incoming inspection traveler was XFEL/DESY document (18 pages)

## Slide 3
QC / Inspection Travelers
Cavity incoming receipt inspection has been split in 3 travelers at JLab:
  Dressed Cavity Inventory Traveler
  LCLS-II Cavity RF Incoming Inspection Traveler
  Incoming Visual and CMM Inspection of Dressed LCLS-II Production Cavities
Revisions might be required based on experience with first articles

## Slide 4
Dressed Cavity Inventory Traveler
The inventory traveler accounts for the integrity of the shipment:
  Check package for damages
  Check and record status of tilt- and shock watch indicators
  Read and upload electronic data of accelerometer
  Check existence of tuner hardware (separate or assembled to split ring)
  Check existence of documentation binder (Hold Point certificates)

## Slide 5
Cavity RF Incoming Inspection Traveler
The RF incoming inspection traveler checks the integrity of the cavity by means of the fundamental passband mode frequencies:
  Check whether the accelerating mode pi-mode frequency is within the specified range at room temperature
  Measure all 9 modes of the fundamental passband with cavity under vacuum using Vector Network Analyzer
  Store and upload the data
  SOTR will analyze the data by comparing with the RF result measured by the vendor sunder the same conditions  impact on field flatness can be assessed
  Check the electrical integrity of all RF antennas (check whether pins are loose

## Slide 6
Cavity RF Incoming Inspection Traveler
RI shipped first 16 cavities in 2 shipping crate designs to test suitability for oversea shipment (note that vendors are responsible for all shipping affairs incl. crates)
Wooden crates were chosen to avoid circulation of empty boxes back to Europe
  Minimize costs, boxes can be recycled/discarded
1st design
2nd design
1st design
2nd design
Cavities received at JLab
None of the cavities received at JLab were deformed
  Frequency shift from before to after shipment acceptable
FNAL and JLab mutually agreed to choose 1st design (lighter, but more costly) but gave feedback to RI to further improve shock absorption  feedback also given to ZANON

## Slide 7
Incoming Visual and CMM Inspection of Dressed LCLS-II Production Cavities
The incoming Visual and CMM Inspection traveler covers all steps required to visually and dimensionally accept incoming cavities
The goals of this inspection covers:
  Visual inspections of the dressed LCLS-II cavity (some checks require torque wrench and caliper)
  CMM inspections (restricted to accessible components on the exterior)

## Slide 8
Incoming Visual and CMM Inspection of Dressed LCLS-II Production Cavities
The traveler currently contains 51 inspection steps
Serial numbers are recorded for various components (cavity, He tank, conical disc, right angle valve, beam tube flanges, high-Q fixed antenna)
Visual inspections covers external components such as 2-phase Helium pipe, conical discs, weld joints, He tank brackets and clamping pin, temporary protection shields for Helium tank bellows unit and He fill lines, damages to Helium bellows after removal of shielding, presence of protection caps, presence of filling line adapters, right angle valve, burst disc, tuner split ring and hardware and bellows restraint brackets, proper number of bolts, screws, nuts, washers on all flanges, bellows restraint brackets and split rings, check of proper torque values on all sealing flanges, number of He inlet ports of beam tube flanges, orientation of right angle valve, proper closure of right angle valve (caliper used), presence and damage to RF feedthroughs (HOMs, pick-up, high-Q antenna, i.e. check damage of inner conductors), damages to HOM coupler housings,
CMM check includes distance of cavity center to center line of 2-phase header pipe, parallelism of the 2-phase TEE, perpendicularity of main coupler to He lugs, distance between He vessel lugs, angle of He vessel lug surface to center plane of 2-phase header pipe

## Slide 9
Incoming Visual and CMM Inspection of Dressed LCLS-II Production Cavities
New photos are being incorporated when becoming available replacing obsolete XFEL photos and sketches

## Slide 10
  Vendor change requests partially accepted
Added
Added
  Weight of fully dressed cavity must be recorded for customs documentation/release
  HPR rinse times follow XFEL recipe (mitigation of field emission)
    Ethanol rinsing is introduced after bulk EP
Quality Assurance and Control
  We have weekly meetings for more than 1 year with both RI and EZ to talk about production and technical issues
    We now provide feedback from receipt inspections and VTA testing

## Slide 11
Hold Point Data Review
Vendors deliver QC documents for all main production steps reviewed at the 3 Hold Points

## Slide 12
Hold Point Data 1 – Mechanical Fabrication

## Slide 13
Hold Point Data 1 – Mechanical Fabrication

## Slide 14
Hold Point Data 1 – Mechanical Fabrication
Serial No. | EGS | DB |  | DB |  | DB |  | DB |  | DB |  | DB |  | DB |  | DB |  | EGL
CAV0001 | T10266 | T10146 | T10368 | T10635 | T11008 | T10387 | T11155 | T10160 | T10357 | T10499 | T11052 | T10662 | T11058 | T10150 | T11157 | T10506 | T11056 | T10569
CAV0002 | T10430 | T10425 | T10714 | T10355 | T10612 | T10640 | T11092 | T10707 | T11189 | T10486 | T10526 | T10373 | T10541 | T10443 | T10656 | T10184 | T10450 | T10032
CAV0003 | T10437 | T10189 | T10413 | T10228 | T10458 | T10712 | T11149 | T10599 | T11147 | T10672 | T11059 | T10224 | T10426 | T10359 | T10555 | T10358 | T10388 | T10291
CAV0004 | T10246 | T10145 | T11050 | T10374 | T10720 | T10671 | T11191 | T10360 | T10598 | T10308 | T10367 | T10665 | T11197 | T10077 | T10414 | T10493 | T10501 | T10281
CAV0005 | T10457 | T10488 | T10726 | T10438 | T10514 | T10079 | T10411 | T10375 | T10495 | T10773 | T11160 | T10191 | T11005 | T10348 | T10732 | T10177 | T10999 | T10628
CAV0006 | T10260 | T10608 | T11001 | T10455 | T10771 | T10610 | T11012 | T10504 | T10995 | T10448 | T10654 | T10500 | T11352 | T10099 | T10362 | T10502 | T11101 | T10899
CAV0007 | T10420 | T10489 | T10636 | T10365 | T10670 | T10372 | T10527 | T10069 | T10307 | T10226 | T10449 | T10363 | T10709 | T10116 | T10338 | T10507 | T11162 | T10898
CAV0008 | T10262 | T10062 | T10484 | T10553 | T11152 | T10427 | T10515 | T10085 | T11089 | T10436 | T10638 | T10595 | T11187 | T10091 | T10491 | T10371 | T10519 | T10317
CAV0009 | T10257 | T10096 | T10370 | T10485 | T10545 | T10415 | T10520 | T10377 | T11208 | T10383 | T11190 | T10361 | T10646 | T10340 | T10605 | T10439 | T10642 | T11112
CAV0010 | T10410 | T10081 | T10172 | T10038 | T10175 | T10068 | T10302 | T10196 | T10522 | T10064 | T10607 | T10090 | T10660 | T10083 | T10716 | T10094 | T10597 | T10616
CAV0011 | T10275 | T10772 | T10985 | T10084 | T10440 | T10023 | T10304 | T10021 | T10998 | T10098 | T10339 | T10461 | T10774 | T10652 | T11049 | T10073 | T10259 | T10132
CAV0012 | T10271 | T10066 | T10364 | T10037 | T11323 | T10009 | T10269 | T10092 | T11164 | T10667 | T11002 | T10147 | T10994 | T10174 | T11188 | T10462 | T10643 | T10300
CAV0013 | T11009 | T10022 | T11156 | T10058 | T11151 | T10724 | T11148 | T10554 | T11011 | T10188 | T11051 | T10342 | T10609 | T10346 | T10647 | T10093 | T11013 | T10323
CAV0014 | T11097 | T10655 | T11010 | T10552 | T11158 | T10199 | T10487 | T10169 | T11087 | T10176 | T10337 | T10117 | T10382 | T10195 | T10497 | T10017 | T10442 | T10848
CAV0015 | T10309 | T10167 | T11098 | T10645 | T11166 | T10719 | T10993 | T10155 | T10380 | T10020 | T10310 | T10024 | T10494 | T10551 | T11006 | T10089 | T10496 | T10280
CAV0016 | T10252 | T10144 | T10183 | T10376 | T10717 | T10118 | T10713 | T10018 | T10596 | T10097 | T10639 | T10385 | T10711 | T10516 | T10710 | T10087 | T10603 | T10618
CAV0017 | T10244 | T10498 | T11161 | T10095 | T11349 | T10540 | T11000 | T10492 | T10708 | T10661 | T11060 | T10723 | T11090 | T10173 | T11055 | T10444 | T10531 | T10287
CAV0018 | T10242 | T10143 | T11125 | T11704 | T11778 | T11402 | T11924 | T11712 | T11745 | T11448 | T11801 | T11616 | T11948 | T11467 | T11813 | T11557 | T11675 | T10034
CAV0019 | T10267 | T10225 | T11054 | T11723 | T11726 | T11392 | T11660 | T11601 | T11837 | T11484 | T11766 | T11403 | T11684 | T11564 | T11847 | T11476 | T11902 | T10055
CAV0020 | T10270 | T11418 | T11873 | T10178 | T10617 | T11443 | T11769 | T11510 | T11762 | T11477 | T11676 | T11396 | T11661 | T11455 | T11756 | T11705 | T11866 | T10838
Cavity half cell composition

## Slide 15
Hold Point Data 1 – Mechanical Fabrication
before chemistry

## Slide 16
Hold Point Data 2 – After N-Doping
  N-Doping of multiple cavities in furnace (so far 2 cavities at a time in furnace)
26 mTorr = 0.0347 mbar
CAV0001 & CAV0002
+/- 15 % pressure limits
2 minutes N-doping
6 min. at 800 deg. C
Temperature (deg. C)
N-Pressure (mbar)
CAV0200 & CAV0201
mass flow (l/sec)
N-Pressure (mbar)
1e-2
2e-2
3e-2
4e-2
5e-2
6e-2
7e-2
8e-2
0
0.5
1
1.5
2
2.5
3
3.5
2 minutes N-doping

## Slide 17
Hold Point Data 2 – After N-Doping
  Residual Gas Analysis
    Partial pressure for any mass > 45 should be at least 300x smaller than sum of peaks of partial pressures up to mass 45 (reference)
CAV0001 & CAV0002
AMU
RGA_end
Pressure (mbar)
300 x smaller than reference
1000 x smaller than reference
Reference = 1.31e-7 mbar
CAV0200 & CAV0201
RGA_end
AMU
Pressure (mbar)
300 x smaller than reference
Reference = 1.49e-7 mbar
1000 x smaller than reference

## Slide 18
Hold Point Data 2 – Before and After bulk EP (1st Articles)
  Wall thickness measurements before and after bulk EP
  New compared to XFEL recipe, but so far limited to 1st articles only
  Reason is to understand
    1) Actual removal at equators given that EP is controlled by removal by weight/integrated current
    2) Differential removal from equator to iris/beam tubes
    3) Gain insight into process volatilities, e.g. variable removal along cavity cells

## Slide 19
Hold Point Data 3 – After Completion of Fully Dressed Cavity
  Cavity frequency of bare cavity after 1st bench tuning (after bulk EP/N-doping)

## Slide 20
Hold Point Data 3 – After Completion of Fully Dressed Cavity
  Cavity frequency of bare cavity after 2nd bench tuning (after final EP)

## Slide 21
Hold Point Data 3 – After Completion of Fully Dressed Cavity
  Field Flatness – Requirement ≥ 90% after completion (98% after 2nd tuning)

## Slide 22
Hold Point Data 3 – After Completion of Fully Dressed Cavity
  Eccentricity of cells

## Slide 23
Hold Point Data 3 – After Completion of Fully Dressed Cavity
  Frequency in vacuum after helium tank welding (before shipment)

## Slide 24
Hold Point Data 3 – After Completion of Fully Dressed Cavity
  Includes e.g. Helium leak checks, RGA spectra (before after final HPR), HPR details, drying time, US degreasing to spec'd rinsing resistance, dimensional and frequency reports (field flatness, passband modes), cavity cell eccentricity measurement, transfer measurements, pressure test and report of visual inspection of welding seams (TPI), cavity weighing

## Slide 25
QC Hold Point Status per 8/17/2016
Cavity # | Hold Point 1 release | Hold Point 2 release | Hold Point 3 release
1 | YES | YES | YES
2 | YES | YES | YES
3 | YES | YES | YES
4 | YES | YES | YES
5 | YES | YES | YES
6 | YES | YES | YES
7 | YES | YES | YES
8 | YES | YES | YES
9 | YES | YES | YES
10 | YES | YES | YES
11 | YES | YES | YES
12 | YES | YES | YES
13 | YES | YES | YES
14 | YES | YES | YES
15 | YES | YES | YES
16 | YES | YES | YES
17 | YES | No data received yet | No data received yet
18 | YES | No data received yet | No data received yet
19 | YES | No data received yet | No data received yet
20 | YES | No data received yet | No data received yet
Hold Point 1
Bare cavity after mechanical fabrication
Hold Point 2
Bare cavity after main EP and N-doping
Hold Point 3
Fully dressed cavity after post- processing just before shipping

## Slide 26
QC Hold Point Status per 8/25/2016
Cavity # | Hold Point 1 release | Hold Point 2 release | Hold Point 3 release
1 | YES | YES | No data received yet
2 | YES | YES | No data received yet
3 | YES | YES | No data received yet
4 | YES | YES | No data received yet
5 | YES | YES | No data received yet
6 | YES | YES | No data received yet
7 | YES | YES | No data received yet
8 | YES | YES | No data received yet
9 | YES | No data received yet | No data received yet
10 | YES | No data received yet | No data received yet
11 | YES | No data received yet | No data received yet
12 | YES | No data received yet | No data received yet
13 | YES | No data received yet | No data received yet
14 | YES | No data received yet | No data received yet
15 | YES | No data received yet | No data received yet
16 | YES | No data received yet | No data received yet
Hold Point 1
Bare cavity after mechanical fabrication
Hold Point 2
Bare cavity after main EP and N-doping
Hold Point 3
Fully dressed cavity after post- processing just before shipping

## Slide 27: Jefferson Lab Vertical Test Area
Eight Vertical Dewars
  Radiation Shielding (6/8)
  Magnetic shielding and compensation coils (7/8)
  Over 4400 vertical cavity tests since 1995
  LHe supply 150L/hr steady state (450 L/Hr short-term)
  Recent upgrade projects:
    PLC-based cryo controls
    Digital LLRF systems
    1300 MHz RF Power Amps

## Slide 28: LCLSII Production Cavity Vertical Acceptance Testing
Day 1: - External cleaning and pass into Cleanroom
    - Mount the cavity to vertical test stand
    - Establish test stand vacuum and open cavity isolation valve (actively pumped during RF test)
Day 2: - Leak check
    - Transfer to Vertical Staging Area (VSA)
    - Mount temperature sensors and magnetic sensors (as required)
    - Cool 4K (p.m. fully automated)
Day 3: - Cool 2K (Automated, but with operator monitoring)
    - HOM survey using VNA, Matlab curve fitting software
    - High Power RF test
    - Warm up
Day 4: - Warm up
Day 5: - Remove cavity from dewar (a.m.), next cavity loads (p.m.)

## Slide 29: LCLSII Production Cavity Vertical Acceptance Testing
Work flow & throughput
  Goal: qualify eight cavities every 5 weeks
  Schedule: Test 2 to 3 cavities per week, 30% fail/rework
  Schedule risk mitigation –
    Two dewars are qualified for LCLSII 9-cell testing (D7 & D8). We could investigate using D3 and D4 (275 cm vs 336 cm).
    D7 and D8 can each support two tests per week (3 days per test cycle, warmups can occur over weekends and unattended).
    Cryo plant is shared between cryomodule test and vertical test
      Cryomodule cooldowns are scheduled for weekends
      Careful cryo coordination between CMTF and VTA is required
      Availability of cryo plant could be mitigated by testing at other labs

## Slide 30: Cavity Delivery Schedule
Schedule for delivery of 133 Cavities
  First eight production cavities (RI) at Jlab
  Eight more scheduled during Sept at Jlab (EZ).
  4 cavities per week Oct 16 through mid-Feb 17.
  8 cavities per week mid-Feb 17 through mid-Apr 17.
  4 cavities per week May 17 through June 17
  Assemble one string (8 cavities) every 5 weeks
  Qualified cavities not needed for the next string assembly will be valved out under vacuum, bagged and stored outside the cleanroom in their original shipping containers
Parts in Circulation Plan
  50% of cavity total PIC allotted based on 5 wk/CM
  PIC returned to vendor after string assembly

## Slide 31: VTA Performance Summary for JLab’s Production Cavities (Status 9/10/2016)
Cav. SN | Initial FE onset (MV/m) | Q0 at 2K at 16 MV/m | Final Emax (MV/m) | Final Q0 at Emax | Final radiation max | Comment
0005 | No FE | 2.2e10 | 16.4 | 2.2e10 | 0.001 mR/h | Quench Limited
0002 | No FE | 2.6e10 | 24.2 | 2.6e10 | 0.006 mR/h | Post degauss of HV Admin Limited
0001 | No FE | 2.3e10 | 24.1 | 1.7e10 | 0.001 mR/h | Admin Limited
0004 | No FE | 2.5e10 | 21.0 | 2.5e10 | 0.004 mR/h | Cable BD limited 21 MV/m
0009 | No FE | 2.7e10 | 17.1 | 2.7e10 | 0.001 mR/h | Quench limit 17.1 MV/m
0012 | No FE | 2.7e10 | 22.1 | 2.7e10 | 0.001mR/h | Cable BD limited 22.1 MV/m
0010 | No FE | 3.0e10 NbTi flange | 23.0 | 2.1e10 | 983 mR/h | Radiation limited, plan to re-rinse, retest 9/16
0014 | No FE | 2.7e10 | 24.0 | 2.7e10 | 0.001 mR/h | Admin limited
Average |  | 2.5e10 SS only | 20.8 | 2.4e10 SS only |  | Stainless Steel flange averages
Fully Qualified, no NCRs
NCR: Use As Is, no rework planned
NCR open,
rework/retest planned
Q0 = 2.5e10 @ 16 MV/m
(with SS flange hardware,
equals ~2.7e10 without flange losses)
Field emission onset
> 17.5 MV/m
Min. Eacc = 19 MV/m
Acceptance criteria: