## Slide 1: Fermilab pCM test results
E. Harms, G. Wu
LCLS-II 1.3 GHz Cryomodule Production Readiness Review
13-14 September, 2016

## Slide 2: Outline
  pCM Test plan and basis
  Installation & Test chronology
  pCM results to date
  Magnetic Field Management
  Cavity performance measurement
  Acceptance Criteria and production readiness
  Next steps
  Documentation, especially Traveler
  Summary

## Slide 3: Test plan
  Detailed plan includes
    Prep for Delivery
    Installation
    Warm Checkout & Cold Test Preparation
    Cooldown
    Cold Testing
    Extended Tests
      Up to 6 Periods of Fast Cooldown Studies
      Slow Cooldown
    Warm Up
    Removal
  Multi-prong development
    Past experiences
    Working group
    Testing workshop
    Minimum Acceptance criteria
  Minimum Acceptance criteria addressed in appropriate testing steps

## Slide 4: Acceptance criteria

## Slide 5: Installation & Test chronology
  Installation
    begun in July, ~6 weeks duration
  Warm checkout
    begun late in installation
  Off resonance conditioning
    Cavities 1-5: 25 to 26 August
    Cavity 8: 12 to 13 September
  Demagnetization
    27 August
  Magnet/supply
    testing since 29 August
  50 K cooldown
    27 to 29 August
  ‘Fast’ cooldown to 4 K
    30 August
  2 K cooldown
    ongoing since 30 August
  ORC
    permission for cold, full power operation received 9 September
  Cold testing
    in progress

## Slide 6: pCM results/Acceptance criteria
Criteria | Design Validation | Workstation | Status
Cavity beamline vacuum Cold (2K) 1x10-10 Torr Warm (RT) 1x10-8 Torr | Vacuum pumping and leak determination | WS 1 – CR Assembly | Warm = 2.5 X10-9 Cold = 4X10-10 Coupler = 5.5X10-9 Insulating vacuum = 5X10-7 (previously identified leaks)
Center Frequency 1.300000 GHz +/- 20kHz | Cavity Fabrication Target frequency |  | All cavities tuned to close to 1.3 GHz
Tuner range –slow 450 kHZ, fast 0-500 Hz | Tuner Design | WS3 – CMA I | All slow tuners tested to at least 64 kHz, most ~300 kHz
Notes: Elvin

## Slide 7: pCM results/Acceptance criteria
Criteria | Design Validation | Workstation | Status
The magnet package is verified electrically to be without shorts or opens and can be operated at a current of at least 20 A without quenching | Magnet Installation | WS3 – CMA II | Electrical checkout good, 20A tests imminent
Nominal FPC Qext = 4E7 with range verified from 1E7 to 6E7 | FPC/CM design verification | WS3 – CMA II | to be determined
Notes: Elvin

## Slide 8: pCM results/Acceptance criteria
Criteria | Design Validation | Workstation | Status
Individual cavities reach at least 16 MV/m | Overall Design and Assembly Validation | WS 1 – CR Assembly | to be tested
Field emission onset ≥ 14 MV/m for each cavity individually | Particle Free Assembly | WS 1 – CR Assembly | to be tested
HOM Qext ≥ 5 x 1011, maximum power measured out of a single HOM is 1.5 W at nominal gradient of 16 MV/m with the forward power set to 2.5 kW for at least 10 hours or until the FPC window temperature reaches equilibrium | HOM notch tuning | WS2 – CMA I | to be tested
Notes: Elvin

## Slide 9: pCM results/Acceptance criteria
Criteria | Design Validation | Workstation | Status
The BPM shall be verified electrically to be without shorts or opens, with cross-talk between electrodes ≤ -30dB. The difference in S-parameter (S21) between electrodes is < 1dB over a frequency range of 0.5 to 2.5 GHz. | BPM design and assembly | WS 1 – CR Assembly | testing in progress
Average CM Q0 ≥ 2.5x1010 at 16 MV/m as measured after at least 10 hours c.w. operation or until the FPC window temperature reaches equilibrium | Magnetic Hygiene and Shielding | WS 2/3 – CMA I/II | to be tested, partially validated
Notes: Elvin

## Slide 10: pCM results/Acceptance Criteria
Measure total static heat load on the CM with all cavities operating at 16 MV/m and document for comparison with the LCLS-II Cryogenic Heat Load table developed by Tom Peterson. A summary of these values is listed below for reference assuming a Q0 = 2.5e10 and all 8 cavities are operating. |  |  | WS2-5 – Final Assembly
Dynamic 2K = 92 W | Dynamic 5K = 8 W | Dynamic 45K = 92 W | 
Static 2K = 7 W | Static 5K = 17 W | Static 45K = 123 W | 
Total 2K = 99 W | Total 5K = 25 W | Total 45K = 215 W | 
To be tested
Notes: Genfa

## Slide 11: Magnetic field management
Demagnetization (results)
Active cancellation (results)
Fast cool down (in progress)
Notes: Genfa

## Slide 12: Vacuum vessel magnetic field management
Vessels come with high, non-uniform residual magnetic fields
Demagnetization reduces magnitude by a factor of 10
  Increases magnetic shielding efficiency of vessel
Bavg > 500 mG
↓
<50 mG & uniform
Bz > 300 mG
↓
<50 mG & uniform
S. Chandrasekaran and colleagues
Notes: Genfa

## Slide 13: Magnetic field management ( Cryomodule Demagnetization )
S. Chandrasekaran and colleagues
Notes: Genfa

## Slide 14: Magnetic field management ( Demagnetization )
S. Chandrasekaran and colleagues
Notes: Genfa

## Slide 15: Magnetic field management ( Demagnetization )
S. Chandrasekaran and colleagues
Notes: Genfa

## Slide 16: Magnetic field management (Active Coil Cancellation)
S. Chandrasekaran and colleagues
Notes: Genfa

## Slide 17: Magnetic field management (Active Coil Cancellation)
If magnetic shields have consistent high permeability as in pCM, cryomodule will have very low remnant field.
Active coil cancellation will depend on the ambient fields at final installed location.
7 production cryomodules and 2 prototype cryomodules will be available to implement the active cancellation.
All internal fluxgate sensors reads <1.5 mG in Fermilab pCM
Notes: Genfa

## Slide 18: Magnetic field management (Flux expulsion)
Several fast and slow cool down cycles are planned for extended studies.
  Cool down procedure will be finalized for production cryomodule testing.
Fast cool down is needed due to the limited diagnostics (no internal fluxgate sensors in production cryomodule.)
Notes: Genfa

## Slide 19: Magnetic field management
Magnetic shield design is successfully validated
Magnetic hygiene is successfully implemented
Demagnetization is successful and will be standard in production
Notes: Genfa

## Slide 20: Cavity Performance Measurement - Calibration
RF calibration
  Forward power at SSA output before the circulator
    Minimize the directional coupler signal deviation due to reflected power
    Calibration using calorimetric load
  Transmitted power and HOM power
    Network analyzer
  Qext1
    Fast oscilloscope for decay time
    RF power decay
Heatload
  Massflow vs. known heater power
Notes: Genfa

## Slide 21: Cavity Performance Measurement - Gradient
Method A – Forward Power (Production method)
  Measure FPC Qext and forward power
Method B – Transmitted Power
  Measure transmitted power and field probe Qt (using VTS/HTS Qt
Notes: Genfa

## Slide 22: Cavity Performance Measurement - Heatload
Method A – Mass flow change
  Measure mass flow delta to extrapolate heat load
Method B – Measure compensation heater (production method)
  Maintain constant mass flow
  Measure RF compensation heater power
Notes: Genfa

## Slide 23: pCM cryomodule test result
Total Voltage | pCM dynamic heatload | pCM total heatload
Cavity | VTS/HTS Eacc | VTS Q0@16MV/m | pCM gradient | pCM FE onset | pCM Q0
TB9AES021 | 23 | 3.08e10 |  |  | 
TB9AES019 | 19.5 | 2.82e10 |  |  | 
TB9AES026 | 21.4 | 2.57e10 |  |  | 
TB9AES024 | 22.4 | 2.95e10 |  |  | 
TB9AES028 | 28.4 | 2.81e10 |  |  | 
TB9AES016 | 18 | 2.75e10 |  |  | 
TB9AES022 | 21.2 | 2.77e10 |  |  | 
TB9AES027 | 22.5 | 2.75e10 |  |  | 
Notes: Genfa

## Slide 24: pCM cryomodule test result – HOM/FP
Cavity | HOM1 Qext | HOM2 Qext | Field Probe Qext | Note
TB9AES021 |  |  |  | 
TB9AES019 |  |  |  | 
TB9AES026 |  |  |  | 
TB9AES024 |  |  |  | 
TB9AES028 |  |  |  | 
TB9AES016 |  |  |  | 
TB9AES022 |  |  |  | 
TB9AES027 |  |  |  | 
Notes: Genfa

## Slide 25: Achievements to date
  Installation – went about as well as it could
    Good leak check; pre-existing insulating vacuum vessel leaks verified
    cold connections (including the line B Indium seal) checked out and verified cold
  Cryo
    Plant and compressors very reliable
    Control loops being established
    Cooldown to 4 K went as expected and met requirements including magnetic flux
    Fast cooldown went well and met requirements (30 g/s and could have been more)
    Investigating control stability of CM on 0.5% slope
    Operating at 2K with cold compressors will require dedicated time
  Magnetic system checks on track
Notes: Elvin

## Slide 26: Achievements to date
  RF system perform as advertised
    All SSA’s operated and calibrated with loads at end of waveguide network
    Most calibrations completed and verified
  Tuners
    All SSA’s operated at 200 Watts cw into each cavity; All Tuners exercised to get close to resonance
    Thermal shorting looks very good – DT ~3 K during extended operation
    Heaters operated including control loops – all good
  LLRF
    Fermilab single cavity version routinely used – frequency lock demonstrated
    8-cavity system undergoing final checks
    SLAC/LCLS-II hardware here and being installed
  Final checkout of the test stand with the CM in place
    Instrumentation, timing, data logging, interlocks all in operation and interfaced via Controls system
Notes: Elvin

## Slide 27: Next steps
  Move cavities exactly to resonance
  Bring up power to 1500 Watts
    preliminary gradient check (pending final calibrations)
    field emission/dark current
  Complete minimum acceptance checks
Notes: Elvin

## Slide 28: Documentation - Traveler
  Imperative to document pCM installation & testing activities as completely as possible
    assure consistency
    check against acceptance criteria
    as complete a record of performance as practical for LCLS-II operation
  Use available tools (and some new ones)
    Electronic Log
    Reports
    Travelers
    Controls system archival system
    High capacity/high speed data collection

## Slide 29: Test Traveler Contents
  Same platform as for other activities – Vector
  Contents based on
    Minimum acceptance criteria
    Installation activities flow
    Test plan developed by joint working group last year
  Reviewed and refined by expected users
  In use, reviewed at least weekly
  Further revisions based on experience
  Use as is for pCM

## Slide 30: Test Traveler Contents
  RFCG 464255, LCLS-II Cryomodule Testing at CMTF
  https://vector-onsite.fnal.gov/GenerateTravelerRequest.asp?qsDocID=18229
  Ongoing refinement
  Next version released for First Production CM

## Slide 31: Summary
  pCM is on test stand and mostly cooled down
  Magnetic field management is validated/successful
  Warm testing complete/successful
  Cold tests in progress – so far good, cavity performance remaining
  2 K operation is a learning experience
  Initiating a testing program + comissioning a new facility
  Suite of documentation tools, especially Traveler in use

## Slide 32: Charge
1 Technical Scope and Schedule (FNAL and JLab)
  a. Is the scope of work defined properly? yes
  b. Is the schedule reasonable to achieve the defined scope? to be determined
  c. Are there opportunities for schedule advancement or schedule recovery in cases of cryomodule rework or repairs?
  d. Are the prototype test-results, as available, consistent with initial acceptance criteria? yes, but….
4 ES&H and Work Planning and Control (FNAL and JLab)
  a. Is there evidence of work planning and control pocesses in day-to-day procedures? yes
  b. Have all safety risks been identified and ranked? yes
  c. Is there evidence of appropriate hazard mitigation plans? yes
6 Production Management (FNAL and JLab)
  d. Have lessons learned and traveler documentation from Eu-XFEL, Fermilab CM02, and JLab 12 GeV Upgrade been incorporated into the assembly procedures and component/system check-out planning?
  e. Are all travelers and assembly procedures updated and available? yes
  f. Is there an agreed upon plan in place to collect and deliver all relevant inspection, assembly and testing data to SLAC for each cryomodule? handoff agreement being developed

## Slide 33
Thank you for your attention – Questions?