## Slide 1
Cons Gattuso
All Experimenters Meeting
Summer Shutdown
9/12/16

## Slide 2: Weekend Power Outages
CUB Power Outage from 5 pm Friday until Sunday afternoon 5 pm
The XGC-108 computer room (across from the Main Control Room) will be without cooling due to CUB Maintenance Friday afternoon through Sunday afternoon.
    All devices in this room need to be powered down starting at 4pm 9/16 and completed no later than 5pm.
    During the outage NO controls system, clock system, desk top networking in AD and AD file serves ( no access to remote drive)
    When cooling is restored (scheduled 5-6 pm Sunday 9/18) systems will be restored starting with networking.
  The official page can be found using this link
    http://www-ad.fnal.gov/ops/schedule.html

## Slide 3: Beam to BNB
On schedule for the end week 10 (~October 10th )
  what's left to do…
    Booster RF buss installation from BRF21/22
    Complete repairs on the MI-8 emergency exit door
    Safety system testing
      Linac/Booster/ 8- Gev line/ MI-12A/B/ Muon campus Transport
    Muon campus transport enclosure
      Safety system gate boxes and cables pulls need to be done
      Re-route power to a chipmunk
    Linac
      Plate heat exchangers need to be reinstalled and system fired up
    MI-10 enclosure
      Interlock tested
      LOTO reconfiguration needs to be complete

## Slide 4: Schedule

## Slide 5
Extra slides