## Slide 1
Keith Gollwitzer
All-Experimenters’ Meeting
October 10, 2016
Proton Improvement Plan Update

## Slide 2: Proton Improvement Plan Goals and Scope (Established in 2011)
Increase the beam repetition rate from the ~7.5 Hz to 15 Hz
  Need at least 9 Hz for NOvA 12-batch slip-stacking
  Requires RF cavities refurbishment, RF Systems
  Eliminate major reliability vulnerabilities and maintain reliability at present levels (>85%) at the full repetition rate
Eliminate major obsolescence issues
Increase the proton source throughput, with a goal of reaching >2E17 protons/hour
  Presently operating up to 1.8E17 protons/hour
    Shielding Assessment being done for 2.7e17 protons/hour
Ensure a useful operating life of the proton source through at least 2025 (extended to 2030 to accommodate PIP-II)

## Slide 3: PIP –Five Years Completed!
Started officially October 2011
  Upgrade Linac & Booster for NOvA, BNB, & Muon experiments
  More than double flux, rep rate, run for the long-term
Much has been achieved
  Booster pulsed @ 15 Hz – 20 refurbished cavities
  Beam on at 15 Hz – supported 700 kW operations
  Operated at limit of current shielding assessment
Several major tasks to complete:
  Linac Modulators
  Linac Laser Notcher
  Booster RF Stations 21 & 22
  New Cavities
  Beam physics, instrumentation, collimation

## Slide 4
Proton Improvement Plan Bill Pellico Bob Zwaska, Deputy Kenneth Domann, Project Controls Valeri Lebedev, Senior Physicist
Booster Keith Gollwitzer
200 MHz RF Power System Fernanda G. Garcia
High-Level RF Fernanda G. Garcia
Linac Modulator Matt Gardner
7835 Procurement Fernanda G. Garcia
Instrumentation Craig Drennan
Utilities
Matthew Gardner
Power Distribution Ryan Crawford
RF John Reid
Anode Supply Ryan Crawford
Bias Supply Pat Sheahan
New Tuners Matt Slabaugh
Replacement Cavities
Tom Kroc
Cavity 1013 Matt Slabaugh John Reid
Accelerator Physics Bob Zwaska
Booster Collimation Valeri Kapin
Radiation Shielding Keith Gollwitzer
Alignment & Aperture Kiyomi Seiya
Booster Notcher Salah Chaurize
Low-Conductivity Water System David Hixson
Power Distribution Ryan Crawford
Vacuum System Dave Augustine
Solid State Upgrade John Reid
Power Amplifier Steve Kotz
Driver Module Tom Kubicki
Cavity Test Stand Pat Sheahan
Linac Notch Creation Dave Johnson
Simulations & Studies Valery Kapin
Accelerator Physics Valeri Lebedev
Vacuum System Dave Augustine
Modulator Rene Padilla
Installation Rene Padilla Steve Kotz
Instrumentation Craig Drennan
Dampers Nathan Eddy
Utilities Todd Sullivan
Booster Cogging Kiyomi Seiya
Beam Position Monitors Nathan Eddy
Simulation & Studies Bob Zwaska
Linac Fernanda G. Garcia
Cavity & Tuner Refurb. Matt Slabaugh
RFQ Injector C. Y. Tan
Beam Position Monitors Nathan Eddy
Low-Cond. Water System Matt Gardner
Perpendicular Cavity CY Tan
Cavities 21&22 Matt Slabaugh Stations 21&22 Tom Kubicki
PIP has 34 Subprojects
24 are completed and closed
Completed
Where PIP effort has been since last AEM
Linac Modulator
Laser Notcher
RF Cavities 21 & 22
RF Stations 21 & 22
Perpendicular (2nd harmonic) Cavity
Booster Vacuum System - Completed

## Slide 5: PIP - Linac 200 MHz RF Power System – Marx Modulators
35 kV Marx Modulator Upgrade
  28-cell unit in operations - LRF1
    Several months of stable operation
  54-cell design for other stations
    Prototype nearly complete
    Will install at LRF5 after shutdown
    Will be able to switch in and test
Preparing to build 4 more modulators
  Major procurements have started
  Install over next two shutdowns
  Plan completion in 2018
New
Old

## Slide 6: PIP - Linac Laser Notcher Create loss @ 750keV, instead of 400MeV
  Complete system assembled and tested in lab at 15 Hz
    Issues with stability under control, for the moment
  Full system installed into Linac
    Notching seen; not as efficienct as desired

## Slide 7: PIP-Booster RF Cavities & Stations 21 + 22
Restoring two previous Booster cavities and establishing two new RF Stations
  Gain further 10% in accelerating voltage and overhead
Cavity 21 is complete - await testing
Cavity 22 dismantled and parts in machine shop for modification/rework
New stations being built in Booster Gallery and Tunnel
  New room for power supplies, amplifiers, controls, etc.
  New runs of striplines to tune cavities
  New slots in Booster available
Schedule:
  Cavity 21 will be ready to go in after shutdown into existing RF station, Cavity 22 later this year
  RF stations 21+22 power systems will be finished over the winter; shutdown work has prepped one slot with second slot to be done later

## Slide 8: New Buss Bar being installed/hung

## Slide 9: New RF Cavities
Replacement Cavities
  Long term operations
  Avoid known weak points of existing cavities
  Higher current operations
    Compatible with PIP-II+ requirements
Harmonic Cavity
  Perpendicular biasing
  Improve injection capture & transition
R&D underway
  Tests of tube amplifiers at 76 & 106 MHz
  Tests of solid-state drivers
  Tests of bonding for garnet pieces
Work on final design
  Large solenoid & PS to bias the garnets
  Thermal design is critical to making a reliable design
Half the length
of standard RF
cavity – yet with
more gap voltage

## Slide 10: Summary
PIP has made Booster ready for 15 Hz beam
Further improvements are for reliability/modernization and loss reduction
Major Replacement of Linac Modulators underway
Linac Laser Notcher is nearing operational tests
Additional Booster cavities to be implemented
  2 additional stations for additional RF voltage & reliability
  Harmonic Cavity
  Replacement Cavities