## Slide 1
Paul Derwent
DOE Independent Project Review of PIP-II
15 November 2016
PIP-II R&D Program

## Slide 2: Paul Derwent
Scientist , PhD 1990 University of Chicago
  20+ years in Accelerator Division
    Antiproton source: design, fabrication, installation, commissioning of Accumulator stacktail stochastic cooling system, achieved record accumulation rates
    Department Head: Recycler (2006-2009), PIP-II (2014-present)
    Associate Project Manager for Accelerator & NuMI Upgrades, NOvA CD-4 2014 (2009-2014)
    Deputy Project Manager for Development & Accelerator Integration

## Slide 3: The PIP-II R&D Program
The purpose of the R&D program is to mitigate technical and cost risks, by validating the choices made in the PIP-II facility design and by establishing fabrication methods for major sub-systems and components, including the qualification of suppliers
  Technical risk: impair the ability to meet fundamental performance goals
  Cost/Schedule risk: compromise the ability to meet currently understood cost or schedule goals
    CD-2: Approve performance baseline
    CD-3: Approve start of construction
  To complete in advance of CD-3

## Slide 4: PIP-II Scope
Section | Freq | Energy (MeV) | Cav/mag/CM | Type
RFQ | 162.5 | 0.03-2.1 |  | 
HWR (opt=0.11) | 162.5 | 2.1-10.3 | 8/8/1 | HWR, solenoid
SSR1 (opt=0.22) | 325 | 10.3-35 | 16/8/ 2 | SSR, solenoid
SSR2 (opt=0.47) | 325 | 35-185 | 35/21/7 | SSR, solenoid
LB 650 (opt=0.65) | 650 | 185-500 | 33/22/11 | 5-cell elliptical, doublet*
HB 650 (opt=0.97) | 650 | 500-800 | 24/8/4 | 5-cell elliptical, doublet*
*Warm doublets external to cryomodules All components CW-capable |  |  |  | 
PIP-II Injector Test

## Slide 5: Primary areas to address technical Risk
Development and integrated systems testing of PIP-II Front End components (PIP-II Injector Test)
Development and demonstration of cost effective superconducting radio frequency acceleration systems at three different frequencies and with rf duty factors ranging from 10% to 100%
Development of requisite capabilities at international partner institutions to successfully contribute to PIP-II construction
Development of a Booster injection system design capable of accepting extended beam pulses from the PIP-II linac
Development of systems designs capable of supporting a 50% increase in the proton beam intensity accelerated and extracted from the Booster/Recycler/Main Injector complex

## Slide 6: PIP-II Injector Test: PIP2IT
Scope:
  A CW H- source delivering 5 mA at 30 keV
  A low energy beam transport (LEBT) with beam pre-chopping
  A CW RFQ operating at 162.5 MHz and delivering 5 mA at 2.1 MeV
  A medium energy beam transport (MEBT) with integrated wide band chopper and beam absorbers capable of generating arbitrary bunch patterns at 162.5 MHz, and disposing of up to 5 mA average beam current
  Low b superconducting cryomodules capable of accelerating 2 mA of beam to 25 MeV
  Associated beam diagnostics
  Beam dump capable of accommodating 2 mA at full beam energy for extended periods.
  Associated utilities and shielding

## Slide 7: NB
two different approaches coming up

## Slide 8: PIP-II Injector Test: PIP2IT
The PIP-II Injector Test (PIP2IT) facility replicates the front end of the PIP-II linac through the first SSR1 cryomodule. PIP2IT is intended to serve as a complete systems test that will reduce technical risks associated with the PIP-II linac in both pulsed and CW operating modes. It is anticipated that PIP2IT will be operated for several years beyond the initiation of PIP-II construction, with the eventual relocation of major PIP2IT components and systems into the PIP-II linac enclosure, where they will serve as part of the PIP-II front end. The construction and operating period of PIP2IT splits naturally into two phases. The mission will evolve over these two phases as follows:
Phase 1 (present through PIP-II CD-3): The mission of PIP2IT during Phase 1 is the retirement of risks associated with operation of the PIP-II linac in pulsed mode as required for neutrino operations and described in the CDR (1% duty factor).
Phase 2 (post-CD-3): The mission of PIP2IT during Phase 2 is the retirement of risks associated with CW operations, in particular as related to utilization of the PIP-II linac for a second generation Mu2e experiment

## Slide 9: PIP2IT: Deliverables
PIP2IT will address the address/measure the following:
  LEBT pre-chopping : Demonstrated
  Vacuum management in the LEBT/RFQ region : Demonstrated
  Validation of chopper performance
    Bunch extinction, effective emittance growth
  MEBT beam absorber
    Reliability and lifetime
  MEBT vacuum management
  CW Operation of HWR
    Degradation of cavity performance
    Optimal distance to 10 kW absorber
  Operation of SSR1 with beam
    CW and pulsed operation
    resonance control and LFD compensation in pulsed operations
  Emittance preservation and beam halo formation through the front end
Collaborators
ANL: HWR
LBNL:LEBT, RFQ
SNS: LEBT
BARC: MEBT, RF
IUAC: SSR1
40 m, ~25 MeV
30 keV
RFQ
MEBT
HWR
SSR1
HEBT
LEBT
2.1 MeV
10 MeV
25 MeV
2017
Now
2015
2019
2018

## Slide 10: NB
2nd one

## Slide 11: PIP2IT: Phases and Deliverables
PIP2IT will address the address/measure the following:
Phase 1 (present through PIP-II CD-3): retirement of risks associated with operation of the PIP-II linac in pulsed mode as required for neutrino operations and described in the CDR (1% duty factor). The primary risks to be retired during this period include:
  Achievement of required beam characteristics from the ion source through the SSR1 cryomodule.
  Demonstration of MEBT chopper operations at a level required for Booster injection
  Demonstration of the operation of the HWR cryomodule, with beam, in close proximity to the MEBT beam absorber
  Demonstration of stable beam acceleration in the SSR1 cryomodule, under the full control of prototype RF control systems, including resonance control within the cavities
Collaborators
ANL: HWR
LBNL:LEBT, RFQ
SNS: LEBT
BARC: MEBT, RF
IUAC: SSR1
40 m, ~25 MeV
30 keV
RFQ
MEBT
HWR
SSR1
HEBT
LEBT
2.1 MeV
10 MeV
25 MeV
2017
Now
2015
2019
2018

## Slide 12: PIP2IT: Phases and Deliverables
PIP2IT will address the address/measure the following:
Phase 2 (post-CD-3, off project?): retirement of risks associated with CW operations, in particular as related to utilization of the PIP-II linac for a second generation Mu2e experiment. The primary risks to be retired during this period may include:
  Full demonstration of the ability of the MEBT chopper to provide customized beam patterns at the bunch-by-bunch level
  Demonstration of the MEBT beam absorber at power levels up to 20 kW
  Demonstration of stable beam acceleration through the HWR and SSR1 cryomodules, with a beam current of up to 2 mA and at 100% duty factor
  Measurement of beam extinction provided by the MEBT chopper system, with a goal of 1E-9.
Collaborators
ANL: HWR
LBNL:LEBT, RFQ
SNS: LEBT
BARC: MEBT, RF
IUAC: SSR1
40 m, ~25 MeV
30 keV
RFQ
MEBT
HWR
SSR1
HEBT
LEBT
2.1 MeV
10 MeV
25 MeV
2017
Now
2015
2019
2018

## Slide 13: RFQ Status
RFQ Installation is complete.
RFQ successfully conditioned with 120kW input power initially at 5% duty cycle,
  Taking into account measured Q0 and beta, estimate vane potential at 66kV (10% above specified).
95 kW in CW operation
  Equivalent to 62 kV vane potential (60 kV required)
RFQ in Enclosure

## Slide 14: Beam from RFQ
We received permission to run the beam through RFQ on March 23, and saw an accelerated beam within an hour
RFQ exit
Current transformer
First doublet (BARC)
Faraday Cup
Second doublet (BARC)
Time of Flight BPM
98% ± 3% transmission efficiency
1 - 10 mA pulsed beam
Energy
  2.11 MeV ± 0.5%

## Slide 15: PIP2IT: MEBT
The MEBT primary technical deliverables:
  Beam Chopping
    Forms the bunch structure required Booster injection
    Testing Prototype kickers in FY17
    Testing Prototype absorber in FY17
  Vacuum Management
    absorber upstream of SRF Cryomodule

## Slide 16: SRF
PIP-II includes
  5 different SRF cavity types and cryomodules
    Half Wave Resonator: installed
    2 Single Spoke Resonators
    2 elliptical cavities
  3 different frequencies (162.5 MHz, 325 MHz, 650 MHz)
R&D program:
  test one complete cryomodule of each frequency to full power
    HWR & SSR1 @ PIP-II Injector Test with beam
    HB650 in a test stand with RF power
  test LB650 dressed cavities with RF power
  test bare SSR2 cavities in vertical test stand
  Resonance control of cavities in pulsed mode operation
    Combination of High Qext, pulsed operation
    Passive means: Mechanical design
    Developing a peizo-based feed forward and feedback system
  Application of High Q0 R&D to PIP-II 650 MHz cavities

## Slide 17: Rings: Booster
Booster: 50% pulse intensity, 33% pulse frequency
  Doubling of proton flux
  New injection region:
    Radiation Deposition in Absorber
    Magnets and Power supplies
  20 Hz vs 15 Hz:
    Resonant magnet system: build a complete girder
    Controls and timing : 15 Hz is the standard clock

## Slide 18: Rings: Recycler / Main Injector
RF systems
    Recycler: New Cavities
      increase in duty factor -> better cooling
      increase in repetition rate -> increased voltage
    Main Injector: New Power Amplifiers
      enough voltage but higher power needed
      two solutions
        Higher power tube
        Two tubes of existing design on cavity
Beam Dynamics and Control
  Recycler: understanding of instabilities
  Main Injector: gt jump for stability through transition
    8 triplets to generate ± 1 unit in 0.5 msec
    test prototype magnet and power supply

## Slide 19: PIP-II Priorities
Goal: Complete the R&D Program in advance of CD3
R&D Goals
  PIP-II Injector Test
    Chopper validation
    HWR and SSR1 Operation with beam
  SRF/IIFC
    SSR1 CM (6 US + 2 India)
    HB650 CM (3 US + 3 India)
    LB650 + SSR2 Cavities from India (2 + 2)
    RF systems (8 US + 16 India)
  Rings
    20 Hz: magnet tested, understand control system impact
    Booster Injection: design and prototype magnet
    RR/Main Injector RF: PA tested, prototype RR cavity, prototype gt magnet
CD Goals
  CD-1 FY17
  CD-2/CD3a FY18
  CD3 Late FY19/Early FY20

## Slide 20: Activities Priorities: Funding Constraints
FY16-FY18 (PIP2IT)
  Beam to end of MEBT and Chopper Test
    MEBT to HWR beam line vacuum transition
  HWR CM Cold with RF Power
  SSR1 CM Cold with RF Power
FY16-FY18 (IIFC)
  US HB650 Dressed Cavities to be tested in STC (4)
    Bare cavities from PAVAC (1)
  DAE HB650 Dressed Cavity (4)
    Commission HTS-2 at RRCAT
  LB650 Dressed Cavity to be tested (2)
  SSR2 Cavity Vertical Tested (2)
  RF Power System delivered and integrated (325 and 650)
FY16-FY18 (Rings)
    20 Hz
    Booster Injection
    RR/Main Injector RF
FY16-FY18 (CD)
  CD-1 FY17: CDR, Analysis of Alternatives, RLS, …..
  CD-2/3a FY18: Environmental Assessment, EVMS, RLS, BoE, TDR,KPP,….
R&D Program completion: early FY20
  PIP2IT program
  HB650 pCM
  Rings
slowed down due to FY16/17 funding constraints
Outside FY16-18 window

## Slide 21: The R&D program will:
At the end of the PIP2IT R&D program:
  have demonstrated understanding of beam dynamics, beam stability, and beam parameters
  have demonstrated beam chopper, absorber, and bunch by bunch selection for pulsed operation
  have determined conditions for operation of SRF cavities with a high power MEBT absorber
  have measured and demonstrated resonance control techniques for pulsed SRF cavities
  validated the critical technologies of the PIP-II Linac front end
At the end of the SRF R&D program:
  have built and tested complete cryomodules at 3 different frequencies
    a good understanding of cost and schedule for construction of the remaining 20+ cryomodules
  have demonstrated the technical capabilities of the collaboration partners
At the end of the R&D program:
  PIP-II will have mitigated technical, cost, and schedule risks
  be prepared to start construction

## Slide 22: Backups

## Slide 23: Primary Risks and Required R&D
PXIE should mitigate most risks related to the frontend
  HWR and SSR1 prototype cryomodules are in fabrication
Design and testing of SC cryomodules is time consuming process
  5 new types of SC cavities: vigorous design work for SSR2, LB650 and HB650 has to be initiated
  Microphonics and LFD detuning suppression
Major challenge for SC linac - reliable operation in pulsed regime
  Task force was organized and is working on this problem
Longitudinal emittance growth at transition crossing in Booster can increase beam loss at slip stacking. It can limit the beam intensity and, consequently, the beam power
  Detailed simulations of transition crossing are carried out
Suppression of fast beam instabilities at slip stacking can be challenging enterprise
  Better understanding of present problems is required
Notes: This looks the same as Valeri’s slide – good work!

## Slide 24: PIP-II Injector Test
Development and integrated systems testing of PIP-II Front End components
  Deliver 2 mA average current with 80% bunch-by-bunch chopping of beam delivered from the RFQ
  Demonstrate efficient acceleration with minimal emittance dilution through at least 15 MeV
All components are being designed and fabricated to PIP-II specifications
  reutilize during the PIP-II construction to the extent possible.
RFQ
MEBT
HWR
SSR1
HEBT
LEBT
Notes: The 80% bunch-by-bunch chopping is unrelated to the neutrino mission – Valeri says 50% in his talk. So be prepared when someone asks why you say 80 and Valeri says 50.
The bullets in the smaller font seem to be orphans. This looks like the scope so why not label it as such.

## Slide 25: Beam Characterization
Energy Measurement:
  Time of Flight BPM
  2.11 MeV ± 0.5%
Preliminary : working to
understand calibrations
understand optics
understand uncertainties
Energy Measurement:
  Phase difference between 2 BPMs
  vary buncher cavity phase and compare to simulations
  90° is nominal vaue

## Slide 26: MEBT stages
MEBT is being installed in 3 main stages, different in the number of focusing elements
  Full-length MEBT is expected to be installed in 2017
MEBT-1
MEBT-2
MEBT-3
1175 mm

## Slide 27: Booster: Injection
new injection point at Long 11, 3 or 4 bump
radiation deposition in area
  an H0/H- absorber
  investigating new gradient magnet design to allow for larger absorber
design complete ?

## Slide 28: Booster: 20 Hz
Booster is a resonant synchrotron at 15 Hz
  Changes to resonant system to get to 20 Hz
    have tested a single magnet successfully at 20 Hz
    Plan to build and test a complete Booster girder
      2 gradient magnets, choke, cap bank, & power supply
    complete by fall 2017
Controls and timing system built around 15 Hz as fundamental frequency
  understand what needs to be upgraded/modified
    Time Line Generator
    TCLK system
    DAQ front ends
    data collection and sampling

## Slide 29: Recycler Ring
With 20 Hz operation and 60 GeV option for LBNF
  need a new 53 MHz RF cavity
    60 GeV option: increase in duty factor -> better cooling
    20 Hz operation: larger separation for slip stacking -> higher peak voltage
  Develop and build a prototype cavity by fall 2018
Beam dynamics and loss control

## Slide 30: Main Injector
Two areas of R&D:
  RF Power:
    have enough voltage but PA does not have enough power for 7.5e13 ppp
    With existing cavity, two possible solutions
      use two power tubes (cavity has requisite ports) of current type
      use a single higher power tube
      With the spare cavity, investigate operation in test stand of both solutions
      ready for testing by the end of 2016
  Transition crossing: need a gt jump for loss control
    8 quad triplets to generate ±1 unit in 0.5 msec at transition
    build and test a prototype magnet and power supply by fall 2017
Notes: Note: Valeri did not identify gammat jump in his talk (but I requested that he add it)