## Slide 1
Victor Kuchler
DOE Independent Project Review of PIP-II
15 November 2016
Environment, Safety and Health

## Slide 2: Speaker Background
Victor Kuchler
Engineer V
39 Years at Fermilab
Facilities Management and Conventional Design for both Fermilab and International Projects
Primary Responsibility for the PIP II Project to oversee the NEPA Compliance Process

## Slide 3: Outline
This talk will address Item 5 of the Review Charge, Environment, Safety and Health
PIP II NEPA Compliance Process
  Overview and Current Status
  Schedule
  Additional Wetland Considerations
  Conclusions
PIP II Injector Test at Cryomodule Test Facility (CMTF)
  Scope
  ES&H Requirements
  Conclusions

## Slide 4: Project Site Overview

## Slide 5: PIP II NEPA Compliance Process
PIP II NEPA Overview and Current Status
  PIP II Mission Need Statement - Approved, September 2015
  Fermilab Environmental Review Form (ERF) - Completed, February 2016
  Continue site specific design to minimize Environmental Impact and Required Wetland Mitigation - On-going
  New Wetland Delineation Report - Completed, July 2016
  Develop Environmental Evaluation Notification Form (EENF) - Draft EENF Completed, October 2016
  Submit EENF to DOE Fermilab Site Office - Pending available funding for Environmental Assessment
  Complete Environmental Assessment (EA)
  Complete Wetland Mitigation
  Develop Application for Permit from the US Corps of Engineers
  Receive “Finding of No significant Impact” (FONSI)

## Slide 6: PIP II NEPA Compliance Process
PIP II NEPA Schedule

## Slide 7: PIP II NEPA Compliance Process
PIP II NEPA Additional Wetland Considerations
  Fermilab is currently pursuing a request to the US Corps of Engineers (COE)
  A number of areas on the Fermilab site are isolated wetlands and do not flow into waters of the state
  All of the wetlands affected by the PIP II Construction fall into this category
  Fermilab will request a determination from the US COE that these wetlands are “Non-Jurisdictional”
    This would simplify the NEPA Compliance Process significantly
    Wetland mitigation would not be required
    A US COE Permit may not be required
  Determination Request Process
    Fermilab will develop a Report describing the reasons for the Determination Request - In-Progress, completion expected November 2016
    Submit request documentation to DOE Fermilab Site Office - Est. November 2016
    DOE FSO to submit request documentation to US COE - Est. December 2016
    US COE evaluation and determination - Est. December 2017

## Slide 8: PIP II NEPA Compliance Process
PIP II NEPA Conclusions
  All aspect of the NEPA Compliance process that can be completed, have been completed at this point
  FY 17 Budget constraints will delay efforts to initiate the development of the Environmental Assessment
  When sufficient funding has been identified to proceed with the Environmental Assessment the EENF will be submitted to the DOE Fermilab Site Office

## Slide 9: PIP-II Injector Test at the Cryomodule Test Facility
Scope:
  A CW H- source delivering 5mA at 30 keV : Installed
  A CW RFQ operating at 162.5 MHz, delivering 5 mA at 2.1 MeV : Installed
  2 SRF Cryomodules capable of accelerating 2 mA at 25 MeV : FY 2018
  Beam Dump for 2 mA at full beam energy : FY 2019
  Utilities and Shielding : As required as configuration changes
FY 2017
FY 2018
FY 2019
CW H- Source
CW RFQ
MEBT
HWR
SSR1
Beam Dump
P Derwent

## Slide 10: PIP-II Injector Test at the Cryomodule Test Facility
ES&H Requirements
  Test accelerator is contained inside a single room enclosure with no extractable beamlines, There is a single entrance labyrinth (north end), with an emergency exit labyrinth (south end) for Life Safety reasons.
  We requested an exemption from DOE Order 420.2c, Accelerator Safety Order for this facility and it was granted.
P Derwent

## Slide 11: PIP-II Injector Test at the Cryomodule Test Facility
ES&H Requirements Cont.
  Enclosure and operation is covered under Title 10, Code of Federal Regulations, Part 835.
  We will treat the enclosure and internal accelerator as a radiation generating device following Fermilab Radiation Control Manual requirements.
    including radiation safety interlocks (Oct 2016)
  We will continue to review and approve accelerator operations through the laboratory Operational Readiness Clearance (ORC) process.
    Chief Accelerator Officer Signs off on the ORC
  Have prepared a Safety Analysis Document for 2.1 MeV operation (PIP-II DocDb #40)
    updates are in progress to address radiation assessment and safety interlocks
  John Anderson (ESH&Q) is the assigned Senior Radiation Safety Officer
P Derwent

## Slide 12: PIP II Injector Test at the Cyromodule Test Facility
Conclusions
  The ES&H Requirements for the PIP II Injector test are identified and well understood and will continue to be implemented as the installation of equipment continues over the next three years
  A review and approval process is established and will be followed as the Injector becomes fully assembled and operational
  The Senior Radiation Safety Officer, John Anderson, will oversee and approve the progress of the full PIP II Injector test installation
  Documentation for the PIP II Injector test will continue to be updated as installation continues