## Slide 1
Steve Holmes
DOE Independent Project Review of PIP-II
15 November 2016
PIP-II Perspective on IIFC

## Slide 2: What are we trying to achieve?
“Total Project Collaboration”
R&D Phase
  Develop capabilities, infrastructure, and working relationships at Fermilab and DAE labs, and allied vendors, that will support construction of the PIP-II linac
  Develop capabilities and infrastructure in DAE labs and allied vendors that will support successful construction of high intensity proton accelerators in India
PIP-II Construction Phase
  Construct and commission PIP-II with a significant India/DAE in-kind contribution, and significant engagement of DAE staff
  India/DAE contribution supports a very significant reduction in the cost to DOE of the PIP-II Project
  In-kind contribution requires a successful R&D phase
Many challenges
  Success requires consistent attention and guidance from management
    But not micromanagement
  Constructive interaction at the technical level is essential in making this work

## Slide 3: Outline
Organization
Mapping IIFC onto PIP-II
Challenges
Moving Forward

## Slide 4: IIFC Organization
Scope and deliverables schedule for R&D phase are governed by the Joint R&D document
  Signed by S. Basu and J. Siegrist
High level management via two Principal Coordinators, supported by two Technical Coordinators
  TC weekly teleconference
Technical integration of work via Fermilab SPMs and Indian SPCs
  SPM/SPC weekly teleconferences
Semi-annual meetings initiated
  January/July 2016 (both at BARC)

## Slide 5: SPC/SPM Assignments
Current SPM/SPC assignments
Generally all are engineers or scientists
Within Fermilab SPMs are typically level 3 managers within PIP-II Project

## Slide 6: Mapping IIFC onto PIP-II/Strategy
Mapping based on consideration of:
  DAE technology interests
  PIP-II risk mitigation strategies
R&D phase scope of work reflects vision of construction phase deliverables
  Development and testing of prototypes
  Development of infrastructure
DAE interests
  Primary interest is acquiring capabilities, intellectual and physical, to construct high power proton accelerators domestically
  Result: DAE is engaged in all critical systems
PIP-II interests/risk mitigation
  All DOE projects are required to mitigate risks: technical and cost
  Primary mechanisms for technically demanding components:
    Multiple suppliers
    Project host lab serves as “general contractor”

## Slide 7: Mapping IIFC onto PIP-II
The DAE laboratories are completely integrated into nearly all aspects of the PIP-II superconducting linac
Areas of collaborative development include:
  Superconducting radio frequency accelerating modules
  Radio frequency power sources
  Radio frequency controls
  Super- and normal-conducting magnets
  Cryogenic Plant
  Beam diagnostics
  Controls
IIFC

## Slide 8: Mapping IIFC onto PIP-II/Major IIFC Deliverables
  * Subject to adjustment and formalization between DAE and DOE
System/Component | R&D Deliverable | Construction Deliverable*
SSR1 | 2 dressed cavities | NA
SSR2 | 2 dressed cavities | 50% dressed cavities
LB650 | 2 dressed cavities | 50% dressed cavities
HB650 | 4 dressed cavities | 50% dressed cavities
SC solenoids | 4 magnets (SSR2) | All SC solenoids
Warm magnets | All PIP2IT/MEBT magnets 2 focusing magnets (650) | All warm magnets (650)
RF Power Sources/325 | 9 sources (SSR1) | All rf sources
RF Power Sources/650 | 7 sources (HB650) | All rf sources
LLRF/RFPI | 4 systems (SSR1,2xHTS-2, CMTF) | 50% of required boards
HTS-2 | 2 test stands (FNAL & RRCAT) | 
LHe Cryoplant |  | 1900 W (@2K) Plant (2)

## Slide 9: Integrated Systems Tests/SSR1 (w/beam)
SSR1 cryomodule under development by IIFC
  Install in PIP2IT immediately downstream of HWR cryomodule
  Plan: 6 U.S. cavities + 2 (successfully tested) Indian cavities
  RF sources from India (8 x 325 MHz, 7 kW)
  Goal: Late 2018

## Slide 10: Integrated Systems Tests/HB650 (w/ RF)
HB650 MHz Prototype Cryomodule
  3 U.S. + 3 Indian cavities (RRCAT)
  Test at full RF power (CMTS)
    RF sources from RRCAT (650 MHz, 40 kW)
    LLRF and RF Protection (BARC w/Fermilab)
  Goal: Early 2020

## Slide 11: Challenges
PIP-II, as far as I am aware, is the first attempt by DOE to construct a domestic accelerator incorporating international in-kind contributions
  Creates a set of generic challenges in how to organize and manage
  India creates a number of specific challenges…
Conducting a collaboration between institutions separated by 11 time zones and 8000 miles
  Communications
  Visits
  Equipment exchange
Export regulations
  India is classified as a “sensitive country” with BARC subject to special scrutiny
Differences in engineering and management cultures also need to be recognized
  Many discussions on what “design” means
  Control of documentation
  (Fermilab processes codified in Fermilab Engineering Manual)

## Slide 12: Moving Forward
Most important: Establish and maintain confidence among the partners
  In process…
Several things have been particularly successful (my opinion)
  FRS/TRS
    Establish the basic requirements, including interfaces to other systems
    Generally involve significant discussion and iteration
    Signed off by both Fermilab and DAE lab
  Guest engineers/scientists
    Our goal for these visits is to provide an experience that is both professionally and personally fulfilling
    7 engineers/scientists at Fermilab for 2-year residencies
      Augmented by a set of shorter term (1-6 months) visitors
    Provide direct support to efforts at Fermilab
    Provide interface to home laboratories
    Upon return will be in unique position to facilitate interactions between Fermilab and DAE labs as well as carrying home knowledge & experience
  Weekly teleconferences
    SPM/SPC
    TC/TC
  These elements form a strong basis for moving forward

## Slide 13: Moving Forward
Areas requiring management attention:
  Management of shared engineering documentation
  Horizontal Test Stand
    Preparing for identical test stands at Fermilab and RRCAT
  Cryoplant
    Very long lead item
  Export licensing
    Involves multiple agency interactions: Dept of Commerce, DOE
  Intellectual Property
    Especially third-party
  DAE Chairman’s Report (March 2017)
    Review of R&D progress;
    Will supports transition to constructing phase
  Prioritization in face of resource limitations
  SPC/SPM interactions
    This is the foundation of everything we do together

## Slide 14: Summary
IIFC has been going for seven years
Interactions have picked up considerably over the last two years, and deliverables are starting to arrive at Fermilab
  In most cases these meet requirements
The approach to requirements and specifications has been formalized
  Jointly developed and jointly approved
Communications have improved over the last two years, both at the SPM/SPC and higher levels
DAE staff at Fermilab for extended visits have had significant positive impact
Challenges remain, but both sides are committed to making this work

## Slide 15: Backups