## Slide 1: System testing and exploitation
Karol Hennessy
ProtoDUNE-SP DAQ Review
3-4 Nov. 2016

## Slide 2: Introduction
Primary goals
  Follow the APA timeline and have DAQ infrastructure in place to qualify front-end
  Reception tests of components both DAQ and Front-end
  Development of DAQ infrastructure, HW, SW, FW in parallel
  Preparation for data taking/Commissioning
Outline
  Test centres
  Timelines
  Testing infrastructure, people
  Exploitation – calibration, run modes
  Risk mitigation

## Slide 3: Charge items
Are DAQ system risks captured and is there a plan for managing and mitigating these risks?
Does the design lead to a reasonable production schedule, including QA, installation and commissioning? Does the DAQ schedule allow sufficient time for testing of other components?
Are operation conditions listed, understood and comprehensive? Are interfaces to calibration systems and plans well understood? Are proposed triggering schemes sufficiently well understood? Has appropriate consideration been made for collection of both zero suppressed and non-zero suppressed data?
Are the DAQ system analyses sufficiently comprehensive for safe handling, installation and operation at the CERN Neutrino Platform? Is the installation plan sufficiently well developed?
Have applicable lessons-learned from previous LArTPC devices been documented and implemented into the QA plan? Are the DAQ quality control test plans and inspection regimes sufficiently comprehensive to assure efficient commissioning and adequate operational performance of the NP04 experiment?

## Slide 4: Interfaces
Interfaces for the individual components have been mentioned in the previous talks.
Here we also focus on the extra dimension of time – that the components arrive so as not to delay overall progress
  This is typically outlined on some unreadable Gantt chart (which I strive to avoid here).
  The testing must serve both the DAQ testing and a system must be in place to check out the FE electronics.

## Slide 5: Testing and Planning

## Slide 7: Testing sites and focus
Four testing sites
  UK
    Simple “emulated front-end” slice setup
    RCE and SSPs to BoardReaders
  US
    Focuses on testing of dataflow through artDAQ and performance improvements thereof
    Testing WIB-RCE interaction
  PNNL + NIKHEF
    FELIX testing – BoardReader on host PC
    WIB-FELIX
  CERN
    Run Control, data challenges, injection tests…
    Full integration and reception testing
    Eventually everything migrates to CERN

## Slide 8: From now to Jan

## Slide 9: UK testing
Use 35t setup as a starting point
  Gain experience necessary to deploy a working ProtoDUNE DAQ
  RCE and SSP setup and 10 G networking infrastructure
  Validate readout software and firmware
  So far tested
    1 COB in data emulator mode sending data to BoardReader PC
    1 SSP in external triggered mode to BoardReader PC
    Data written to disk
To do
  Update above to ProtoDUNE components/firmware/software
  Test first timing prototypes (one end-node, then many)
    Configuration interface and BoardReader
    Test both RCE and SSP
  Test new RCE components and FW
  Test monitoring
  Add WIB emulator to slice, test interaction with RCE, and read-out

## Slide 10: US Testing
35t migration
  Like UK, using what works and migrating from there
  artDAQ software focussed developments
Current testing – based on artDAQ-demo
  Unit testing of individual computing components
    BoardReaders -> EventBuilders -> storage
  Finding hardware throughput limits before testing software
  Then adding artDAQ software and benchmarking
  10 G networking
  CERN CentOS7
Ongoing:
  Test enhancements to artDAQ
  The FNAL testing site will remain in operation after CERN migration as a means of cross-checking on-site problems
  Also acts as a development area prior to deployment
    Many artDAQ developers situated in Fermilab
  Test WIB-RCE interaction (data protocol, timing, sync, new RCE components/FW, burn-in, etc).
  Run control developments
  Online Monitoring

## Slide 11: PNNL+NIKHEF Testing
FELIX testing
  New firmware releases
    Simpler GBT mode
  Loopback testing
    In principle, FELIX is data agnostic – only throughput matters
  Developing artDAQ BoardReader for FELIX
Todo (Nov)
  WIB testing
  Investigating compression schemes (both CPU and FPGA)
  Investigating BoardReader implementation on FELIX host PC
    Can interfere with DMA throughput
  High rate testing (200 Hz)

## Slide 12: From Jan to 1st APA

## Slide 13: CERN Testing
Some common ground between all other sites as CERN will be the final destination
  Gain experience in hardware setup early
  Components will migrate to CERN
Reception testing
  Has anything broken in transit?
  Common suite of tests between host and CERN
  Integration into CERN infrastructure
Robustness testing
  “Burn-in” tests – running for extended periods without error
  Full system tests – running the system in “shift mode”, as if it were the real thing

## Slide 14: From Jan to 1st APA
Integration
  Basic online computing infrastructure (more later)
  Initial assembly of components in racks
  Power and networking and other cabling to computing
  Clone test stand software setup from UK-test or FNAL-test
  Initial tests initialization FEMB-WIB-RCE from artDAQ
  Setup of some SSPs at CERN
Extensive testing of above
Sync tests (pulse FEs) appear in data at same time
Initial Run Control with artDAQ (JCOP to follow)

## Slide 15: 1st APA arrival
At this point need to partition DAQ into two slices – Reception testing and DAQ development
  Reception testing
    used to test the APA, FE electronics and all new DAQ equipment arriving at CERN
    Step-by-step commissioning of APA test area DAQ
    Requires a DAQ we can hand over to operators (basic config, run control, read-out)
    35t software will be used where ProtoDUNE is not ready

## Slide 16: From 1st APA to 3rd APA

## Slide 17: From 1st APA to 3rd APA
  DAQ development
    As equipment is qualified, it can be added to the second partition
    Develop new RC, HW and DQ monitoring
    Mock data challenge from DAQ to storage
    Test new firmware revisions
    Add beam counter and BPM hardware, commission trigger

## Slide 18: From 3-6 APAs – full system

## Slide 19: From 3-6 APAs – full system
Reception testing in full swing
  Full set of COBs, aTCA, RTMs arrive at CERN
  Full set of SSPs arrive at CERN
  Full set of WIBs, flanges, FEMBs for APA#n arrive at CERN
  Full set of computers arrive at CERN
  Step-by-step commissioning as new APAs installed DAQ
Development slice
  Final timing system arrives at CERN
  EVB Software developments
  Monitoring
    Dataflow, HW, Data Quality
  Run Control with artDAQ and JCOP - basic functionality
  Configuration Control with JCOP - test functionality

## Slide 20: 2018 – commissioning

## Slide 21: Commissioning
Integrate all hardware into the system
The first reception test slice will essentially disappear at point
And the second development slice will become the primary system
  But partitioning still available for parallel testing/developments
Testing will focus on integrating beam instrumentation, tests with cosmics and robustness of the system
  Move to a system that can be operated by shifters and not just experts
  Since BI and CRT we have special “nearline” data taking modes for these interfaces, that have to be merged with “standard” DAQ data, we have to test/commission this early in conjunction with other groups

## Slide 22: Testing Plan Summary
UK
US
PNNL/
NIKHEF
CERN
CERN
Integration
Stable
Partition
Dev
Partition
Dev
Integration
Multiple
Partitioning
APA Testing
Commissioning

## Slide 23: Some test detail

## Slide 24: APA response calibration
Detector response will have to be done in conjunction with other groups (CE, PDS)
  We expect (also listed in other groups QA/QC plans):
    TPC noise characterisation
    APA Wire testing/Cable-Channel Mapping
    SSP threshold scans – for signal optimisation
    TPC drift time calibration – may take 5ms of drift time, but prefer more post-trigger info than pre-trigger.
    HV scans
    etc.
From the DAQ perspective we need to provide the data taking mechanisms for these calibrations
  Necessary data taking paths and bandwidth
  Special Board Reader configurations
    If data format differs to standard
  Special monitoring for calibrations
    Data vs. expectation comparisons
    Signal finding routines, pattern checking, etc.

## Slide 25: Sync tests – timing system
First simplest slice = 1 FEMB > 1 WIB > 1 RCE > 1 BR > 1 EB > analysis/monitoring FEMBs have pulse injection, so we can fake signals and check that they arrive at the RCEs, and hence in the data as we expect
Repeat with 2 of everything except EB. Synchronised pulse injection on both FEs.
Repeat (1) with PDS and LED pulser
Repeat (2) with combined TPC and PDS readout.
Automate
Repeat with trigger inputs during Beam Inst. commissioning (1-4 allow us to set “detector timing”, but does not mean we are in phase with the beam).

## Slide 26: Data Challenge
Can “generate” data in multiple ways:
  In-FPGA data generators
  Low signal thresholds to match cosmic rate (i.e., boost noise hits count)
  Cosmics
Test the elements piecemeal:
  Data consumption by Board Readers – monitor buffers, backpressure
  Repeat adding successive layers: Event Builders, Aggregators, Storage, EOS.
  Further challenges can include prompt processing in coordination with offline computing group
First challenge = 1 APA
Last challenge = 6 APAs, Beam Inst., Cosmic Tagger
Commissioning = real data becomes the challenge

## Slide 27: Testing and data taking infrastructure
Material tracking database and web front-end
Logbook – many options
Documentation site – twiki or similar
  Probably want a strict structure/manager for these as it quickly gets out of control and impossible to find anything
Databases
  Run database
  Configuration database
User accounts – probably make all these CERN SSO facilities
Needs to be accessible outside CERN
In general, leverage CERN solutions where possible

## Slide 28: System Exploitation

## Slide 29: Calibration modes (without beam)
Qualify detector as much with cosmics as far in advance of data taking with beam as possible
  As this will be the dominant source of particles, detector occupancy should be close to beam conditions
  Use a fake spill trigger
  High rate testing (how far can we push the system)
  Useful test of all monitoring
  Complete system noise can be qualified early
Cosmic mode – full data taking
Photon Detector mode
TPC triggerless modes
Beam Instrumentation and Cosmic Tagger

## Slide 30: Run Modes – with beam
Most of the time we will have standard physics running
Special calibration runs for:
  Photon Detector
    Allow taking data with just Photon Detector
    Full waveform data essential for calibration
  Inter-spill cosmic data
    Background count
  Beam Trigger
    Threshold scans with different beam modes

## Slide 31: Risks
Monitoring
  Need more people actively working on this on all aspects (HW, DQ, dataflow)
  Have basic 35t monitoring software as backup
New critical components
  E.g. WIB
  Anything late or having serious design flaws can cause serious knock-on effects
  Will have WIB-emulator
Channel mapping
  Mistakes lead to incomprehensible data, very difficult to fix on the spot
  Labelling, database tracking, verification of channel mapping with pulse injection

## Slide 32: Risks
Delays to EHN1
  Have other areas at CERN (ready) which can be used for DAQ installation and testing.
  However, “cold box” is destined for EHN1, therefore overall test schedule of Cold Electronics could fall behind
  Can seriously affect schedule
High noise affecting compression
  Reduce inter-spill data taking to compensate
  Reduce drift margin (currently taking 2x drift time)
  Try different compression algorithms
Backpressure
  Reset buffers by end of spill cycle – always in same state at start of spill
  Detailed monitoring of buffers
  Software trigger throttle

## Slide 33: 35t lessons learned
We have several documents on lessons learned from the 35t
  Principle problem was that of system noise
    A taskforce is in place to ensure ProtoDUNE cryostat is sufficiently isolated from external noise sources. Care has been taken to plan exactly what components are on detector power and what is on building power
    From the DAQ – optical will be used whenever connecting to the detector
  Need sufficient number of people “on the ground” to ensure deadlines are met
    (Signed and agreed) list of people to be at CERN in the crucial 2017 commissioning year – number expected to grow as funding requests get approved, and new groups join
    Need to also minimise people turnover and ensure knowledge transfer for those being replaced

## Slide 34: 35t lessons learned
Data taking stability
  Problems with backpressure
    Plan to monitor backpressure in detail and have throttle mechanisms (in SW) to reduce trigger rate if necessary
  Software instabilities
    Need to have well-tested stable releases of SW. Separation of testing and stable paths
Monitoring
  Lack of online displays, event monitors
    Need extensive online monitoring for problem tracing and resolution
    Need automated alerts

## Slide 35: Conclusion – charge items revisited
  We are aware of the big risk items. Most have fallback strategies, others need manpower
  Outlined the plan for component testing and the infrastructure necessary for QA
  Detailed what needs to come online and when for progressive stages of commissioning and installation
  Detailed the run modes, calibration modes, special data runs and lead times
  Have a lot of re-usable monitoring from 35t and other LAr experiments, but monitoring is an understaffed area
  Need to attract new groups and encourage physics groups to participate further
  Have a detailed catalogue of lessons learned from the 35t prototype – most of which involve noise isolation, and meeting deadlines

## Slide 36: Supporting Documentation
35t lessons learned
  http://docs.dunescience.org:8080/cgi-bin/ShowDocument?docid=1315
Risk register
  https://docs.google.com/document/d/1-sa5M29dshODIRxJVc7A5Zde4Pv_u9h8JeV3t2mNLvY/edit?usp=sharing
Detailed Testing plan
  https://docs.google.com/spreadsheets/d/10qfOsnc2UKal0J8Bkml8FM-dLaWvlgMO5IDiAU41JA8/edit?usp=sharing

## Slide 37: Backup