## Slide 1: FPC Issues
Premo
LCLS-II 1.3 GHz Cryomodule Production Readiness Review (JLAB)
9-11 January, 2017

## Slide 2: FPC Issues, Oxidation on recent shipments
CPI Couplers, 5 returned
Cause: Cleaning with 30 % water Isopropyl alcohol
RITH Couplers, 2 returned
Cause: Unknown

## Slide 3: Storage of FPC components until ready for use
Store ready for use after incoming QC
Warm end and cold ends will be stored separately
  Cold ends to be stored under vacuum, inside MP9 clean room
  Warm ends stored in cabinet under nitrogen purge, to prevent oxidation
  Hardware to be stored in kits
Storage problems due to mismatch of FPC delivery and installation at partner labs:
  All couplers are scheduled to be delivered by March-April 2017
  Cryomodule production is not expected to be complete until May 2018
  Parts in circulation concept requires quick return of shipping cases and cold end stands, and couplers will have to be stored

## Slide 4: FPC Storage, cold ends
Based on latest delivery and production schedules:
Estimated up to 100 cold ends will be in storage in MP9 clean room
  Duration in storage could be as long as 1 year
  Cold ends should be stored under vacuum
  Vacuum storage manifolds (Qty 10, storage of 80 couplers) are being procured for storage inside the clean room
  At the end of coupler production, some coupler cold ends could be stored as shipped on the stands

## Slide 5: FPC Storage, warm ends
Based on latest delivery and production schedules:
Estimated up to 120 coupler warm ends will be in storage
  Duration in storage could be as long as 1 year
  Warm ends should be stored under nitrogen purge desiccator to prevent oxidation
  There is one available cabinet in MP9, this cabinet can hold up to 32 warm ends
  In order to provide adequate storage, 4 cabinets will be required to store 120 warm ends
  3 additional cabinets are ordered delivered in January
Cabinet in MP9

## Slide 6: FPC Delivery
  Current delivery rate is about 8 couplers/Lab/week
  All couplers were scheduled to be delivered by March-April 2017
    Due to PIC and quality issues original delivery schedule has slipped about 2 months
    Estimate of completion May –June 2017
    There is no current official schedule of deliveries from the vendors to reflect these changes
  Coupler deliveries will not impact CM production schedule
    We have plenty of couplers

## Slide 7: FPC Issues
  Quality Issues
    Initial shipments: problems with cleanliness, dirty bellows restraint
      Vendor has solved most of these issues, not a problem now
    Plating oxidation issues on CF100 area, CPI and RITH, 7 couplers
      CPI solved problem, RITH investigating cause
    Leak through RAV valve on wave guide stands, (2) couplers, CPI
      Couplers arrived not under vacuum
      Valve red tagged, vendor notified
  PIC and storage issues
    Lack of sufficient # of PICs delayed production
      Additional PICs procured and delays due to PICs eliminated for now
      Lack of storage delayed PIC returns and therefore production
        Storage capacity increased at FNAL, solution in place by end of January 2017