## pCM String Assembly
LCLS II pCM Lessons Learned Log
2016-05-10
Rev. 0
ID | Date Entered | Work Center | Activity | Task | Category (Process, Procedure, Design, Tooling, Resources) | Affected Traveler | Affected Procedure | Effect | Cause | Mitigation or Recommendation
Ex. | 2016-05-10 | State which work center is responsible for the activity, e.g., Cavity Assembly | Identify the activity that was being performed, e.g., Cavity string assembly | Identify the specific task that was being performed, e.g., Attaching the FPC to cavity AES034 | Relate the issue to one of the categories | Identify the traveler that is associated with the task | Identify the procedure that is associated with the task | Describe the effect. An effect is something that is produced by a cause, e.g. The vacuum joint between the FPC and cavity AES035 leaked | Describe the cause. A cause is a person or thing that acts, happens, or exists in such a way that some specific thing happens as a result; the producer of an effect, e.g. The FPC flange was not properly aligned with the flange on the cavity | What corrective action was taken to mitigate the cause or what is recommended to be done
pCM01 | 2016-05-12 | Multiple | Cavity string assembly | Torquing nuts on cavity string bellows flanges | Assembly procedure, joint design | L2PRO-CST-ASSY seq 0 |  | Three leaks occurred at flange joints on the cavity string | The cause appears to be that the torque required to seal these joints is higher than the torque called out in the JLab procedure. FNAL and DESY do not use torque wrenches, and it appears that their technicians may be torquing to higher values than was originally used at JLab. | Torque was increased on the leaking joints until they sealed. Two were torqued to 39.1 ft-lbs and one to 51 ft-lbs. All joints passed leak check after this. For the production, the best solution should be evaluated: in separate tests to failure, stripping of the nuts occured around 50 ft-lb and fracture of the stud occured around 60 ft-lb. Failures of the fasteners occured at lower torque in joints where the flanges went metal to metal. (We have seen variability in the depth of the seal groove on the bellow/spools.) Ari has also raised a concern about the possibility of gasket flaking under this compression load.
pCM02 | 2016-05-12 | Cavity assembly, engineering | String assembly | Attaching the FPC to cavity AES033 | Procedure&tooling | L2PRO-CST-ASSY seq 1 | In progress | Misaligned flanges prevented the gasket from being properly crushed, which resulted in the string not being able to pump down | A combination of design criteria, lack of awareness and tooling issues led to misalignment of the fpc flange and the NW40 flange on the cavity | Procedural changes were made after we became aware of this issue. We changed our alignment procedure and added a verification step to ensure proper alignment of the fpc flange to the nw40 flange. It is recommended that engineering look at the alignment tooling and see if the slop can be removed.
pCM03 | 2016-05-12 | Cavity assembly, engineering | String assembly | Attaching the FPC to cavity AES032 | Procedure&tooling | L2PRO-CST-ASSY seq 1 | In progress | Misaligned flanges prevented the gasket from being properly crushed, which resulted in the string not being able to pump down | A combination of design criteria, lack of awareness and tooling issues led to misalignment of the fpc flange and the NW40 flange on the cavity | Procedural changes were made after we became aware of this issue. We changed our alignment procedure and added a verification step to ensure proper alignment of the fpc flange to the nw40 flange. It is recommended that engineering look at the alignment tooling and see if the slop can be removed.
pCM04 | 2016-05-12 | Cavity assembly, engineering | String assembly | BPM Sub-assembly | Procedure&tooling | L2PRO-CST-ASSY-BPM | In progress |  |  | It is recommended that the lollipop tooling be assessed by engineering to see if we can accommodate a horizontal assembly on the rail
pCM05 | 2016-05-12 | Cavity assembly | String assembly | String pump-down | Tooling | L2PRO-CST-ASSY-LEAK | CP-STP-CAV-EVAC | Diminished ability to read the vacuum levels when pressure is close to atmosphere | Piranhi side of the full range guage on the pump cart needs cleaning and/or repair(pump cart does have a convectron control guage) | The new pump cart has a piezo guage which is more precise at the higher pressures. We will have an immediate understanding if there is a problem with the vacuum.
pCM06 | 2016-05-12 | Cavity assembly | String assembly | String leak check | Specification | L2PRO-CST-ASSY-LEAK | CP-C100-CAV-LKTS | String was okayed for removal from clean room with the cumulative leak rate higher than desired | The string drawing in use in the clean room had a specification of NDL at 2E-9 std cc/sec. The revised drawing shows NDL at 1E-10 std cc/sec. The verbal specification is NDL at 2E-10 std cc/sec | Suggest a standardized and clear leak rate specification for the project. This should be clearly indicated on drawings and in use by all parties involved in the project
pCM07 | 2016-05-12 | Cavity assembly, engineering | String assembly | Cavity Handling with the two-armedture on the back tech | Tooling | L2PRO-CST-ASSY | In progress | Unwanted dirt and metal particles in clean room | Aluminum clearance hole for threaded rod fasteners creates shavings when technician tightens and/or loosens the clamps | Use of shoulder bolt in lieu of threaded rod and possibly placing a sleeve in the clearance hole.
pCM08 | 2016-05-13 | Cavity assembly, engineering | String assembly | gate valve attachment during string assembly | Tooling | L2PRO-CST-ASSY | In progress | Limited freedom of movement of the gate valve while trying to align for installation during string assembly | The bonnet of the valve is larger than the body. The fixture does not allow for extra clearance for the bonnet. The height of the lollipop system limits the ability to drop the valve low enough. | Possible redesign of the bottom of the valve fixture. May be as simple as creating a cutout for the valve bonnet.
pCM09 | 2016-05-13 | Cavity assembly, engineering | String assembly | Torquing fasteners during string assembly | Procedure/Specification | L2PRO-CST-ASSY | In progress | Possible root cause of beam-line string leaks | Current torque specification of 23 ft/lbs may not be sufficient to have a 100 percent leak tight track record | Suggesting a possible increase to 35 ft/lbs or so for the M8 fasteners in the string.
pCM10 | 2016-05-13 | Cavity assembly | string partial rework | replacing/repairing leaking parts in strings | Procedure | L2PRO-CST-ASSY | In progress | Need path forward for possible string repair issues in the future | No current procedure for partial string disassembly and re-assembly. Right now we are only prepared to do a full string re-processing | Need to develop a procedure that will allow for partial dis-assembly of future strings in case of the need to replace or repair individual components in a string that has been built but will not pass the leak check specification.
pCM11 | 2016-05-13 | Chemistry Dept. | Warm FPC Cleaning | Remove the Cu oxide without getting the coupler wet. | Process |  | New procedure was developed | The top of the FPC coupler was severely oxidized from the bake box treatment. | The copper oxidizes from the heat of the bake box | The coupler was cleaned with a clean room wipe dipped in a Micro 90 solution. The top of the coupler was scrubbed until the oxide was gone. The Micro was removed with a Clean room wipe soake in water.
pCM12 | 2016-05-13 | Chemistry Dept. | Cavity HPR | Removing stains from beam tube seal sufaces. | Process |  | New procedure was developed to eliminate taking the cavity out of the clean room. | A stain develpoed on two different beam tubes. I'm not sure what caused it. | Cause unknown. | The flanges were polished with Scotchbrite in the Closed Chemistry Cabinet.
pCM13 | 2016-05-13 | Chemistry Dept. | Cavity HPR | Cavity HPR | Process |  | Cavity String HPR | Covers causing particles? | Does the cover and spring clamp cause more particles than just rolling the cavity through the clean room uncovered? | After HPR, remove cavity from cabinet and roll to drying area uncoverd.
pCM14 | 2016-05-13 | Chemistry Dept. | Cavity HPR | Hot HPR | Process |  | Cavity String HPR | NA | NA | Improvement idea undergoing testing
pCM15 | 2016-05-13 | Chemistry Dept. | Cavity Cleaning | Removing Studs | Process. |  | Cavity Prep for string assembly | Nuts removed from 8mm studs. | Technician injured her shoulder while trying to break loose and stubborn nut. | A ratchet wrench replaced the combination wrench providing more torque to loosen the nut.
pCM16 | 2016-05-11 | Cavity Assembly | String Assembly | Bleed-up cavities for HPR & BPM Sub-assembly | Tooling | BPM Magnet sub-assembly Traveler, String assembly Traveler | Slow Bleed-up |  |  | Prototype system was used, improvements were identified for production
pCM17 | 2016-05-11 | Cavity Assembly | String Assembly | Slow pump-down | Tooling | BPM Magnet sub-assembly Traveler, Cavity string evacuation and leak test | Slow Pump-down |  |  | The old system was used to manually throttle the pump-down curve. A prototype system has been assembled but time for proper testing was not available before prototype string use. A second cheaper system is proposed and in the works. Both systems will be tested so an automated pump will be ready for production.
pCM18
pCM19
pCM20
pCM21

## pCM Cold Mass I
LCLS II pCM Lessons Learned Log
2016-05-10
Rev. 0
ID | Date Entered | Work Center | Activity | Task | Category (Process, Procedure, Design, Tooling, Resources) | Affected Traveler | Affected Procedure | Effect | Cause | Mitigation or Recommendation
Ex. | 2016-05-10 | State which work center is responsible for the activity, e.g., Cavity Assembly | Identify the activity that was being performed, e.g., Cavity string assembly | Identify the specific task that was being performed, e.g., Attaching the FPC to cavity AES034 | Relate the issue to one of the categories | Identify the traveler that is associated with the task | Identify the procedure that is associated with the task | Describe the effect. An effect is something that is produced by a cause, e.g. The vacuum joint between the FPC and cavity AES035 leaked | Describe the cause. A cause is a person or thing that acts, happens, or exists in such a way that some specific thing happens as a result; the producer of an effect, e.g. The FPC flange was not properly aligned with the flange on the cavity | What corrective action was taken to mitigate the cause or what is recommended to be done
pCM1 | 2016-08-14 | CM Assembly | Tuner Installation | Installing limit switches | Procedure | L2PRO-CM-ASSY-SCND |  | Limit switch leafs were damaged, and needed replacement | Accidental contact with tools during tuner installation | Staff were instructed to take extra care when working around limit switches. A protective cover could be used to stop future issues
pCM1 | 2016-08-10 | CM Assembly | Tuner Installation | Installing Stepper Motor | Process | L2PRO-CM-ASSY-SCND |  | Motor was found to be defective at the final testing step, which required a time-consuming disassembly of the tuner | One of the wires in the motor was frayed by contact with the motor housing, causing a short | Each motor will be tested for motion at the time of installation, so that a replacement motor can possibly be installed without requiring the disassembly of the tuner
pCM1 | 2016-08-22 | CM Assembly | Tuner Installation | Installing limit switches | Procedure | L2PRD-CST-INSP-TUNMT |  | Several limit switches were found to be wired incorrectly; they needed to be repaired while installed on the string | Limit switches were incorrectly wired from the vendor | A check for limit switch wiring will be included in the Stepper Motor inspection traveler
pCM1 | 2016-08-14 | CM Assembly | Tuner Installation | Tuner Assembly | Process | L2PRO-CM-ASSY-SCND |  | Assembly work was held up due to two teams requiring the use of the same tool at the same time | Only one set of tools was available for two teams working simultaneously | Four sets of tools will be made available for tuner installation during production
pCM1 | 2016-10-12 | WS2 String on rails | Install/align magnet | Install the split magnet ass'y. The weight must be supported by the transfer carriage. | Resources - front face of two halves of magnet not flat | L2PRO-CM-ASSY-FRST -R1 seq 7 | Alignment and installation of magnet. | Magnet not properly aligned to bpm. | Quad magnet face was not planer | Shim Quad magnet face where it bolted to the BPM flange.
pCM1 | 2016-10-12 | WS2 String on rails | Install 50K shields | Install 50K shields on CPI couplers | Resources - | L2PRO-CM-ASSY-FRST -R1 seq 6 | Install 50K shields on couplers | Had to remachine interfacing parts | Production couplers were rejected and prototype CPI couplers used on two cavities | Use prototype CPI coupler and re-machine thermal shields
pCM1 | 2016-10-12 | WS3 - work under four poster | Weld UCM piping | Complete welds on 2 phase pipes | Resources would not work with process called out. | L2PRO-CM-ASSY-FRST seq 24 | Weld 2 phase piping | Could not use orbital welder on UCM piping | Pipe ordered would not weld properly with automated welder | Adjust the welding program, and occasional hand repair
pCM1 | 2016-10-12 | WS3 - work under four poster | Weld UCM piping | Complete welds on 2 phase pipes | Resources would not work with process called out. | L2PRO-CM-ASSY-FRST seq 24 | Weld 2 phase piping | Orbital welder could not be used on the cavity string welding | “T’s were hand ground and not machined. | Hand weld pipes.
pCM1 | 2016-10-12 | WS3 - work under four poster | Install HOM clamps. |  | Design - HOM clamps did not fit | L2PRO-CM-ASSY-FRST seq 34 |  | HOM clamps did not fit. | Interference between clamp and HOM load. | Modify HOM clamps to Rev A dwg.
pCM18
pCM19
pCM20
pCM21

## pCM Cold Mass II
LCLS II pCM Lessons Learned Log
2016-05-10
Rev. 0
ID | Date Entered | Work Center | Activity | Task | Category (Process, Procedure, Design, Tooling, Resources) | Affected Traveler | Affected Procedure | Effect | Cause | Mitigation or Recommendation
Ex. | 2016-05-10 | State which work center is responsible for the activity, e.g., Cavity Assembly | Identify the activity that was being performed, e.g., Cavity string assembly | Identify the specific task that was being performed, e.g., Attaching the FPC to cavity AES034 | Relate the issue to one of the categories | Identify the traveler that is associated with the task | Identify the procedure that is associated with the task | Describe the effect. An effect is something that is produced by a cause, e.g. The vacuum joint between the FPC and cavity AES035 leaked | Describe the cause. A cause is a person or thing that acts, happens, or exists in such a way that some specific thing happens as a result; the producer of an effect, e.g. The FPC flange was not properly aligned with the flange on the cavity | What corrective action was taken to mitigate the cause or what is recommended to be done
| 2016-10-12 | WS2 - work under four poster | Load center support post |  | design | L2PRO-CM-ASSY-SCND seq 4 |  | Center support post did not fit. | The support post was damaged. | The support post had to be remachined and load tested.
| 2016-10-12 | WS2 - work under four poster | Cryomodule assembly | Test magnet electrically prior to shield installation | Process- | L2PRO-CM-ASSY-SCND seq 44 | Refer to Hiatt | Short on magnet lead to cold mass. | Improper installation of conductor insulation | Disassemble clamp assembly and reinstall conductors and insulation
| 2016-08-03 | WS2 - work under four poster | Cryomodule assembly | string in place waiting for alignment | Resources?- Power removed | L2PRO-CM-ASSY-SCND |  | Ion pump shut down for 7 hours | power outage in test lab | Close valve, restart ion pump, re-establish vacuum, open valve
| 2016-10-12 | WS2 - work under four poster | Cryomodule assembly | Weld fill lines | Resources would not work with process. | L2PRO-CM-ASSY-SCND |  | Could not use orbital welder to make welds. | Orbital welder would not fit in fill line area. | Fill lines were not butt welded, instead couplers were used and hand welded.
| 2016-10-12 | WS2 - work under four poster | Cryomodule assembly | Align Cryo pipes at ends of CM | Design- pipes had bends in them | L2PRO-CM-ASSY-SCND seq 44 |  | Cryo pipes are not at transverse positions spec'd at ends. | Explosively bonded joints were not plumb. Resulting pipe bent. | Use as is. Risk of fracture in joint is high if pipe rebent.
| 2016-10-12 | WS2 - work under four poster | Cryomodule assembly | Align string to UCM | Process - Cavity moved on INVAR rod | L2PRO-CM-ASSY-SCND seq 27 |  | Cavity 1 moved in Z direction during alignment. | Vacuum load on cavities caused Cavity 1 to move on invar rod during alignment | Second friction clamp placed on Invar rod to restrain cavity 1 movement in Z direction.
| 2016-10-12 | WS2 - work under four poster | Cryomodule assembly | Install cold coupler heat stationing straps | Design - production strap assy's used on prototype | L2PRO-CM-ASSY-SCND seq 36 |  | Installed cu spacer bars on heat straps | Wanted better heat stationing for cold couplers so used production design. | CU interface plate installed between the flanged 50K shield pipe and the thermal straps
| 2016-10-12 | WS2 - work under four poster | Cryomodule assembly | Add Metglass to cover bearing supports | Design - wanted better mag shielding so added Metglas | L2PRO-CM-ASSY-SCND seq 40 |  | Installed additional Metglas over bearing blocks | Wanted better Magnetic shielding for cavities | Added Metglas covers to bearing supports
| 2016-10-12 | WS2 - work under four poster | Cryomodule assembly | Install 2K pipe | Procedure - hadn't been clear pipe slid in supports | L2PRO-CM-ASSY-SCND seq 44 |  | Needed to remove clamps and remachine contact surfaces | Jlab personnel did not realize pipe had to slide in clamps during cooldown. | Remove clamps and remachine contact surfaces. Reinstall.
| 2016-10-12 | WS2 - work under four poster | Cryomodule assembly | Install lower 50K shields | design | L2PRO-CM-ASSY-SCND seq 45 |  | 50K lower shields would not fit | 50K shields manufactured to early dwg revision | Remanufacture 50K shields to lates dwg revision
| 2016-10-12 | WS2 - work under four poster | Cryomodule assembly | Install lower 50K shields | design | L2PRO-CM-ASSY-SCND seq 45 |  | 50K lower shields would not fit | insufficient clearance from 50K shield to 1/4" Helium fill lines | Modify 50K shields to clearance to the 1/4" He fill lines.
pCM18
pCM19
pCM20
pCM21

## pCM VV Assembly
LCLS II pCM Lessons Learned Log
2016-05-10
Rev. 0
ID | Date Entered | Work Center | Activity | Task | Category (Process, Procedure, Design, Tooling, Resources) | Affected Traveler | Affected Procedure | Effect | Cause | Mitigation or Recommendation
Ex. | 2016-05-10 | State which work center is responsible for the activity, e.g., Cavity Assembly | Identify the activity that was being performed, e.g., Cavity string assembly | Identify the specific task that was being performed, e.g., Attaching the FPC to cavity AES034 | Relate the issue to one of the categories | Identify the traveler that is associated with the task | Identify the procedure that is associated with the task | Describe the effect. An effect is something that is produced by a cause, e.g. The vacuum joint between the FPC and cavity AES035 leaked | Describe the cause. A cause is a person or thing that acts, happens, or exists in such a way that some specific thing happens as a result; the producer of an effect, e.g. The FPC flange was not properly aligned with the flange on the cavity | What corrective action was taken to mitigate the cause or what is recommended to be done
|  | WS4 | MLI installation | MLI on JT valves | design | L2PRO-CM-ASSY-VV | MLI installlation | Avoid icing on JTs | Insufficient insulation. | used new MLI and heat stationing methods from FNAL
|  | WS4 | insertion of Cold mass into VV | Adjust support posts | procedure | L2PRO-CM-ASSY-VV | Install fixed support post assemblies. | Support post bound up during lift | Hardware not sufficiently loosened; small misalignment. | Emphasize need for hardware to be loosened fully before support post installation.
|  | WS4 | VV Inspection | Leak check VV | Procedure | L2PRO-CM-ASSY-VV |  | Fix welds on VV | Welds leaked | Leak check next VV
pCM18
pCM19
pCM20
pCM21

## pCM Final Assembly
LCLS II pCM Lessons Learned Log
2016-05-10
Rev. 0
ID | Date Entered | Work Center | Activity | Task | Category (Process, Procedure, Design, Tooling, Resources) | Affected Traveler | Affected Procedure | Effect | Cause | Mitigation or Recommendation
Ex. | 2016-05-10 | State which work center is responsible for the activity, e.g., Cavity Assembly | Identify the activity that was being performed, e.g., Cavity string assembly | Identify the specific task that was being performed, e.g., Attaching the FPC to cavity AES034 | Relate the issue to one of the categories | Identify the traveler that is associated with the task | Identify the procedure that is associated with the task | Describe the effect. An effect is something that is produced by a cause, e.g. The vacuum joint between the FPC and cavity AES035 leaked | Describe the cause. A cause is a person or thing that acts, happens, or exists in such a way that some specific thing happens as a result; the producer of an effect, e.g. The FPC flange was not properly aligned with the flange on the cavity | What corrective action was taken to mitigate the cause or what is recommended to be done
|  | Final assembly | Warm coupler installation | Installation | resources |  | Warm coupler installation | Insufficient warm production couplers available | Not sufficient production couplers qualified | Warm couplers cavs 1-4 are from RI, other half 5-8 are from CPI (Prototype)
|  | Final assembly | Warm coupler installation | Installation | design |  | Warm coupler installation | Warm couplers on cavs 5-8 were ~ ½” long, requiring some squash during Frisbee install | Cavitites 5-8 have prototype couplers from CPI | Use as is.
|  | Final assembly | Warm coupler installation | Installation | Berry bolt removal |  | Warm coupler installation | Redo wiring to sensors on warm coupler | Wires were taped to berry bolts, | broke wires to sensors on Cav 3, repaired(sensors were added to diff area)
|  | Final assembly | Warm coupler installation | Installation | Berry bolt removal |  | Warm coupler installation | 3 berrybolts were dremeled out | parts galled on cavity 3 | Don't use SS on SS next time
|  | Final assembly | End cap installation. | seal end cap to pCM | Design |  | End cap installation | End cap O-ring wouldn't seal | O-ring didn't fit; wouldn't seal | End cap O-ring groove remachined larger
|  | Final assembly | End cap installation. | seal end cap to pCM | Design |  | End cap installation | End cap O-ring wouldn't seal | End cap flange welding warped part | Duct seal pCM; remachine flange to be flatfor Production
pCM18
pCM19
pCM20
pCM21

## pCM Accept Test
LCLS II pCM Lessons Learned Log
2016-05-10
Rev. 0
ID | Date Entered | Work Center | Activity | Task | Category (Process, Procedure, Design, Tooling, Resources) | Affected Traveler | Affected Procedure | Effect | Cause | Mitigation or Recommendation
Ex. | 2016-05-10 | State which work center is responsible for the activity, e.g., Cavity Assembly | Identify the activity that was being performed, e.g., Cavity string assembly | Identify the specific task that was being performed, e.g., Attaching the FPC to cavity AES034 | Relate the issue to one of the categories | Identify the traveler that is associated with the task | Identify the procedure that is associated with the task | Describe the effect. An effect is something that is produced by a cause, e.g. The vacuum joint between the FPC and cavity AES035 leaked | Describe the cause. A cause is a person or thing that acts, happens, or exists in such a way that some specific thing happens as a result; the producer of an effect, e.g. The FPC flange was not properly aligned with the flange on the cavity | What corrective action was taken to mitigate the cause or what is recommended to be done
pCM18
pCM19
pCM20
pCM21