## Slide 1: Cold Mass Assembly Experiences and Lessons Learned
Quadrupole Magnet
  The quad magnet had an assembly problem which confused alignment; the two halves faces were not in plane
  We aligned the center of the quad to the centerline of the beamline and ignored the magnet faces. The magnet face was then shimmed where it bolted to the BPM flange
Cavity Magnetic Shields
  Two suppliers, different designs, each with special controls due to different permeability
  Modified all the magnetic shields (both vendors) prior to installation
Alignment
  Alignment of the string was more complicated than originally thought; Learning curve
  Added an additional clamp to hold cavity 1 to Invar rod against vacuum loading
HOM clamps
  Would not go on as originally designed and received
  Parts modified to last drawing revision to incorporate the thermal sensor and scallop feature

## Slide 2: Cold Mass Assembly Experiences and Lessons Learned
Helium Circuit Stainless Steel Pipe
  Pipe acquired by the project for the He piping did not work well with the orbital welder, surface finish not polished
  Sections of Helium pipes were hand welded
Vacuum Vessel
  The lifting fixture for the vacuum vessel was specified with slots for metric all thread supports, but SAE all thread ordered
  Modifications were made to lifting fixture and because it was part of a lifting fixture, Load test by an outside source was required
  The threads in VV for lifting rods were loose fit.
  Nuts placed on threaded rods after it passed through the lifting plate
  The vacuum vessel had a vacuum leak as received
  Leak welded shut. Leak check added to receipt inspection.

## Slide 3: Cold Mass Assembly Experiences and Lessons Learned
Power outage in Test Lab
  Ion pump on string lost power for 7 hours at work station 2
  Use procedure to restart pump. Put beamline ion pumps on emergency power.
Helium circuit pipes’ ends not in correct transverse positions
  Explosively bonded joints were not square. Resulting pipes ‘bent’.
  Risk of fracture in explosively bonded joint high if pipe re-bent. Use as is.
Tuners
  Limit switches were wired incorrectly from the vendor
  A check of the limit switch wiring will be included in the traveler
  A tuner motor was found to be shorted after assembly, requiring complete disassembly of the tuner
  Motors will be tested for shorts during the inspection traveler
  Only one set of tools available for two teams doing installation delayed work
  Four sets of tools procured and segregated for tuner installation

## Slide 4: Cold Mass Assembly Experiences and Lessons Learned
JT Insulation and heat stationing
  JT valve at FNAL exhibited icing during operation.
  Use production MLI and heat stationing design from FNAL for JT installation
VV to Cold mass Integration
  Support posts bound up during lift and mating operation
  Fully loosen alignment screws before integration.
  Support posts are heavy and difficult to lift above cantilever fixture
  Use separate chainfall to lift support posts into place
50K shields
  50K shields required re-machining to match new drawings
  Always use latest drawing revisions.
  50K shields did not clear ¼” Helium fill lines; potential heat leak
  Shields were modified to give more clearance and Helium lines were pushed up against the Helium vessel after welding.

## Slide 5: Cold Mass Assembly Experiences and Lessons Learned
Warm couplers
  Insufficient production Warm couplers available for prototype.
  Installed RI couplers on cavities 1-4; 5-8 are CPI prototypes.
  Sensor wiring damaged where they were taped to berrybolts
  Changed dressing of wiring in tuner area
  Berry bolts sheared during removal
  Remove pieces and change part call out to avoid SS on SS interfaces
End Cap Installation
  Coils installed on VV for demagnetization interfered with clamps used to hold the End cap and Bayonet box on the pCM
  Move coils from ends of pCM onto End Cap and Bayonet Box. Reused for final demag on all future cryomodules.
  Flange surfaces warped and would not seal.
  Duct seal for test and re-machine flange on second end cap for next test
  Shipping
  Insufficient room around shipping fixture on flat bed to safely install CM in-situ.
  Move shipping fixture to floor and install CM, then re-lift to truck bed. Load test of shipping fixture required.

## Slide 6: Cold Mass Assembly Lessons Going Forward
Warm couplers
  Bad coupling of tuning rod between warm and cold couplers.
  After pCM is warmed up, remove to work station 5 and disassemble to determine cause. Correct tooling, procedures, etc?
Heat Exchanger Can
  Borrowed heat exchanger bypass valve may have slowed cool down.
    Main cause was valve in u-tube that was incorrectly installed limiting flow rate. Problem has been corrected.
  New heat exchanger on order and will be delivered before next CM test with modified bypass valve (large Cv) as a mitigation
U Tubes
Return U tube valve may have slowed cool down.
Valve controller reset to vendor’s specification
Installing CM into CMTF
Impossible to have two modules at cave entrance and lift a module in simultaneously
Changed direction of module approach to cave from south to north