## Slide 1: 3.9GHz Cryomodule Assembly at Fermilab
Tug Arkan / Chuck Grimm
LCLS-II 3.9GHz CM Final Design Review
January 30-31, 2017

## Slide 2: Outline
    Production Strategy
    Fermilab Cryomodule Assembly Facility (CAF) infrastructure
    Detailed CM Assembly Workflow at CAF
    Travelers and Part kits
    Summary

## Slide 3: Planned LCLS-II Production CMs Workflow at Fermilab
Receive dressed, ready to be tested in VTS (vertical test stand) cavities from the vendors (Beamline under vacuum)
Incoming Inspection at IB4.
Test cavities in VTS at IB1
Qualified Cavities go to CAF-MP9 cleanroom for cold end coupler assembly (WS0). Non qualified cavities will be re-processed (HPR, light EP etc.) and re-tested.
One cavity out of every sixteen will be tested in horizontal test stand (HTS) . Other cavities still stay in the cleanroom and ready to be assembled into a cavity string.
8 qualified cavities, BPM, Gate Valves, Interconnecting Bellows/Spool: Cavity String Assembly at CAF-MP9 Cleanroom (WS1)
Cold Mass Assembly at CAF-MP9 (WS2)
Cold Mass Assembly at CAF-ICB (WS3 & WS4)
Final Assembly and QC checks (WS5) and prep for transport to CMTS at CAF-ICB (WS6)
Cryomodule Test at CMTS
Transport the module back to CAF-ICB (WS6)
Prepare and Ship Module to SLAC

## Slide 4: Supply Chain for Production CMs assembly at Fermilab
Dressed cavities delivered ready to be tested
Fundamental power couplers delivered ready to be assembled at WS0 and WS5
Gate valves (VAT) cleaned to Class 1000 standard at the vendor
BPM
Copper plated beamline components
Cavity String Assembly Hardware
Cold Mass Upper assembly (long lead procurement)
Cold Mass peripherals
Instrumentation
Vacuum Vessel (long lead procurement)
Vacuum vessel peripherals
Full or batch delivery Supply Chain Manager working with SOTRs & TD QMD for qualified parts storage in TD inventory system Parts are kitted & delivered to work stations Sort, magnetic hygiene QC, clean and use
Leverage from the supply chain experience gained during 1.3GHz CMs Production

## Slide 5: CAF-MP9 during LCLS-II Production
WS1
WS2
WS0

## Slide 6: CAF-MP9 Clean Room
Cavity String Assembly Clean Room
A ~2500 square-feet clean room:
  Class 1000 (ISO6) ante clean room area (36 ft. x 24 ft.)
    Preparation of the dressed cavities for transportation into the assembly clean room.
  Class 100 (ISO5) sluice area
    Parts and Fixtures final preparation to enter the Class 10 assembly area.
  Class 100 (ISO5) area ( 60 ft. x 12 ft.)
    Parts and Fixtures preparation for assembly.
  Class 10 (ISO4) assembly clean room area (60 ft. x 12 ft.)
    Where the cavities vacuum is vented to interconnect them with bellows.
Class 1000
Class 10
Rail
Class 100

## Slide 7: Cleanroom Infrastructure
Vacuum / Gas Manifold
Class 1000 softwall cleanroom for dry cleaning before entry to ante cleanroom
Particle Free UHV Pumps System
Boiled-off LN2 gas dewars and gas delivery panels
Cavity Support Fix Rail System
8 stations for pumping, purging and backfilling

## Slide 8: Tooling/Fixtures Strategy
Use 1.3GHz CM assembly fixtures/tooling as much as possible while reconfiguring to assemble 3.9GHz CM. Additional brackets, adapters are needed during reconfiguration.

## Slide 9: String Assembly Workflow
Receive dressed qualified Cavities
Receive/Clean peripheral parts/hardware
Assemble dressed Cavities to form a String in WS1
HTS tested
with FPC
No
Yes
Assemble cold end of FPC to the dressed cavity in WS0
Leak Check & Backfill
Roll the string out of the cleanroom to WS2

## Slide 10: Parts / Fixtures / Hardware Entrance to Cleanroom Preparation
Assembly hardware:
  Wash in the ultrasonic bath
  Dry under Class100 hood
  Move into the Class 1000 ante clean room
  Blow clean with ionized nitrogen while monitoring the particle count in the sluice area (Class 100)
  Transport into the Class 10 assembly area
Class 10 Hood
US cleaners
Electro-polished, rolled thread 316L stainless steel studs; silicon bronze nuts
Class 1000 softwall cleanroom
Magnetic Hygiene Quality Control for every part, hardware, fixtures, tools that will be used in the cleanroom for assembly prior cleaning

## Slide 11: Cold End Coupler Assembly (WS0)
Leak check, RGA the dressed qualified cavity (received with beamline under vacuum)
Assemble pump/backfill/purge flex hose to the cavity
Backfill the cavity
Leak check the coupler pair in the processing stand as delivered
Backfill
Remove a cold end coupler from the stand
Assemble cold end coupler to the cavity using particle free flange assembly (PFFA) procedures.
Pump down, leak check, RGA
Backfill

## Slide 12: String Assembly-I (WS1)
Rotational alignment of cavities
Gate Valve (GV1) to Cavity #1 Assembly:
  Check the particle free cleanliness of the GV and clean as needed
  Sub-assembly of the GV peripherals
  Installation to the support post and vacuum hose assembly
  Alignment to the cavity beam line flange
  Assemble the gate valve to the cavity

## Slide 13: String Assembly-II (WS1)
Cavity to Cavity Assembly with the interconnect bellows:
  Assemble flex hose to the cavity. Pump down and Leak check. Backfill
  Align the interconnect bellows to the cavity field probe end beampipe flange
  Assemble with PFFA
  Align the bellows to the cavity coupler end beampipe flange
  Assemble with PFFA

## Slide 14: String Assembly-III (WS1)
BPM+GV2 assembly and leak check
BPM/GV2 subassembly to the 8 cavity string
Pump down fully assembled cavity string, bag the bellows, leak check. Backfill
Roll out of the cleanroom to WS2

## Slide 15: CAF-MP9 During LCLS-II Production
WS1
WS2
WS0

## Slide 16: FNAL 3.9 GHz Cryomodule Assembly at WS2
After Roll-Out at WS1
Dressed Cavity Ordered Without Tee

## Slide 17: FNAL 3.9 GHz Cryomodule Assembly at WS2
2-Phase Line Welding
Same welding configuration and parameters.
Tee will be added as part of the procedure.

## Slide 18: FNAL 3.9 GHz Cryomodule Assembly at WS2
Tank Heaters
Heaters will be installed in this location
Along with Kapton tape and Stycast, Ti shim material will keep
heaters securely fastened to He tanks like 1.3GHz

## Slide 19: FNAL 3.9 GHz Cryomodule Assembly at WS2
Magnetic Shielding
Shields installed on the upstream and downstream ends and up the chimney – not on the outside center section
Internal He vessel shield will cover length of cavity end-to-end

## Slide 20: FNAL 3.9 GHz Cryomodule Assembly at WS2
Bladetuner Installation
Bladetuner and piezos installed at WS2, for 1.3 GHz lever tuner was installed at WS3.
Bladetuner has safety rods for safe transport
Safety rods

## Slide 21: FNAL 3.9 GHz Cryomodule Assembly at WS2
Upper Coldmass Attachment
Due to a slight interference issue with the bearing block leg and 2-phase chimney, the cavity string will need to roll upstream slightly on the lollipop stands than back downstream after clearing the chimney
Warm-up/Cool-down welding same as 1.3 GHz

## Slide 22: FNAL 3.9 GHz Cryomodule Assembly at WS2
Coldmass Transport to WS3 at ICB
Modifications to red fixture will allow use for 3.9 GHz upper coldmass move
1.3 GHz upper coldmass fixture
Same transport fixture will be used

## Slide 23: CAF-ICB during LCLS-II Production
Sick CM
repair area
WS4
WS3
WS5
WS6

## Slide 24: FNAL 3.9 GHz Cryomodule Assembly at WS3
Cavity String Alignment
Fiducials Glued on Beam Flanges
Laser Tracker
“Z” adjustment first
“X” and “Y” follow

## Slide 25: FNAL 3.9 GHz Cryomodule Assembly at WS3
Cavity String Alignment
Larger diameter prisms are more desirable
Cavity clamp to invar rod
“Z” tolerance +/- 1mm
Relative to FPC spacing
“X” tolerance +/- .075mm
“Y” tolerance +/- .075mm
Relative to electrical centerline of cavity
“X” offset is set at this WS

## Slide 26: FNAL 3.9 GHz Cryomodule Assembly at WS3
Thermal Straps and Cables
Similar to 1.3 GHz

## Slide 27: FNAL 3.9 GHz Cryomodule Assembly at WS3
Lower Thermal Shields Attached
Same setup as 1.3 GHz except coupler ports on opposite sides
Finger Welds

## Slide 28: FNAL 3.9 GHz Cryomodule Assembly at WS4
Insulation Wrap and Vacuum Vessel Integration
MLI wrap same as 1.3 GHz
Setup on fixture same as 1.3 GHz
Coldmass integration to vacuum vessel same as 1.3 GHz

## Slide 29: FNAL 3.9 GHz Cryomodule Assembly at WS4
Final Cavity Alignment and Cold Offset
Once the vacuum vessel and coldmass is leveled, the roll is taken out by adjusting the support nuts
Setup on fixture same as 1.3 GHz

## Slide 30: FNAL 3.9 GHz Cryomodule Assembly at WS4
Final Cavity Alignment and Cold Offset
Bring the cavity string beam axis to the designed z (longitudinal) position wrt vv by using the along the vessel push bolts.

## Slide 31: FNAL 3.9 GHz Cryomodule Assembly at WS4
Final Cavity Alignment and Cold Offset
Bring the 2 posts into a plane normal to local gravity and at such a height that the cavity string beam axis is at the designed dH vertical offset from the VV center. Use the up and down bolts.

## Slide 32: FNAL 3.9 GHz Cryomodule Assembly at WS5
JT Valve Welding
X-ray location
Final welded configuration
JT valve assembly same as 1.3 GHz

## Slide 33: FNAL 3.9 GHz Cryomodule Assembly at WS5
Warm End Coupler Installation, Waveguides, and Instrumentation
All final leak checks and pressures tests are performed at this workstation prior to move to CMTF
Same procedures as 1.3 GHz but installed on both sides due to alternating FPC’s
Final instrumentation connections

## Slide 34: CM Assembly Travelers
Electronic Travelers will be developed for CM assembly.
We will use vector.fnal.gov (see Jamie Blowers talk)

## Slide 35: Parts Kit Lists (MBOM)
Parts kit lists will be created
Parts/hardware will be stored at Technical Division (TD) Storage Areas and will be organized by the TD inventory management systems
When a kit is requested by the production floor, LCLS-II supply chain manager will ensure that the parts/hardware are kitted as specified and the kit is delivered to the specific work station
Excerpt from the 1.3GHz CM cavity string assembly at WS1 parts kit list

## Slide 36
LCLS-II Cryomodule Assembly Team
Lead
(T. Arkan)
(K. Premo), deputy lead
Fundamental Power Coupler
Cavity String Assembly @ MP9 [WS0, WS1]
(M. Battistoni)
M. Chlebek
B. Kuhn (C)
Alexey Akimov (C)
Cold Mass Assembly
@MP9 & ICB [WS2 ~WS5]
(G. Smith)
J. Wittenkeller
Ryan Thiede
James Focht (C)
Luis Bonilla
Technician (C)
Ryan Treece (C)
Jared Gaza (C)
M. Snyder (C)
Tuner
(Y. Pischalnikov)
RF
(T. Khabiboulline)
P. Berruti
M. Awida
Instrumentation
(D. Orris)
F. Lewis
P. Dubiel
D. Eddy
Electrical Tech (C)
Electrical Tech (C)
Alignment
(V. Bocean)
Technician
Technician
Crew Chief
QA/QC
(T. Beale)
Process Eng
(J. Szal)
Eng. Support
-E. Borissov
-Y. Orlov
-J. Kaluzny
-Y. He
-V. Roger
-J. Theilacker
J. Yun
Supply Chain Manager
(J. Rife)
Components Storage
(l. Peters)
Magnetic Hygiene
(S. Chandrasekan)
S
uppo
r
t
(C. Grimm), deputy lead
Welding
Andrew Penhollow (C)
Technician (C)
Technician (C)
Thermal Intercepts
(J. Kaluzny)
Magnet/ Current Leads
(A. Makarov)
Machine & Weld Shops

## Slide 37: Summary
CAF infrastructure is a proven, fully operational facility to assemble 1.3GHz and 3.9GHz cryomodules.
Each work station infrastructure is ready for the LCLS-II CMs assembly.
To date, we have assembled 1.3GHz pCM, CM02 is at WS3, CM03 is at WS2 and CM04 is at WS0
3.9GHz CMs will be assembled when we complete the 1.3GHz Production CM assembly at CAF. Trained and experienced technician workforce will be in place.
We plan to use the same tooling/fixtures from the 1.3GHz CM for 3.9GHz CM with reconfiguration strategy.

## Slide 38: LCLS-II Helium Vessel Production CM FDR
Thank You!