## Slide 1: FNAL 3.9 GHz Cryomodule Project Management
Camille Ginsburg
LCLS-II 3.9 GHz CM Final Design Review
January 30-31, 2017

## Slide 2: 3.9 GHz CM FDR Project Management Outline
Overview of the work scope
Technical status
Procurement plan
Organization and staffing
Cost and schedule data
Risks
Outline of the review
Summary

## Slide 3: Overview of the 3.9 GHz CM work scope
PL Management & Integration (1.04.05.01)
  Oversight and integration of all WBS 1.04.05 related activities
  Overall CM support in areas that include ES&H, QA/QC, and supporting engineering
  CM related travel M&S (including vendor visits)
Engineering & Design (1.04.05.05)
  Design 1.3GHz prototype and production cryomodules, and 3.9 GHz cryomodules
  Produce all necessary calculations, analyses, models, and drawings
  Perform design verification tests of cryomodule subcomponents
3.9 GHz Cryomodule Procurement and Fabrication (1.04.05.12)
  Procure materials, receiving/inspection, dressing, processing, and testing cavities, assembling and testing 3.9 GHz LCLS-II cryomodules assuming two(2) CM with eight(8) cavities in each CM
Infrastructure (1.04.05.15)
  Design, procure, install, and commission additional infrastructure required to produce and test the 1.3 GHz and 3.9 GHz cryomodules at rates consistent with the project schedule
  Includes infrastructure for VTS, HTS, Assembly and CMTS1
Installation Support & Shipping (1.04.05.20)
  Ship all CM’s from FNAL to SLAC including all fixtures and transport costs plus FNAL installation support
Notes: Review touches on 5 of my 11 control accounts

## Slide 4: 3.9 GHz cryomodule technical status
Based on 1.3 GHz experience, 3.9 GHz plan was fine-tuned
  Improved plan is now in the baseline
Cryomechanical design and component design nearly 100% complete
  Dressed Cavity FDR & CM PDR occurred in Nov.’15
Incorporated design verification plan for components (tuner, coupler, HOM couplers, thermal anchors, magnetic shielding)
  Note: these are standard Nb SRF cavities, not high-Q0
Optimized procurements so that low-risk or already established items are procured in advance of final design
Engineering Specification Document – currently under review
Next plans
  Design verification ongoing through mid-2017 (incl. integrated HT)
  CM Final Design Review – Jan.’17
Notes: Design and drawings done or nearly done:
Support posts (same as 1.3 GHz)
Support structure on the vacuum vessel which interfaces with the posts (same as 1.3 GHz)
Vacuum vessel nearly done (given priority due to the need for external interface information)
Cavity and magnetic shield (priority here to enable procurements for testing)
Helium vessels (so, with cavities and magnetic shielding, most of beamline string in done)
Instrumentation flanges (nearly identical to 1.3 GHz)
Tuner (early effort coordinated with helium vessel)
Still to be done:
Thermal shield (very similar to 1.3 GHz)
HGRP
Cryogenic piping (very similar to 1.3 GHz)
Coupler vacuum manifold.

## Slide 5: Microphonics
The 1.3 GHz prototype CM’s at both FNAL and JLab have high levels of microphonics; too high
Investigation and mitigation are ongoing at CMTS1
Any improvements to the 1.3 GHz cold mass internal support and cryogenic delivery system will be duplicated in the 3.9 GHz cryomodule

## Slide 6: 3.9 GHz CM Procurement Plan
3.9 GHz CM procurements are 31% complete, by cost
Sensitive Information Omitted for Online Posting

## Slide 7: FNAL CM Staff
Highly experienced staff who worked on prototype 1.3 GHz CM continue to work on 3.9 GHz and production CM’s

## Slide 8: 1.04.05 - FNAL Cryomodules - Summary Schedule
Status end July 2016
Sensitive Information Omitted for Online Posting

## Slide 9: WBS 1.04.05- Cryomodule – FNAL– BAC
3.9 GHz cryomodule design, procurement, assembly, test and shipping
3.9 GHz CM design and design verification primarily in FY17
3.9 GHz cryomodules are to be assembled and tested through FY18, after 1.3 GHz
Status end July 2016
Sensitive Information Omitted for Online Posting

## Slide 10: Risks & Risk Mitigations (High Impact) (1/2)
pCM Assembly | If pCM designs don't integrate as planned, THEN production assembly will be delayed | Develop Lessons Learned, Use prototype work to refine processes and design to reduce impact to production assembly. Revise tooling, update procedures, and revise QA/QC processes. cold test will give lessons learned, design changes and process improvements. | Fermilab pCM begins cold testing 09.2016 JLab pCM cold testing 10.2016.
Damage during shipping | If shipping subjects CM has extreme shock Then delivery will be delayed. | Other labs (DESY XFEL) have realized 2/101 failure without mitigations in place. SNS similar Perform dry-runs under realistic conditions. Investigate and determine alternate scheme. Shipping test March 2017. labs will need to store Cryomodules until OK. | Preliminary shipping test for Q1FY17
CM rework | Production Cryomodule fails test Then require rework/retest | Supply Chain, Defective Parts Include pre-production Cryomodule in project plan at each partner laboratory. Production plan includes longer duration for the first three Cryomodules to finalize assembly and QC procedures. | pCM almost complete 9/2016.
Title | IF/THEN | Mitigations | Schedule

## Slide 11: Risks & Risk Mitigations (High Impact) – (2/2)
JLAB Cryomodule test lab availability | If the CMTF is not available because of cryoplant refurbishment, then the project will experience delays in testing | Actively seeking other cryogenic facilities for backup testing, and evaluating testing cycles, assessing schedule impact. | CMTF cryoplant work is scheduled for early 2017. Integrated planning underway
Title | IF/THEN | Mitigations | Schedule

## Slide 12: Design Review Definitions (LCLSII-1.1-QA-0009-R0)
Preliminary Design Review [~30-50% Design Maturity]
  Documented technical and interface requirements
  Mechanical/structural/thermal design and analyses
  Preliminary layouts, drawings
  Reliability, maintainability
  Assessment of risk areas
  Plan for obtaining safety approval
Final Design Review [~90-100% Design Maturity]
  Requirements of PDR plus…
  Final detailed design
  Final implementation plans including engineering models, prototypes and spares
  Engineering model test results and design margins
Readiness Review
  Needed for authorization prior to construction activities
  Objectives, documentation, QA, safety, residual risk

## Slide 13: 1.3 GHz CM FDR Committee Charge - Overview
The LCLS-II 3.9 GHz cryomodule design is nearly completed, and thus ready for review.
The review committee is charged to evaluate the system design readiness to approve implementation, procurement, and fabrication activities.
This review focuses on the cryomechanical aspects of the design, since the RF component design verification tests (for dressed cavity, magnetic shielding, tuner and coupler) are ongoing.
The committee is requested to consider only the functional design and integration of these RF components into the cryomodule, and a follow-on review for these three elements will be held after design verification phase is completed.

## Slide 14: 1.3 GHz CM FDR Committee Charge - Detail
Technical Scope
Are the designs mature and technically sound to satisfy design specifications? – EH, YH, NS, GW
Is the design likely to meet performance expectations?
  Does the cryomodule cryogenic design meet the heat load requirements? – EH, YH, TP
  Would potential modifications to RF component designs after design verification tests significantly impact the CM cryomechanical design? EH, NS, GW
Have cryomodule assembly procedures and tooling been adequately developed? – TA/CG
Have shipping, rigging, and handling procedures been adequately developed? - MMcG
Have all the major interfaces been identified and incorporated into the design? - YH
All design specifications, requirements, performance, and interface documents reviewed, approved and released? - YH
Design Management
Is the design team organized and staffed to successfully complete the project? - CMG
Have all of the major risks been identified and managed? – CMG, JB
Are procurements appropriately planned? - CMG
Is the development of associated drawing packages sufficiently mature? JB, YH
Cost and Schedule: Is the cost and schedule reasonable to achieve the planned scope? - CMG
ES&H
Are all related ES&H aspects being properly addressed? – JB, JT
Has the appropriate failure modes and effects analysis (FMEA) been performed on the components and system? – JT, YH
Miscellaneous
Have all the previous design review action items/comments been addressed? - EH
Are there any other issues that have been identified that need to be addressed?
Overall Readiness: Is the design sufficiently mature so as to allow Final Design Review approval?

## Slide 15: 3.9 GHz Final Design Review Agenda
Welcome and safety – Stanek
Cryomodule (CM) design project management – Ginsburg
Cryomodule Functional Requirements - Harms
FNAL LCLS-II QA/QC program – Blowers
CM Cryomechanical Safety Framework - Theilacker
CM Cryomechanical Design – He
RF Component Design - Solyak
Design Verification - Wu
CM Heat Loads - Peterson
CM Assembly– Arkan / Grimm
CM Transportation – McGee

## Slide 16: 3.9 GHz Cryomodule Project Management Summary
3.9 GHz cryomodule
  Design well advanced
  Component design verification studies started
Experienced and available staff, proven infrastructure
Risk registry elements actively managed
Cost and schedule are well understood after pCM experience and substantial production 1.3 GHz CM procurements (~30% complete)
Lessons learned from 1.3 GHz are being incorporated into 3.9 GHz CM

## Slide 17: Acknowledgments
Tug Arkan, Anna Grassellino, Chuck Grimm, Elvin Harms, Yun He,
Josh Kaluzny, Matt Kramp, Jerry Leibfritz, Yuriy Orlov,
Tom Peterson (SLAC),
Yuriy Pischalnikov, Ken Premo, Nikolay Solyak,
Rich Stanek, Jay Theilacker, and Genfa Wu
provided information and slides for this presentation
We greatly appreciate the collegial collaboration with JLab; all relevant lessons learned are incorporated here
We have benefited hugely from collaboration with XFEL: DESY, INFN Milan/LASA, CEA Saclay
I am grateful for their assistance