## Slide 1: Q1 Status Report and Forecast – RFQ
James Steimel
PIP-II Quarterly Progress and Forecast Review
27, January, 2017

## Slide 2: RFQ Schedule Status
What is the primary driver for the change in the schedule for the first primary goal above?
  Input couplers have not been reliable for CW operation. Two, original couplers had vacuum failures during CW operation.
  Also, the priorities for PIP2IT were recently changed to make proof of CW operation less critical before commissioning cryomodules.

## Slide 3: RFQ Financial Status Discussion
Has a funding change request been submitted for the increase in FTE/SWF and M&S, and what are the impacts if not granted?
  Yes, funding change request has been submitted for design and construction effort for input couplers. Without the funding, we will be forced to commit to pulsed RF and beam operation on PIP2IT through commissioning of the cryomodules.

## Slide 4: Other Questions, Comments for RFQ
If applicable, is your EPDM up to date? If no, provide brief explanation on why.
  Yes.
For beam operation into the HWR cryomodule, RFQ needs to be retuned to a higher resonant frequency. This will involve machining 80 tuners to extend an extra 1mm into RFQ. This has been tabled until FY18.