## Slide 1: LBNL’s WPC Journey
2009
2014
2016
2017
Feb 2009
  HSS audits LBNL and concludes in April report that WPC is less than adequate
2010
  Benchmarking and planning
2011
  Kick off system design and development
Nov 2014
  Site-wide roll out.. followed moments later by site-wide feedback… followed days later by system enhancement initiative
Mid 2016
  Implement assurance mechanisms
2010
2011
Mar 2016
  Full transition to new system
2015
Feb 2017
  Kick off ISM initiative
Notes: Purposefully slow and careful. This was the biggie out of all of the HSS audit findings and the one we had to get right. (just as with electrical safety, had history of doing half-baked jobs and committed to getting this right)
Kick-off had both a policy group of senior mgt. and a user group. Crucial that they were involved all along the way. Did Agile development – lots of commitment from that group on the sprints.
Some important budget milestones. Idea of minimum viable product (MVP) came up somewhere along 2014.
For full transition – ~1,700 activities; 6,000 people, 30%/40%/30% Risk Level breakdown, fewest activities by division 1 (HR), most activities by division 180 (ALS). This was way, way, way beyond what we expected. Also, all 1700 were essentially done from ground up – relatively little cut/paste jobs. Essentially did a site-wide risk assessment!!!!!! We did this purposefully as a long transition – no big bang!!!!
Along the way, solicited lots of feedback internally from users (surveys, net promoter scores, self-assessments, …) and externally (met with ANL, SLAC, LLNL, LANL, PNNL, ORNL, etc.); this continues to this day – still receiving feedback about efficiency of the system.
Some aspects contributing to success, flexibility of the system (users take ownership to configure it to work for them), graded approach, intuitive (if young), …
Went from adoption metrics and tool efficacy metrics (year of the transition) to ISM metrics (which brings us back to the original goal of the project!).