## Slide 1
Bruce Hanna
PIP-II Risk Workshop
Thursday 4/6-4/7/2017
PIP-II Project Risk: Design/Construction of a QPM System for Superconducing Magnets in PIP-II

## Slide 2: Risk Summary: Opportunity or Threat
Risk Owner: Bruce Hanna
The PIP-II Project plans to have the EE Support group design and build quench protection systems for all superconducting magnets in PIP-II
  Supply all components and interfaces to turn off and decay current so as to protect the magnets
Risk Cause:
  Modifying existing HINS QPMs is more extensive or not feasible
Risk Effect:
  Will require a new design. This means we would need to identify an engineer and technicians to do the design, prototyping and construction of the QPMs

## Slide 3: Risk: Probability, Technical Impact
QPMs needed for HWR, SSR1 and SSR2 cryomodules
  Will they be the same or will SSR2 have different needs than SSR1 and HWR
Probability
  20%
Technical Impact
  Low
Risk Rank
  1 (Low)
Cause or Trigger
  Modifications/testing of existing HINS QPM, future quench analysis

## Slide 4: Risk: Cost Impact and Estimate
Cost Impact: (Two Point)
  5 to 50 k dollars
Estimate:
  Cost of existing HINS QPM approximately $7,000
  Cost of knowledgeable EE- Support technician
  If necessary, cost of EE Support Engineer
Quality of Risk Estimate
  Guess based on manpower needs to build HINS QPM.

## Slide 5: Risk Mitigation
Project will soon begin modifications and testing of HINS QPM. Additional quench analysis will be performed by Technical Division
Start Date:
  May 1 is when EE Support personnel are potentially available to work on modifications and software for our QPM.
End Date:
  September 31 (end of Fiscal year 2017)
Monitoring Required:
  PIP-II group will monitor progress