## Slide 1
Bruce Hanna
PIP-II Risk Workshop
Thursday 4/6-4/7/2017
PIP-II Project Risk: Design/Construction of a QPM System for Superconducing Magnets in PIP-II

## Slide 2: Risk Summary: Opportunity or Threat
Risk Owner: Bruce Hanna
The PIP-II Project plans to have the EE Support group design and build quench protection systems for all superconducting magnets in PIP-II
  Supply all components and interfaces to turn off and decay current so as to protect the magnets
Risk Cause:
  Modifying existing HINS QPMs is more extensive or not feasible
Risk Effect:
  Will require a new design. This means we would need to identify an engineer and technicians to do the design, prototyping and construction of the QPMs

## Slide 3: Risk: Probability, Technical Impact
QPMs needed for HWR, SSR1 and SSR2 cryogenic magnets
  Will they be the same or will SSR2 have different needs than SSR1 and HWR
Probability
  20%
Technical Impact
  Low
Risk Rank
  1 (Low)
Cause or Trigger
  Modifications/testing of existing HINS QPM, future quench analysis

## Slide 4: Risk: Cost Impact and Estimate
Cost Impact: (Two Point)
  10 to 50 k dollars
Estimate:
  Cost of existing HINS QPM approximately $7,000
  Cost of knowledgeable EE- Support technician
    2months time $17 k
  If necessary, cost of EE Support Engineer
    1 month time  $20 k
Quality of Risk Estimate
  Guess based on manpower needs to build HINS QPM.

## Slide 5: Risk Mitigation
Project will soon begin modifications and testing of HINS QPM. Additional quench analysis will be performed by Technical Division
Testing of QPMs at PIP-II IT
Start Date:
  May 1 is when EE Support personnel are potentially available to work on modifications and software for our QPM.
End Date:
  September 31 (end of Fiscal year 2017) (for modifications/tests of prototype)
  PIP-II IT testing complete mid 2022
Monitoring Required:
  PIP-II group will monitor progress

## Slide 6
Bruce Hanna
PIP-II Risk Workshop
Thursday 4/6-4/7/2017
PIP-II Project Risk: SSR1 QPM Inadaquate

## Slide 7: Risk Summary: Opportunity or Threat
Risk Owner: Bruce Hanna
The PIP-II Project Quench protection for SSR1 solenoid magnets
  Original design required a dump
  New Cryo Magnetics design has cold diodes
  Have quenched magnets at test facility
Risk Cause:
  Planned QPM system does not include a resistive dump; if a Quench analysis shows one is needed we will need to modify the QPM
Risk Effect:
  Inadequate quench protection can result in damage to the magnet.

## Slide 8: Risk: Probability, Technical Impact
A quench analysis will be done for SSR2 solenoids. As a check the analysis will be used for SSR1 solenoids where we have quench results.
  If we determine that voltages or temperatures could exceed limits we may need to add a dump.
Probability
  10%
Technical Impact
  Low
Risk Rank
  1 (Low)
Cause or Trigger
  Quench analysis will indicate if this is necessary

## Slide 9: Risk: Cost Impact and Estimate
Cost Impact: (Single Point)
  $20 k
Estimate:
  Estimated cost of HINS dump= $1 k each.
  Estimated technician cost = $15,000.
Quality of Risk Estimate
  Guess based on manpower costs and old POs for dump parts.

## Slide 10: Risk Mitigation
Project will work with TD and AD engineers to determine if we need to make changes based on SSR1 quench analysis.
Performance in PIP-II IT.
Start Date:
  Summer of 2017 (Quench analysis begins).
End Date:
  Mid 2022 (PIP-II IT complete)
Monitoring Required:
  Periodic contact with TD engineers
  QPM performance at PIP-II IT

## Slide 11
Bruce Hanna
PIP-II Risk Workshop
Thursday 4/6-4/7/2017
PIP-II Project Risk: Quench Calculations and QPM System

## Slide 12: Risk Summary: Opportunity or Threat
Risk Owner: Bruce Hanna
It is planned to perform Quench calculations on superconducting solenoids
  SSR1 as a check
  SSR2
Risk Cause:
  Calculations may show 1) that our QPM system is not adequate for SSR1 solenoids and 2) that dumps may be needed for SSR2
Risk Effect:
  Could result in the need for modifications or redesign of QPM system. May show the need to include a dump (SSR2)

## Slide 13: Risk: Probability, Technical Impact
Calculations could indicate the need for a dump system. This may require modifications to the QPM and modification or design of a dump
Probability
  80%
Technical Impact
  Will need to look at existing HINS dump to see if it is useable
Risk Rank
  2 (Medium)
Cause or Trigger
  Calculations indicate damage to coils during a quench

## Slide 14: Risk: Cost Impact and Estimate
Cost Impact: (Single Point)
  20 k dollars
Estimate:
  Cost of HINS dump
  Cost of knowledgeable EE- Support technician
  Possible need for design engineer
Quality of Risk Estimate
  Rough guess based on documentation for HINS dump.

## Slide 15: Risk Mitigation
A thorough quench analysis needs to be done for both SSR1 and SSR2 solenoids.
Start Date:
  Summer 2017
End Date:
  December 2017
Monitoring Required:
  Monitored as new information becomes available