## Slide 1
Bruce Hanna
PIP-II Risk Workshop
Thursday 4/6-4/7/2017
PIP-II Project Risk: Quench Calculations and QPM System

## Slide 2: Risk Summary: Opportunity or Threat
Risk Owner: Bruce Hanna
It is planned to perform Quench calculations on superconducting solenoids
  SSR1 as a check
  SSR2
Risk Cause:
  Calculations may show 1) that our QPM system is not adequate for SSR1 solenoids and 2) that dumps may be needed for SSR2
Risk Effect:
  Could result in the need for modifications or redesign of QPM system. May show the need to include a dump (SSR2)

## Slide 3: Risk: Probability, Technical Impact
Calculations could indicate the need for a dump system. This may require modifications to the QPM and modification or design of a dump
Probability
  80%
Technical Impact
  Will need to look at existing HINS dump to see if it is useable
Risk Rank
  2 (Medium)
Cause or Trigger
  Calculations indicate damage to coils during a quench

## Slide 4: Risk: Cost Impact and Estimate
Cost Impact: (Single Point)
  20 k dollars
Estimate:
  Cost of HINS dump
  Cost of knowledgeable EE- Support technician
  Possible need for design engineer
Quality of Risk Estimate
  Rough guess based on documentation for HINS dump.

## Slide 5: Risk Mitigation
A thorough quench analysis needs to be done for both SSR1 and SSR2 solenoids.
Start Date:
  When appropriate people become available.
End Date:
  2019
Monitoring Required:
  Monitored as new information becomes available