## Slide 1
Shekhar Mishra
PIP-II Risk Workshop
Thursday 4/6-4/7/2017
PIP-II Project Risk: Currency Fluctuation

## Slide 2: Risk Summary: Opportunity or Threat
Risk Owner: Steve Holmes
The PIP-II Project plans to purchase from international suppliers
  Nb,
  superconducting cavities, and
  cryogenic equipment
Risk Cause:
  If the value of the U.S. dollar relative to the local currency changes in a significant manner, the cost of components supplied by international vendors could decrease,
Risk Effect:
  Enhancing (Jeopardizing) the ability to the Project to meet cost and schedule goals.

## Slide 3: Risk: Probability, Technical Impact
Since 2014 US $ has become stronger with respect to Euro and Yen.
  These rates are defined by monitary policies and politics.
Probability
  50%
Technical Impact
  Negligible
Risk Rank
  2 (Medium)
Cause or Trigger
  International Policies of the US government, market conditions

## Slide 4: Risk: Cost Impact and Estimate
Cost Impact: (Single Point)
  +/- $2.5M
Estimate:
  The U.S. dollar has fluctuated about 5% over the last two years wrt the Euro.
  Total international purchases for PIP-II are going to be in the range of $50M.
  Thus the total exposure is roughly $2.5M with a 50/50 chance of an upward vs downward fluctuation.
Quality of Risk Estimate
  Reasonable based on market data of past 10 yrs.

## Slide 5: Risk Mitigation
Project will work with the purchasing office to place all the international contracts in US $.
Start Date:
  CD3A  When the Project plans to starting placing all major international order(s).
End Date:
  2022  By this time Project should have placed all the order
Monitoring Required:
  Continuous by the Project Office